SIXTH FRAMEWORK PROGRAMME

Research Infrastructure – Communication Network Development

Contract for:

SPECIFIC SUPPORT ACTION

Annex I - “Description of Work”

Project acronym: CYCLOPS

Project full title: CYber-Infrastructure for CiviL protection Operative ProcedureS

Proposal/Contract no.: 031874

Related to other Contract no.: Not Applicable

Date of preparation of Annex I: 13th March 2006

Start date of contract: 1st June 2006

# Table of Contents

Table of Contents	2

1.	Project summary	3

2. Project objective(s) and state of the art	3

3. Participants list	15

4. Relevance to the objectives of the specific programme and/or thematic priority	15

5. Potential Impact	17

5.1 Contributions to standards	18

5.2 Contribution to policy developments	19

5.3. Synergies with other relevant projects	20

6. Project management and exploitation/dissemination plans	21

6.1 Project management	21

6.2 Plan for using and disseminating knowledge	24

6.3 Raising public participation and awareness	26

7. Workplan– for whole duration of the project	26

7.1 Introduction - general description and milestones	26

7.2 Work planning and timetable	33

7.3 Graphical presentation of work packages	33

7.4 Work package list	35

7.5 Deliverables list	36

7.6 Work package descriptions	38

8. Project resources and budget overview	54

8.1 Efforts for the project	54

8.2 Overall budget for the project (Forms A3.1 & A3.2 from CPFs)	57

8.3 Management level description of resources and budget	58

9. Other issues	60

Gender issues	60

Appendix A - Consortium description	61

A.1 Participants and consortium	61

A.2 Sub-contracting	73

A.3 Third parties	73

A.4 Funding of third country participants	73

Appendix B -  Glossary	74

Appendix C – EGEE Support Letter	76

Appendix D – Description of Relevant Projects	78

D.1 Project LessLoss	79

D.2 Project RiskEOS	81

D.3 Project PREVIEW	85

D.4 Project RISK-AWARE	94

D.5 Project AMPHORE	98

# Project summary

The Global Monitoring for Environment and Security (GMES) concept was endorsed by the EU Commission in 2001 with the aim of “establishing by 2008 a European capacity for Global Monitoring of Environment and Security” to gather and use all available data and information in support of sustainable development policies. GMES has the potential to stimulate economic growth by creating innovative value-added services. The challenge for GMES is to use these services to enable decision makers to better anticipate or mitigate crisis situations and management issues related to the environment and security. The Final Report for the GMES Initial Period recognised the European Civil Protection (CP) as one of the GMES service categories. This report outlines the importance to develop enabling e-infrastructures and virtual organisation services to serve specific GMES applications. Indeed, the EU EGEE (Enabling Grids for E-Science in Europe) project provides a powerful GRID platform to implement services for specific application Communities. However, GRID evolution has mainly focused on technology, while, GMES services have mostly been user-oriented. Thus, there is a need to cross-disseminating the approaches, requirements and visions of the diverse Communities, in order to fully exploit the GRID capabilities for GMES applications. CYCLOPS brings together these two important Communities: GMES and GRID, focusing on the operative sector and needs of European CP. The main objectives of CYCLOPS are:

1) To disseminate EGEE results to the CP Community, assessing EGEE infrastructure for CP applications. A variety of activities will focus on dissemination and outreach, training, workshops, possibly in close relation with EGEE events and on promoting a close collaboration between the two communities.

2) To provide the EGEE Community with knowledge and requirements that characterise the CP services. These requirements will also be used to assess the possibility for the development of an advanced grid platform enabling Real Time and near-Real Time services and implementing a security infrastructure very close to the defence systems standards.

3) To evaluate the possibility to utilise the present EGEE services for CP applications, developing the research strategies to enhance EGEE platform.

4) To develop the research strategies to enhance EGEE platform, especially for Earth sciences resources.

CYCLOPS will contribute to the EU policy developments establishing liaisons and synergies with other existing projects and initiatives dealing with GMES, GRID and complementary sectors, among them: PREVIEW, Risk EOS, RISK-AWARE, BOSS4GMES, EGEE Networking Activities and Application Support, e-IRG and INSPIRE. In fact, Consortium partners are involved in all these projects and initiatives.

# 2. Project objective(s) and state of the art

### The Context and state-of-the-art

The Global Monitoring for Environment and Security (GMES) concept was endorsed by the EU and European Space Agency (ESA) Councils in 2001. In its Communication to the EU Gothenburg Summit (2001) the Commission called for “..establishing by 2008 a European capacity for Global Monitoring of Environment and Security”. GMES initiative has now reached a stage of maturity, ready for its development and implementation phase, with service provision for different areas becoming operational in a staged approach. GMES has been selected as one of the “Quick Start” projects in the Commission’s Initiative for Growth.

GMES is a highly innovative research initiative, driven by the needs of end users; first steps will concern the full exploitation of currently available data (either archived or provided by ongoing and impending Earth Observation missions) in order to suit needs posed by end-users’ applications. Full exploitation of data and resources will necessarily require their mutual sharing, which will impact consistently on economic aspects. GMES must provide a structured framework for data integration and information management (i.e. a European shared information capacity). The following key architectural requirements must drive GMES implementation: interoperability, scalability, dependability, data security, quality of service, ubiquity of access.

This is reckoned in the final document of the implementation plan ("Final Report of GMES Initial Period" (2001-2003).  In the same report, the GMES service categories for the period 2004-08 were introduced, Civil Protection is one of them. The importance of Civil Protection, in the European context, was also, reaffirmed by the decision 2001/792/EC - Official Journal L 297 of 15.11.2001, which supplements the Community action programme in the field of civil protection (2000-2004). The aim is to improve the coordination of assistance intervention in the event of natural, technological, radiological, ecological or environmental disasters, including serious marine pollution, occurring inside or outside the Community. On the 10th of November 2005, the European Commission adopted a new Communication on “Global Monitoring for Environment and Security (GMES): From concept to reality”. This Communication plans to introduce the first three earth observation services that have been identified for ‘Fast Track’ treatment: Emergency Response, Land Monitoring and Marine Services. In particular, the Emergency Response service aims to reinforce the European capacity to predict and respond to crises and emergencies associated with natural and man-made disasters such as: meteorological-driven hazards, e.g. storms, fires, floods; geophysical hazards, e.g. earthquakes, tsunamis, volcanic eruptions, landslides; technological disasters, whether deliberate or accidental, e.g. urban fires, chemical accidents on industrial sites; humanitarian disasters generated by sudden natural, technological and weather driven disasters. In the long run, the proposed service will guarantee that Europe can provide adequate information system capabilities to support early warning, urgent assistance, relief operations, humanitarian aid, reconstruction wherever and whenever they may by required around the world.

Grid paradigm is another technological and economic revolution in high performance distributed computing as the World Wide Web has been since the last ten years for what concerns the meaning and the availability of a global information. Grid-based platforms will allow the implementation of widely distributed computing environment operated as a uniform service.

In 2003, within the FP6 Research Infrastructure program, the EU approved the EGEE (Enabling Grids for E-Science in Europe) project, which aims to integrate current national, regional and thematic Grid efforts, in order to create a seamless European Grid infrastructure for the support of the European Research Area. After less than one year, the EGEE computing Grid is now operating and includes more than 100 sites in 31 countries. This makes it the world's largest international scientific Grid. Such an occasion of progress for the whole European Society must be leveraged by important and strategic sectors like GMES, and in particular Civil Protection operative infrastructures: Civil Protection organization, is a typical example of virtual organization and its system infrastructures need high performance distributed computing environment to share critical data and resources.

Civil Protection, as well as most of GMES services, require a strict integration with research infrastructures providing heterogeneous and distributed resources (e.g. computing, data, services, knowledge, expertise, etc.) useful in the full cycle of emergency situations (i.e. forecasting,  warning, management, assessment). Moreover, Civil Protection and GMES activities typically involve many different actors (e.g. Civil Protection systems, public bodies, research centers, etc.) who need to share resources in a coordinated and effective way. In this document, the term “CP community” is used to describe this community as a whole, since Civil protection Agencies sensus stricto act as leaders in GMES as well as in this project Grid infrastructures offer useful services to face these needs. Indeed, grid technologies are designed just to allow the coordinated sharing of resources (i.e. computing, storage, communication and sensors) needed by Virtual Organizations (VOs) such as Civil Protection systems. Consequently the adoption of a Grid-based infrastructure to support GMES applications seems a natural choice.

Current Grid platforms were mainly designed to support research and applications requiring intensive processing and data management, thus they offer high computing and storage capabilities. Only in recent times Grid research is facing new problems like sensor interaction and communication quality of service. They need an enhancement to support new kinds of applications such as Civil Protection.

Indeed, Civil Protection applications have specific requirements that are not commonly satisfied by typical research infrastructures.

These requirements (e.g. real-time support, sensor control functionalities, geo-information sharing services, advanced policy and security support) have a strong impact on research strategies (i.e. new data models, algorithms, methodologies need to be investigated) and consequently on the enabling research infrastructures (i.e. new protocols, services and architectures must be designed and experimented).

### CYCLOPS Objectives

Taking into account the previously described context, the main goal of the present Specific Support Action is to bridge the gap between Grid and GMES communities making Civil Protection people be aware of the services provided by Grid infrastructures, and, at the same time, letting Grid researcher to be aware of Civil Protection specific requirements and service enhancement needs.

CYCLOPS will bring together these two important Communities: CP and GRID, creating a fruitful interaction between Civil Protections agencies, experts of CP Information Technology requirements and Grid/EGEE community, in order to have an effective synergy guiding the development of future Grid research infrastructures and studying the feasibility of getting them run onto the European Grid Infrastructure.

CYCLOPS will provide a support action to the EGEE and EGEE-2 I3 projects in order to utilize its platform in the Civil Protection community.

The Main Goal represents a really general objective. To carry out effective actions toward it, this main goal is translated in six Project Objectives (PO):

PO_1) To assure effective project management

PO_2) To assure effective technical activities

PO_3) To assure quality of the results

PO_4) To define CP community requirements for Grid platforms

PO_5) To carry out CP and Grid communities inter-dissemination

PO_6) To prepare for future innovation and R&D projects

The Project Objectives define what CYCLOPS will do in the framework of the Main Goal. They are designed in terms of the six key criteria that are considered fundamental for the success of the project:

- Relevance to the Objectives of the Programme

- Potential Impact

- Quality of the Support Action

- Quality of the Management

- Mobilisation of the resources

The first three POs aim to assure the overall quality of the project, while the last three ones aim to define which results the project will carry out in respect of the Main Goal. In particular:

PO_1 (To assure effective project management) aims to assure an effective project management to satisfy the Quality of the Management criterion;

PO_2 (To assure effective technical activities) aims to satisfy the Mobilisation of resources criterion.The Support Action specific objectives (see PO_4 to PO_6) are carried out mainly through technical activities such as performance of studies and analyses, development of research or innovation strategies, dissemination actions. Thus an action of monitoring and coordination of the human resources (working group) is needed. CYCLOPS defines a specific PO for assuring the human resource  effectiveness of the technical activities carried out in the framework of the project.

PO_3 (To assure quality of the results) aims to satisfy the Quality of the Support Action criterion. Since CYCLOPS activities are mainly carried out by expert groups, the quality of the support action strictly depends on the expertise and involvement of the expert group members.

PO_4 (To define CP community requirements for Grid platforms) aims to satisfy the Relevance to the Objectives of the Programme criterion. Taking into account the Objectives of the Programme (see section 4) the main PO concerning it is the definition of the CP community requirements for Grid Platforms.

PO_5 (To carry out CP and Grid communities inter-dissemination) and PO_6 (To prepare for future innovation and R&D projects) aim to satisfy the Potential Impact criterion. Being an SSA, CYCLOPS effectiveness and potential impact strongly depend on the inter-dissemination between the CP and Grid communities and on the preparation of exploitation strategies through innovation and R&D projects that CYCLOPS studies could start.

These Project Objectives are translated in Operational Goals (OG) which are reached carrying out specific Tasks. The Operational Goals define the actions and the expected results of CYCLOPS as regards the relative PO.

Fig. 1 depicts a diagram of such decomposition showing the Main Goal, the Project Objectives (highlighting the key criteria they are relative to), the Operational Goals and the Tasks collected in Work Packages (described in the WP forms).

Fig. 1 Project Objectives diagram

### Operational Goals description

The Operational Goals define what CYCLOPS will carry out as regards its Project Objectives. In the following forms, each Operational Goal is briefly described showing the means planned to achieve it, how its progress is measured and how its success is estimated.

To monitor the project progress and results, each workpackage will devote some resources to assessment and evaluation activities. The WP leaders will report the results of such activities to the Project Management Board that is responsible of monitoring the overall progress and taking actions to respond to possible deviations and problems.

| OG_1.1 | Advanced Management |
| --- | --- |
| Description | An important objective goal for the CYCLOPS success is to set up an advanced project management. Project management aims to plan and organize effort to accomplish the expected CYCLOPS results Monitoring progress, tracking deliverables and reporting back to the EC and partners, actions carried out with: - permanent monitoring of the situation with reliable information; - Establish clear visibility in the content of work for any partner; - Nominate package leaders with high responsibility delegated; - Limit the interfaces and simplify links for driving and reporting. The project has been broken down in to 5 workpackage series, allowing clear responsibility distribution and coherence. Project management includes also developing CYCLOPS project plan Another important aspect address the project plan implementation, along with careful controls to stay on the "critical path", that is, to ensure the plan is being managed according to plan. |
| Means to achieve it | Project plan implementation is carried out through the day-by-day activities required for the project management. In order to facilitate the management, there will set up a collaborative environment: specific tools for enabling collaborative working. These instruments will be set up and managed to facilitate the working group activities. In particular the following services will be made available: - project web site; - mailing lists and discussion forums; - project document repository; - collaborative editing environment; - audio/video conferencing tools. |
| Measure of progress | PM 1 D1 Project Presentation PM 2 D3 Perspectives on cooperation with existing projects and initiatives PM 3 M1.3 Project ready to start support activities |
| Measure of success | The timely delivery of CYCLOPS products (i.e. deliverable, Web site, publications, etc.); The effectively organization of CYCLOPS events (e.g. tutorials, workshops, etc.). The success rate for internal conflict resolution. |

| OG_2.1 | Resources setup for Technical Activities |
| --- | --- |
| Description | In order to assure an effective mobilization of resources, CYCLOPS must setup a successful working group which is in charge of carrying out any support activities concerning the project tasks. |
| Means to achieve it | To establish a high level working group: at least one member of each partner is part of the WG. The WG can be further divided into work teams for accomplish well-defined sub-tasks. The WG consults the expert groups on specific issues. |
| Measure of progress | PM 1 M1.2 Working Groups set up |
| Measure of success | The timely accomplishment of CYCLOPS tasks; The success rate for technical conflict resolution; The effectively use of allocated resources. |

| OG_3.1 | Expert Groups setup |
| --- | --- |
| Description | In order to provide a good quality support action, CYCLOPS must rely on high level competences on present Civil Protection structures and procedures, as well as applied technologies for risks prevention and management. |
| Means to achieve it | Definition of a Civil Protection Expert Group (CPEG). Typically, one member for each Civil Protection, involved in the project, is part of the CPEG. The CPEG provides knowledge about the typical business processes and internal procedures of the different Civil Protections involved in the project. Definition of a Technical Expert Group (TEG). The TEG is composed of members carrying expertise on information and communication technologies (ICT) applied to the following specific sectors: Environment, Earth Observation and Civil Protection. Actually, the TEG provides the knowledge about technologies and resources available –or needed- for Civil Protection applications. |
| Measure of progress | PM 3 M1.3 Project ready to start support activities |
| Measure of success | The timely setup of CPEG; The representativeness of the CPEG experts; The timely setup of TEG; The representativeness of the TEG experts |

| OG_4.1 | To analyze CP agencies systems |
| --- | --- |
| Description | In order to define the requirements of Civil Protection community for Grid platforms, CYCLOPS will first analyse the heterogeneous European Civil Protection needs and available resources; then, it will provide common use cases and system requirements. |
| Means to achieve it | Heterogeneous Civil Protection systems, infrastructures, operational structures and procedures will be captured and described. Then, common or visionary use-cases, representative of typical scenarios of Civil Protection, will be achieved. On the top of it, common requirements will be worked out. In particular, the following analyses will be used to achieve this goal: Business Process analysis: a Business Process analysis of the Civil Protections systems active in the partner countries. This analysis should highlight the internal processes and the interactions with external entities such as public bodies, research centers, data and knowledge providers. Cross-boundary activities will be particularly considered. Existing Analysis: to collect information about the resources (information systems, communication services, computing resources, etc) commonly used by the different Civil Protection systems involved in the project; Use-cases analysis: to identify and describe a set of significant use-cases that could be ported, improved or even made possible by using Grid technologies. The objective of this study is to help in the definition of the system requirements. System Requirements Analysis: functional and non-functional requirements of a Grid-based infrastructure for enabling Civil Protection applications, based on the previous analyses results. This study is the basis for researches on grid infrastructure addressed by future projects. |
| Measure of progress | PM 5 - D6 Business Process analysis document released PM 6 - D8 Existing Analysis document released PM 7 - D9 Use-cases document released - M3.1 Civil Protection System description available PM 10 - D11 System Requirements document released - M3.2 System Requirements available |
| Measure of success | - Number and significance of Civil Protection Agencies and systems surveyed; - Number and significance of Civil Protection Business Processes analysed; - Number of Cross-boundary activities considered. - Number and significance of use cases worked out; - Number and significance of functional and non-functional requirements achieved. |

| OG_4.2 | to define Request for Enhancements for EGEE platform |
| --- | --- |
| Description | To assure the Relevance to the Objectives of the Programme is the target of the definition of Civil Protection requirements for Grid platforms. In particular this Operational Goal concerns the Requests for Enhancement for EGEE platform to make possible the support of Civil Protection applications on the top of it. |
| Means to achieve it | This Operational Goal is achieved through several activities. First of all the EGEE middleware is installed at the CP sites for test purposes. Then, basing on the System Requirements analysis a study is performed about the integration of the Civil Protection framework with the EGEE middleware. This is a preliminary activity to highlight weaknesses of current EGEE platform in supporting CP applications. After that, basing on the results of T3.1 (Business Process analysis) the EGEE needed extensions are analyzed. Finally, the possible implementation (porting) of existing Civil Protection applications on the enhanced EGEE infrastructure is analyzed. |
| Measure of progress | PM 13 M4.1 EGEE infrastructure deployed PM 15 M4.2 EGEE Integration analyzed PM 16 M4.3 EGEE enhancement analyzed D14 “EGEE Request for Enhancement” document released PM 18 M4.4 Application porting analyzing |
| Measure of success | - Number of EGEE installations. - Peer-review of deliverables from EGEE members. |

| OG_5.1 | Tutorial on EGEE platform for Civil Protection agencies |
| --- | --- |
| Description | The first CYCLOPS operational goal to have an effective inter-dissemination between Civil Protection and Grid communities is the presentation of EGEE platform to possible users. This is intended to provide an example of Grid platform to evaluate and test its capabilities in the GMES context considering the Civil Protection applications. |
| Means to achieve it | One of the member of CYCLOPS consortium is also member of the EGEE consortium (INFN). INFN experts will organize dissemination and training events open to Civil Protection personnel to present the current EGEE architecture and its planned evolution |
| Measure of progress | PM 7 First Training Workshop PM 13 Second Training Workshop |
| Measure of success | - Number of training events. - Number of attenders at training events. - Questionnaire for self-evaluation of training events. |

| OG_5.2 | Civil Protection framework and EGEE coordination |
| --- | --- |
| Description | A fundamental aspect of GMES and Grid communities inter-dissemination is the knowledge exchange with EGEE, the main Grid project at European level. To enhance the potential impact of CYCLOPS a specific operational goal is the coordination between EGEE project and the development of the framework for the applications of Grid technologies to the Civil Protection context. CYCLOPS members developing the Civil Protection Grid framework must be kept continuously updated about new EGEE middleware functionalities implemented by the EGEE project, at the same time need to give feedback to EGEE developers highlighting the weakness encountered in the Grid middleware and suggesting possible improvements for satisfying their requirements. |
| Means to achieve it | One of the member of CYCLOPS consortium is also member of the EGEE consortium (INFN). INFN experts will provide the needed link between the project. They will present the new EGEE middleware functionalities to the CYCLOPS expert group and will report the Civil Protection requirements to the EGEE developers. |
| Measure of progress | PM23 D17 dissemination and coordination activity final report released |
| Measure of success | Number and impact of feedback provided by CYCLOPS to EGEE. Timeliness of information about new EGEE middleware functionalities implemented by the EGEE project. Peer review of deliverables. |

| OG_5.3 | To define dissemination activities |
| --- | --- |
| Description | Organize the activities to be performed in order to distribute adequate knowledge from the project and promote the exploitation of the results by the widest Civil Protection and GMES community and interest in Europe The actions are expanded towards a wide range of existing public bodies, national and local decision makers, users and scientific society, data and product providers, EC and general RTD sector, industry in order to enhance the potential of the solutions for safety improvement and let them share an interest in the success of this initiative, delivering technical and operational outcomes. |
| Means to achieve it | Organization of a project open conference, a project final workshop, a mid-term project workshop and a, two Self Training Workshop Participation to other relevant conferences There are a great number of events, conferences, seminars, workshops taking place all over Europe focusing Grid technology. The partners have to careful choose those events which seem most appropriate to meet their objectives, for example those organized by the following entities: users (civil protection units), scientific community and researchers, strategic bodies (EC DG, OECD…), disaster reduction initiatives (ISDR), GMES forum, space agencies addressing the space applications development, national institutions (ministries). The content of the CYCLOPS presentations will reflect the goals of the project and its progress. Partners will make contributions to appropriate publications that provide high impact opportunities, like users periodical journals, annual reports, risk assessment publications, and research published papers. Civil Protection representatives will facilitate contacts and access to the civil security official publications and newsletters. Results may reach researchers and research groups active in the related areas. These contributions will be coordinated and reviewed by the CYCLOPS management and all published information will include contact details and the web site address from where further information can be obtained. The project will implement and maintain a web site for global information dissemination. The web site plays the important role of being the main communication tool and, providing suitable access restriction, the main repository of information about the project activities as well. |
| Measure of progress | PM1 - D2 Project open conference PM3 - M5.1 Dissemination started - D4 Dissemination Plan released PM12 - D12 Mid-term project workshop PM 23 D18 Project results presentation released D19 Final Plan for using and disseminating knowledge released D20 Report on raising public participation and awareness released D21 Project final conference PM 24 M5.2 Project results disseminated |
| Measure of success | - Number of public bodies, national and local decision makers, users and scientific society, data and product providers who will participate to the project open conference and the couple of workshops foreseen. - Number and role of people who will attend the project tutorials. - Number and appropriateness of national and international conferences to which CYCLOPS will present its activity. - Number of accesses to the CYCLOPS Web site. - Number of downloads of CYCLOPS documents, published on-line. |

| OG_6.1 | To define exploitation strategies |
| --- | --- |
| Description | The success of CYCLOPS Project is strongly dependant on the exploitation of its results. Indeed, as a support action, the number and quality of following initiatives is the real measure of its success. Thus, a detailed exploitation plan is considered a valuable resource to enhance the impact of the project. The exploitation plan will consider a wide range of initiatives built on the top of CYCLOPS output such as R&D project startup (funded by national or international bodies), cooperative research activities, SMEs and GEs involvement, coordination actions for existing projects (both at European and international level). |
| Means to achieve it | The exploitation plan will be defined through the activity of a working group made of representative of both Civil Protection and Grid communities. The exploitation plan will take into account the results of the dissemination activities considered useful to build a community made of research centers, public bodies, enterprises and interested in Grid applications for Civil Protection. |
| Measure of progress | PM23: - D19 Final Plan for using and disseminating knowledge released |
| Measure of success | - Number and impact of proposed R&D activities. - Impact of SMEs and GEs involvement. - Impact of coordination actions for existing projects (both at European and international level). - Peer review of deliverables |

| OG_6.2 | To carry out perspective studies for future innovation and R&D projects |
| --- | --- |
| Description | CYCLOPS aim to provide studies that could be the base for future R&D projects in the field of Grid technologies applied to the GMES context and for defining the innovation strategies for Civil Protection as regards the Grid technology adoption. In particular, a deliverable called “Research Strategies for the development of a Civil Protection E-Infrastructure” collects the open issues on the application of Grid technologies to the Civil Protection context, providing the directions for targeted projects. These studies could be useful both for EGEE middleware development and for new R&D projects. A deliverable called “Toward a Grid - Guidelines for Innovation Strategies for Civil Protection Systems” collects the requirements for the adoption of Grid technology in the context of Civil Protection agencies taking into account the existing and required resources. |
| Means to achieve it | The studies are carried out through the activity of expert groups made of members with expertise in Civil Protection management and in Grid and Information & Communication Technologies. In particular the results of an User Requirement Analysis, and the analysis of the problem of porting Civil Protection applications in a Grid platform will be specifically considered. Concerning the innovation strategies, the results of an Existing Analysis and a technical requirements analysis will be considered. |
| Measure of progress | PM20: - Operational Goal achieved - D15 “Toward a Grid - Guidelines for Innovation Strategies for Civil Protection Systems” report released - D16 “Research Strategies for the development of a Civil Protection E-Infrastructure” report released - M4.5 Research and innovation strategies investigated |
| Measure of success | Number and significance of open issues on the application of Grid technologies to the Civil Protection context provided. Impact of provided directions for targeted projects dealing with application of Grid technologies to the Civil Protection. Number and importance of provided requirements for the adoption of Grid technology in the context of Civil Protection agencies. Peer review of deliverables |

# 3. Participants list

| Partic. Role | Partic. No. | Participant name | Partic. short name | Country | Date enter project | Date exit project |
| --- | --- | --- | --- | --- | --- | --- |
| CO | 1 | Dipartimento della Protezione Civile | DPC | IT | 1 | 24 |
| CR | 2 | Istituto Nazionale di Fisica Nucleare | INFN | IT | 1 | 24 |
| CR | 3 | Istituto di Metodologie per l’Analisi Ambientale | IMAA | IT | 1 | 24 |
| CR | 4 | Direction de la Défense et de la Sécurité Civiles | DDSC | FR | 1 | 24 |
| CR | 5 | Civil Protection of Chania Prefecture | CP-CH | GR | 1 | 24 |
| CR | 6 | Technological Educational Institute of Crete | TEI-CR | GR | 1 | 24 |
| CR | 7 | Serviço Nacional de Bombeiros e Protecção Civil | SNBPC | PT | 1 | 24 |

*CO = Coordinator

CR = Contractor

# 4. Relevance to the objectives of the specific programme and/or thematic priority

As stated in the Work Programme 2004-2006 about Structuring the European Research Area, within the Sixth Framework Programme, the objectives of the Communication Network Development (CND) scheme, in support of existing Research Infrastructures, is to create, in conjunction with the priority thematic research area on Information Society Technologies (IST), a denser network between related initiatives, in particular by establishing a high-capacity and high-speed communications network for all researchers in Europe (GÉANT) and specific high performance Grids and test-beds (GRIDs). Broadband communication networks and Grid technologies are keys for the development of the Research e-Infrastructure, enabling collaborative work and resource sharing among researchers spread across Europe. For what concern the GRIDs area of work, the CYCLOPS project aims to address the following general objectives indicated by the CND scheme:

- ensure that Grid infrastructures exhibit production-level performance capabilities and constitute themselves distributed facilities at gigabit/terabit scales (in terms of computing, storage and communication power) for use by a broad range of different research disciplines;

- promote complementary work vis-à-vis national Grid-Programmes in Europe in view to add value to national Grid-initiatives and support the creation of a network of (e.g. National) Grid Support Centres in Europe;

- emphasise the integration of access facilities and interfaces/portals into core Grid infrastructure environments (e.g. wireless-devices, sensors);

- address and integrate both supercomputing and distributed computing technology, concepts and resources;

- foster interoperability across heterogeneous technology domains and interoperability of solutions across different disciplines in an effort to achieve broader scale uptake of Grid technology across numerous user communities;

In particular, within the GRIDs area of the CND scheme, the CYCLOPS project is actually placed in the sub-area of work called eInfrastructure-Consolidating Initiatives, where it will contribute to the following additional specific objectives:

- the reinforcement of the user communities engagement (e.g. social sciences, humanities and education; astronomy; environment; earth observation, biomedicine etc);

- the reinforcement and stimulation of eInfrastructure policies for science and engineering, and policy based management actions and tools (e.g. authentication, authorisation, ICT-resource sharing, security, registries/repositories of resources and policies etc).

The CYCLOPS project, in complementing the EGEE I3 project, clearly matches all of the above general objectives, in fact:

- Civil Protection community will fully exploit the existing EGEE Grid infrastructure, testing the quality of the middleware services, providing continuous feedback to EGEE architects, and helping to find common solutions in order to enhance the production-level capabilities of the e-Infrastructure;

- the participation of Civil Protection agencies of different European countries to CYCLOPS project will assure the interconnection among their national Grid initiatives;

- the wide use of  sensor networks and data acquisition systems is typical of Civil Protection applications: the CYCLOPS project will provide a valuable set of requirements in order to integrate these new access facilities into the EGEE platform;

- specially for complex simulation tasks, supercomputers are often needed for the most demanding computations: the CYCLOPS project will deal with the issue of integrating supercomputing and distributed computing technologies, always selecting the best computational solutions for their applications;

- Actually, Civil Protection applications adopt several different technologies, but need to cooperate to accomplish their tasks: it means that a coordinate way to share their resources by mean of Grid Virtual Organisations is not enough, but also interoperable solutions among heterogeneous technologies are required and will be investigated within the CYCLOPS project.

The more specific objectives relevant for the eInfrastructure-Consolidating Initiatives will be fully addressed by the CYCLOPS project work-plan, for the following reasons:

- the Civil Protection community, after defining the requirements for a Grid-based infrastructure satisfying their needs, will evaluate and test the EGEE platform, taking advantage from the dissemination activity of the EGEE results planned by the CYCLOPS project. The dissemination activity is usually the first step in the process of engaging new user communities for the eInfrastructure, it provides the general picture and introduces state of the art Grid technologies and services covering a broad range of scientific and technological areas, highlighting the benefits every community can obtain from joining a Grid computing infrastructure. A second step, also planned by the CYCLOPS project, consists in the evaluation and testing of the EGEE platform carried out by experts in Civil Protection applications. This activity will bring the potential users of these communities deep into the technical details, giving them, as a training process, the proper knowledge and the skills to use the Grid computing infrastructure. These pioneer users can act then themselves as further dissemination vectors within their communities. They not only will assess the power of the Grid computing, but also eventually identify critical areas where their specific requirements are not yet fully addressed by the current platform, giving valuable feedback to EGEE community and developing strategies in order to enhance the eInfrastructure and enable it for Civil Protection applications, stimulating an effective synergy between the CYCLOPS and the EGEE projects;

- among the high priority issues of the Grid computing concerning the overall management of the eInfrastructures certainly are the definition of the Acceptable Use Policy (AUP) for the eInfrastructure, and the definition of a policy for Authorization and Authentication (AA), commonly agreed for accessing and sharing in a controlled way the computing, data storage and networking resources geographically distributed across different administrative domains. Security of course plays a key role in attracting new user communities other that eScience, for example from industry, business, finance and defence, since their activities often require secrecy and privacy. The interaction with military resources typical of Civil Protection systems sets new strict data policies and security requirements on the ICT-resource sharing, putting the CYCLOPS project in the position of stimulating and guiding the reinforcement of the global eIfrastructure policies and policy based management actions and tools, according to the objectives of the CND scheme. Again, it will produce an effective synergy between the CYCLOPS and EGEE projects, which is the goal of the complementary activities supported through the Specific Support Action instrument adopted.

# 5. Potential Impact

The current  EGEE platform is based on the middleware developed by several pioneering projects, most notably DataGrid, where the main focus was put on enabling to Grid computing the data intensive scientific applications in the fields of High Energy Physics, Earth Observations and Genomic Exploration. Their requirements lead to a platform designed to handle the processing of a large amount of distributed data, ranging in size from 0.1 to 10 PetaBytes/year, exploiting the sharing of computing, storage and network resources in a coordinated way.

Civil Protection applications will certainly benefit from the above design, nevertheless they also have specific requirements not yet or only partly addressed within the EGEE platform. They concern the integration of sensor networks and acquisition systems, the data policy and security support management, the communication quality of service. The impact of the CYCLOPS project in the area of Grid computing research will be then of great value. The project will provide useful inputs to the EGEE community: a set of use-cases representative of typical scenarios of Civil Protection activities will establish the e-Infrastructure functionalities which are suitable to satisfy their requirements. Besides missing needs specific of Civil Protection community will be outlined. The impact will be strong on both sides: data models, algorithms and methodologies typical of Civil Protection applications could be reviewed to better adapt and exploit the Grid functionalities already available through the EGEE platform; new research strategies will be defined to plan an enhancement of the EGEE platform in order to fully support Civil Protection applications.

As far as Grid infrastructures are concerned, other national and international research activities will be taken into account by means of the tight collaboration with EGEE Project which deals with creating a European Grid infrastructure.

As far as similar initiatives in the field of Civil Protection are concerned, Civil Protection agencies involved in CYCLOPS Project will provide the necessary liaisons.

Interoperability solutions and Grid infrastructures represent an important opportunity to expand knowledge in the monitoring and security sectors and to enable new applications (especially in relation to 3D and 4D process modelling using Real-Time and Near-Real-Time data): from this perspective, there exists a direct connection between GÉANT, EGEE and GMES. Therefore, this unique opportunity can be realized only in carrying out the work at a European level (as it is the dimension of GÉANT, EGEE and GMES).

## 5.1 Contributions to standards

Being a Project mainly concerned with dissemination and outreach activities, CYCLOPS will not directly contribute to develop any standards in grid computing. However, from one side CYCLOPS, trough the INFN, will closely follow the activity of the Global Grid Forum and other standardization activities, such as those of OMII Europe, and, from another side, CYCLOPS will early adopt, test and validate, the middleware re-engineered by EGEE and EGEE-2 in compliance with the current open standards. In this way, CYCLOPS will actively participate in requirements capture and feedback on the middleware, standards and protocols, but also Grid management tools. Via this feedback through EGEE and EGEE-2, CYCLOPS will indirectly contribute to international standards.

Being IMAA an active member of the Open Geospatial Consortium (OGC), Cyclops may profitably contribute to several areas of OGC standardization activity.

OGC is a non-profit, international consortium of more than 270 companies, government agencies and universities, that is leading the development of standards for geospatial and location based services. Through a member-driven consensus programs, OGC works with government, private industry, and academia to create open and publicly available interface specifications so as to promote interoperability of geographic information and "geo-enable" the Web, wireless and location-based services, and mainstream IT.

In particular, some of the anticipated Cyclops results may be proposed as OGC Discussion Paper to germane OGC Working Groups, such as the following:

- Risk and Crisis Management Working Group, set to improve the efficiency and effectiveness of users in each phase of the risk and crisis management life cycle and across the risk and crisis management community through changes and extensions to OGC specifications;

- Sensor Web Enablement Working Group, focused on developing standards to enable the discovery and exchange of sensor observations, as well as the tasking of sensor systems;

- Earth Observation Working Group, particularly involved in the G8-sponsored initiative for the implementation, in the next 10 years, of a Global Earth Observation System of Systems (GEOSS), which will provide the institutional mechanisms for ensuring the necessary level of coordination, strengthening and supplementation of existing global Earth observation systems, and for reinforcing and supporting them in carrying out their mandates.

Moreover, Cyclops results may be contributed to the ongoing activities for setting up the Infrastructure of Spatial Information in Europe (INSPIRE), an initiative that aims to establish a base collection of standard technical rules, policies and institutional arrangements and to facilitate discovery, evaluation, application of (existing digital) geospatial and environmental data for users and providers within all levels of government, the commercial sector, the non-profit sector, and academia and by citizens in general.

## 5.2 Contribution to policy developments

Being a sister Project of EGEE, CYCLOPS will closely follow the international policy developments made in the context of EGEE Network Activity and Application Support and e-IRG.

CYCLOPS will also contribute to policy developments via a number of its internal activities:

- Enhancing collaboration between national protection communities, thus paving the way for educational, scientific and cultural exchanges, initiatives and projects across the borders.

- Stimulating the sharing of the know-how in terms of Grid computing among the partners.

- Facilitating research activities over a number of scientific sectors linked to the national protection, by providing access to the nascent e-Infrastructures to a wide spectrum of applications.

- Encouraging the interaction of research communities and governmental bodies with the aim of gaining long-term support for e-Infrastructures. CYCLOPS aims to trigger these actions by involving the participating countries in latest developments and e-Infrastructure practices in computing and e-Science.

The project is expected to improve the following knowledge-based society indicators along 3 distinct lines: 1) Providing cheaper, faster, secure and immediate access to computing and storage resources; 2) Investing in people and skills; 3) Exploiting the network infrastructures provided by GEANT and GEANT2.

CYCLOPS will contribute to the GMES initiative, with particular attention on Long Term Sustainability issues, as far as the Civil Protection sector is concerned: this action will be pursued by disseminating and reusing CYCLOPS analyses and results at both the National and European level. In fact, the CYCLOPS Civil Protection agencies are fully part of the GMES working groups at the European level and are involved in GMES activities. For example, DPC and IMAA are involved in the Italian steering committee for the GMES programme and are part of European-funded projects on GMES (e.g. BOSS4GMES, OASIS, EURORISK-Preview).

CYCLOPS will contribute to the INSPIRE initiative, as far as the ESDI (European Spatial Data Infrastructure) design and development is concerned. This action will be pursued by disseminating and reusing CYCLOPS analyses and results at both the National and European level in the INSPIRE framework. DPC and IMAA are among the initiator of an INSPIRE SDIC (Spatial Data Interesting Community) which is focused on GMES and INSPIRE technology harmonization, with particular attention on Grid solutions. Experts of such SDIC are experts of the Drafting Teams which have been working on the INSPIRE Implementing Rules.

## 5.3. Synergies with other relevant projects

Several partners of CYCLOPS Consortium are active in other relevant EC-funded projects in the Civil Protection, GMES and GRID sectors. Whereby, CYCLOPS will establish close relationships and synergies with the following projects: PREVIEW (in the context of DG INFSO and DG RECH), RiskEOS Stage 2 (in the context of Programme ESA GMES Service Element), EGEE/EGEE-2 (in the context of DG INFSO) and RISK-AWARE and AMPHORE (in the context of INTERREG III B). Full description of these projects objectives are included as annexes.

When feasible and opportune, CYCLOPS will plan its workshops and training events in close connection with analogous initiatives promoted by PREVIEW, RiskEOS, EGEE/EGEE-2 and RISK-AWARE.

CYCLOPS is a sister project of EGEE and will closely follow the international policy developments made in the context of EGEE Network Activity and Application Support and e-IRG. New developments and technological decisions taken by EGEE Consortium will be promptly presented to CYCLOPS Technical Management Board by INFN which is part of EGEE. Moreover the INFN, holding the main responsibility for the middleware development within EGEE, will play a key role in triggering the required improvements of the Grid-based

infrastructure for enabling CP applications to run on the Grid environment. CYCLOPS dissemination activity towards GRID Community will be pursued in close synergy with EGEE, e.g. scheduling CYCLOPS activity presentations at the main EGEE events. Furthermore, INFN will pursue the needed steps inside EGEE to allow CP community to be acknowledged as a new EGEE Virtual Organisation.

As far as INTERREG III B projects are concerned (i.e. RISK-AWARE and AMPHORE) they will provide useful support to collect requirements from the operative Civil Protection infrastructures for cross-borders use cases.

PREVIEW and CYCLOPS will share the following common strategic objective: to enlarge as much as possible the list of target users so that these projects can collect their needs, inform them and disseminate projects’ results as largely as possible in Europe in the framework of FP6. The aim is to create the demand, in terms of GMES risk information services (e.g. GRID-based ones), and push for deployment of such services at medium to long term. In PREVIEW and CYCLOPS this objective has the leadership of Civil Protection partners, respectively: the PREVIEW “User Task Force” and the CYCLOPS “Civil Protection Expert Group (CPEG)”.

GMES RiskEOS and CYCLOPS will collaborate on the same strategic objectives, previously described for PREVIEW, but in this case focusing on ESA-GMES community. In GMES RiskEOS this objective has the leadership of the “User Executive Body”.

Therefore, PREVIEW “User Task Force”, GMES Risk-EOS “User Executive Board” and CYCLOPS CPEG will establish a strong synergy and a close relationship for: collecting needs, inform Civil Protection Community and disseminate projects results. Besides, CYCLOPS management will invite representative European Civil Protection experts, who are involved in PREVIEW and Risk-EOS, to join the CPEG.

It is noteworthy that the DDSC acts as: Risk-EOS “User Executive Board” coordinator, PREVIEW “User Task Force” coordinator and CYCLOPS “Civil Protection Systems Analysis” work package leader.

CYCLOPS partners are also involved in other interesting projects of the Space Research and Applications sector, which are still in the negotiation phase, such as: LIMES and BOSS4GMES. In the due course, synergy actions could be planned with these projects, too.

In general, synergies with existing projects from Unit F3 'Research Infrastructures' will be sought at clustering and concertation events organised by the Commission according to the Special Clause 3bis on Clustering and concertation:

“In order to assure coherence of the work within the specific programme and its relevance in worldwide developments, the contractors will be required to participate in periodic cross-dissemination meetings together with other related projects. When applicable, the contractors of these projects shall collectively discuss common approaches to standardisation activities. The concertation activities related with the project clusters foresee up to four meetings per year with the presence of project representatives. Interest groups clusters will be flexible and will be organised by the Commission services if added-value is demonstrated and if they answer a particular need for action in relation to a clearly identified and targeted theme.” [Decision DL/2003/3004]

# 6. Project management and exploitation/dissemination plans

## 6.1 Project management

### General description

The CYCLOPS project is designed to link with related initiatives at the National level (an important task of National Civil Protections member of the consortium) and the trans-national EU-funded EGEE project, in particular. Given the close relationship to EGEE project, we propose to manage the CYCLOPS project using a management structure similar to EGEE one. This approach has the main benefit to fully exploit the complementarities of these projects.

The Management of the project is designed to deal with the problem of a number of geographically distributed partners with light project management resources. To meet this challenge the management of individual work-packages has been devolved to experienced work-package managers, appointed by the lead partner in each of the work-packages. Another important role of CYCLOPS management will be to ensure the effective and enabling availability of the work developed by EGEE and by the useful initiatives at the National level. Eventually, a key task of CYCLOPS management will be the set up of working and expert groups (i.e. civil protection and technical expert groups).

Communication between all participants will be via electronic mail and the use of audio/teleconferencing to reduce time lost through travelling and travel expenses to a minimum. The Project Manager will ensure that digests of communication between partners are transferred to the project’s Web site providing easily accessible information on the current activities of all partners. The project will make use of common styles for deliverables etc.

The work package managers and project manager will generate quarterly progress reports. These reports will indicate the progress made in each task and the resources consumed.

Project meetings will be organized every six months. The result of these meetings and the quarterly progress reports will be used as input into the annual EU review of the project.

The project manager will organise project meetings and the annual EU reviews.

### Detailed project management structure

The project management will be organized with the following structure:

- A project manager (PM), nominated by the coordinating partner to run the project on a day-to-day basis.

- A Project Management Board (PMB) composed of one management representative of each partner and the PM. The PMB will supervise the project from the political and administrative points of view. PMB will co-ordinate and manage items that affect the contractual terms of the project.

- A Technical Management Board (TMB), comprising of one representative from each Work Package (normally the WP manager), to take decisions on technical issues.

- A leader for each work package: the WP manager.

#### Project Manager

Implementing decisions taken by the management board, the Project Manager will undertake the following tasks:

- To be in charge of communication between the project and the EU.

- To be in charge of taking decisions between board meetings.

- To be in charge of organizing links with other related or relevant Projects on both sides of the Atlantic and related activities.

- To be in charge of ensuring that Intellectual Property Rights (IPR) and knowledge issues will be properly addressed.

- To be in charge of all administrative management tasks.

The PM will report to the PMB.

#### Project Management Board

The project management board will address strategic and contractual decisions concerning the project, supervising it from the political and administrative points of view. It will be composed of one management representative from each partner and chaired by an elected chairperson to be appointed annually. The project manager will act in support  of the board. The management board will take decisions affecting the budget and the objectives of the project, changes and dissemination agreements. All partners will have the right to vote.

#### Technical Management Board

The Technical Board will take day-to-day technical decisions on analysis and methodologies to be used. When necessary, experts (e.g. from application fields or technical expert groups) can participate to Technical Board decisions. Technical Board will report to the management board. In coordination with the project manager, the technical board will be responsible for the overall technical management and execution of the project: fixing the study and analysis strategy, the choice of methodologies and techniques to be used, supervising the monitoring of the results and coordinating the quality assurance function.

The technical board will be responsible for monitoring the quality and timely production of deliverables. It will propose corrective action (to the management board) in the event that partners fail to meet their commitments.

The technical board will be composed of one representative from each Work Package (normally the WP manager), to take decisions on technical issues; The technical management board will nominate a chairperson among its members who will be responsible for reporting to the PMB.

#### Working Group

The Working Group is made of members from the project partners, who are involved in the project on regular basis. It is in charge of carrying out the specific actions of the CYCLOPS Project (studies, dissemination, etc.). As a Specific Support Action, mainly targeted to studies, analyses, dissemination and research preparation, the setup of an effective Working Group is an important objective and a specific task is dedicated to such an action.

#### Expert Groups

The two Expert Groups (Technical Expert Group and Civil Protection Expert Group) are made of persons with high expertise in specific domains of interest for CYCLOPS: Information Technologies and Civil Protection. The members are selected both externallyand internally to the Consortium (maximum one member from each relevant partner)  and act as consultants for the project on specific issues to assure the quality of the actions. The Expert Groups also play the fundamental role of establishing a liaison with Grid and GMES communities. A specific task is dedicated to the setup of the Expert Groups.

#### Work Package Manager

Each work package is under the responsibility of a single partner who will designate a Work-package Manager. It will be the responsibility of this person to organize suitable contacts between the partners involved in the work-package and also be responsible for the management of the production of the deliverables.

#### Conflict resolution

The management board will have both the authority and the responsibility for conflict resolution. Normally it is expected that conflicts will be resolved by voting on a simple majority. The PMB will take remedial action based on advice from the technical board in the event of milestones being missed or deliverables not being available. The project management board will normally conduct its business by email. We expect it to need to meet every six months at the same time as the project meetings. Exceptional meetings can be called by the PM on request from one or more of the partners.

#### Dissemination, Exploitation and Intellectual property

Dissemination and Exploitation activities are very important activities of the present SSA, tightly coupled to the technical aspects of the project, whereas they are not “embedded” among the management duties. A specific, fully dedicated, Work Package (WP5) will carry out dissemination and exploitation for the entire project extent. The WP5 Manager, in collaboration with the PMB, will be in charge of Dissemination and Exploitation activities; of course, all partners will contribute to such work package. The detailed plan for these activities is discussed in detail in the B.3 section.

In addition to the normal dissemination and exploitation of the work through scientific journal and professional bodies, Civil Protection Community will be specifically targeted for dissemination of the CYCLOPS deliverables and their future exploitation of the results.

WP5 Manager, coordinating its activity with the PMB, will develop a coordinated plan for the full exploitation of the project results. They will actively audit and evaluate project outcomes and make recommendations on Intellectual Property protection and routes to Civil Protection Community. They will maintain target Communities awareness and intelligence to inform the scientific direction of the project and to identify on-going scientific and application opportunities.

Project Management Structure

## 6.2 Plan for using and disseminating knowledge

A Project WEB site, Management Database, e-Mail, Mailing lists, Templates for Meetings Agendas, Meeting Minutes, Reports and Costs statements are the basic tools that will be put in place for information bookkeeping and flow. Besides, a project website will be settled with security levels, in order to interface persons with the basic tools.

The project activities’ meetings are key tools for the running of the project. They will be held either in presence, by phone conference or by videoconference. A calendar with the dates of ordinary meetings will be agreed yearly at the kick-off meeting and at the last meeting of the first year. Specific actions will be undertaken to successfully disseminate project results. These include:

- Establishing close relationship with European Infrastructure projects such as EGEE and EGEE-2 and with Projects involved in the development of Grid infrastructures outside Europe (EELA, EUCHINAGRID, EUMEDGRID, etc.) A CYCLOPS contribution to the EGEE-II project conference and user forum will be assured

- Monitor and follow up European and worldwide standards as they emerge within international bodies like the Global Grid Forum (GGF).

Organization of and participation in conferences, workshops and knowledge dissemination events, so as to disseminate the project results to the potentially interested communities. In particular the Cyclops partners plan the:

- Organization of a project open conference (in Italy, Roma – DPC) to be organized during the first year, to meet Grid, Civil Protection and GMES experts broaden the opportunities for dialogue and discuss  the  EGEE platform for Civil Protection applications also towards other national and transnational organization.

- Organization of a mid-term project workshop to present the analysis of civil protection structure and processes  as well as to brainstorm on the research strategy definition activities on the basis of use-cases.

- Organization of a project final conference to present the results  to many different communities: scientific and technological, Civil Protection, GMES and Earth Observation.

- Co-ordination of dissemination activities by project partners in the academic and research communities of the participating countries.

The project will facilitate the spread and exchange of technical expertise between all participating countries. The Project will also facilitate the exchange of information between the participating countries and the rest of the world, via close interactions with worldwide Grid efforts and projects. This interaction between the associated participants of the project is envisaged to promote the integration of the research communities of the region to the ERA (European Research Area). In particular INFN will take the lead of the Organization of two Training Workshop specially directed to the Civil Protection community which will include theoretical lectures, debates and round tables discussion, case studies, practical exercise, to focus the proper knowledge and the skills to use the GRID computing infrastructures -place: Chania(Greece) and Padova or Bologna(Italy).

Regarding the contribution to standard activities, the project will pursue collaboration with Pan- European efforts namely EGEE and EGEE-2. The specifications will be closely linked so as to achieve the similar policy formats, service definitions, architecture, tools etc. Moreover, WSRF and other Globus/GGF standards will be closely observed and fed back into. The relationship with EGEE and EGEE-2 will be of particular value in this context where these Projects will act as a strong link with international Grid efforts, including the Global Grid Forum (GGF). Again, active participation in quick requirements capture and fast feedback to the EGEE and EGEE-2 middleware developers will indirectly contribute to international standards.

## 6.3 Raising public participation and awareness

Get the operational people aware of CYCLOPS and its future developments is essential, as they can relay information and disseminate such knowledge in their different working environment. Therefore, it is envisaged to generate a module for increasing awareness of the operational community, which could be released during the end users training sessions or included in the instructional material with the support of end user training authorities.

# 7. Workplan– for whole duration of the project

## 7.1 Introduction - general description and milestones

### The context

Many Civil Protection applications require a strict integration with research infrastructure providing resources (computing, data, services, knowledge, expertise, etc.) useful in the full cycle of emergency management (forecasting,  warning, management, assessment). Moreover these activities typically involve many different actors (Civil Protection systems, public bodies, research centers, etc.) that need to share resources in a coordinated and effective way. The recent development in the information and communication science and technology, provide the basis for enabling such applications. In particular, Grid technologies are designed just to allow the coordinated sharing of resources (computing, storage, communication, sensors) needed by such Virtual Organizations (VOs).

Consequently, the adoption of a Grid-based infrastructure seems a natural choice to build a cooperative platform for supporting Civil Protection activities. However Civil Protection applications have specific requirements such as:

- especially during emergency situations, they require to access research infrastructure to run models or search information, but they need real-time (RT) or near-real-time (NRT) responses, privileging time of response instead of accuracy.

- during emergency situations, they gain great benefit from the possibility to control sensors networks and acquisition systems to modify their acquisition strategy and processing chain;

- they require to share geo-spatial information that has specific characteristics. In particular, remote-sensing observation from new satellite sensors produces huge amount of data that are frequently updated;

- Civil Protection systems often need to interact with military resources so they have the strict data policy and security requirements  typical of dual systems (civil/military);

- they require knowledge-based systems that starting from data, can provide information suitable by the decision-makers;

These requirements have strong impact on research strategies (new data models, algorithms, methodologies need to be investigated) and consequently on the functional and non-functional requirements of the enabling research infrastructures (new protocols, services and architectures are to be designed and implemented).

Current Grid platforms were mainly designed for researches requiring intensive processing and data management, thus they offer high computing and storage capabilities. Only in recent times Grid research is facing new problems like sensor interaction and communication quality of service. Thus they presumably need an enhancement to support the typical Civil Protection applications that are Real-Time or Near-Real-Time applications requiring data-integration, high-performance computing and a distributed environment for simulations and modelling.

In the Grid technology domain, EGEE Project, which is targeted to the design and development of an enabling Grid platform for e-Science, is a natural choice as starting point for CYCLOPS activities, since it is facing many problems that also CYCLOPS must consider. Nevertheless EGEE platform, and the resulting middleware, is designed for typical research activities aiming to gain knowledge mainly through the processing of great amount of generated or acquired data. Hence, to support Civil Protection applications, research infrastructure should enable the new models, algorithms and services that they require.

This Specific Support Action will elaborate on this and provide commentary and guidance for further research along the EGEE guidelines, in so supporting 6FP, with particular reference to the Communication Development Scheme, GMES, and eventually, contributing to foster innovation in Society.

### Overall architecture

Fig.  1 General CYCLOPS architecture

Fig. 1 depicts the overall architecture that guides the CYCLOPS activities. It is based on preliminary investigations whose results suggest the need of the studies and analysis planned in the present support action. As a Specific Support Action CYCLOPS Project will not develop the infrastructure in itself, anyway a reference framework is essential to guide the studies and analyses that are an important part of the project. They will be summarized in the definition of proper research strategies. Future R&D projects, exploiting CYCLOPS results, can be directed towards the design and implementation of specific parts of an infrastructure based on this architecture.

The figure shows how the existing Grid Platform (EGEE) can provide the coordinated sharing of computing, storage and communication resources of existing and enhanced Processing Infrastructure and Network Infrastructure of Civil Protections and research centers involved in the emergency management procedures. Other specific resources that are part of the Environmental Monitoring Infrastructure (sensors and acquisition systems) need to be grid-enabled through services for Earth Science resources. Such services (sensor discovery, description, access for acquisition and control, etc.) make possible the virtualization of sensor resources in a Grid view.

On top of the Grid platform, providing basic services, specific Grid Services for Earth Science can be implemented to build the infrastructure for Civil Protection applications: the CYCLOPS Infrastructure. These are:

- advanced Grid services (e.g. Quality of Service management, orchestration services, Knowledge Grid services, etc.);

- Spatial Data Infrastructure services for geo-spatial data management.

These Grid Services for Earth Science make the CYCLOPS Infrastructure providing domain-specific services suitable to develop Grid-enabled application for Civil Protection applications.

The applications are built using generic Business Logic (e.g. expert systems) and Presentation/ Fruition (e.g. GIS, collaborative work environment) services according to a Service-Oriented Architecture (SOA) approach. Beside these services, an advanced Security Infrastructure provides the Security and Policy services required at each level, for handling the complex data policies typical of the Civil Protection domain. They allow to satisfy the strict requirements of integrity, confidentiality and data/services access control that Civil Protection applications impose to the enabling platform. Moreover, to complete their tasks, many applications should be able to interact with external infrastructure such as existing Grid platforms, security systems, e-Government infrastructures, and Spatial Data Infrastructures. Thus, an interoperability infrastructure completes the platform.

These high-level services and tools make the CYCLOPS platform, a complete Grid-based platform supporting Civil Protection applications.

Basing on this view many problems have to be investigated. For example:

- How is it possible to integrate sensor networks and acquisition systems in the EGEE platform?

- How is it possible to integrate Spatial Data Infrastructures (SDI) in a Grid platform?

- Which advanced services are needed to support Civil Protection applications (knowledge-based services, Quality-of-Service management, etc.)?

- Which Data Policy and Security support is needed for Civil Protection applications?

- Which generic Business Logic or Presentation and Fruition Services are useful to build Civil Protection applications?

To answer to these and other arising questions an extensive research is required. A preliminary study to define the research strategies in the EGEE enhancement is necessary to guide further activities.

### Workplan description

The CYCLOPS workplan is aimed to reach the Operational Goals of the project. It is made of two kinds of activities:

- Support activities, carrying out the work for reaching the Operational Goals;

- Management activities that aim to coordinate and facilitate the Support activities for the best result of the project;

They are summarized in the following lists:

- Management activities

  - Project Management

- Support activities

  - Coordination with EGEE activities

  - Civil Protection system analysis

  - Research and Innovation Strategies definition

  - Dissemination and Exploitation

Concerning the Management activities, a specific Project Management Work Package (WP1) exists. It is dedicated to the global coordination of the project, and to the project setup. Indeed creating a successful synergy between the Civil Protection and EGEE communities requires great care in the creation of the working group, the specific expert groups and their relationships. In particular two expert groups need to be set up to provide specific knowledge to the working group. The former is made of persons with expertise in the working of Civil Protection systems. The latter is a panel of experts in Information and Communication Technologies (ICT) applied to Civil Protection, the Earth Sciences, environmental monitoring and GMES applications. The working group, possibly divided in teams, carries out the day-to-day activities also using collaborative work tools that allows for the strict collaboration between members in different countries. This activity assures that after an initial setup time the project can go through the support activities without any major problem.

The WP1 is divided in five tasks. A first task T1.1 is devoted to the day-to-day activities, while the other fours are dedicated to preliminary activities for  the start of the project. In particular T1.5 aims to create a collaborative work environment and along with T1.1 make possible an advanced management for assuring the quality of the management itself. A specific task (T1.2) is dedicated to the setup of the working group and it is essential to assure a correct mobilisation of the resources that are essentially human resources since CYCLOPS results are mainly studies and reports. The other two tasks aim to create the expert groups which are made of members with high expertise in different domains (CP agencies work and Grid/IC technologies). The availability of these expert groups aim to assure the quality of the support action results.

CYCLOPS is a project that complements the EGEE I3 project. For a better synergy between them a specific WP is dedicated to their coordination. The Coordination with EGEE activities WP aims to keep in touch the EGEE and Civil Protection communities. It transfers knowledge from one project to the other. Initially EGEE results need to be disseminated to the Civil Protection community in order to have a precise view of what EGEE Grid platform can provide. In particular Civil Protection experts need to know what a Grid-platform can provide to them in terms of resources and support, to identify new possible scenarios and applications. ICT experts need to know the EGEE middleware development stage to evaluate the need of future enhancement specific for the Civil Protection domain.

During the project a continuous interaction is useful both for guiding CYCLOPS activities in the EGEE view and to report preliminary results of CYCLOPS to the EGEE designers. At the end of the project the final results of CYCLOPS can be reported to EGEE community.

The WP2 is divided in two tasks. T2.1 is dedicated to the dissemination of EGEE architecture and middleware to CP agencies to inform about the possibility of Grid platforms. T2.2 is a fundamental task dedicated to the coordination between EGEE/EGEE-2 and CYCLOPS. It performs one of the core actions that is the exchange of information between the two projects, providing CYCLOPS members with the information about EGEE middleware evolution, and providing EGEE technical group with the knowledge about the Civil Protection requirements resulting from CYCLOPS activities. T2.1 and T2.2 perform a specific aspect of the Grid and Civil Protection communities cross-dissemination establishing a link between Civil Protection agencies and EGEE members. This is an essential issue to increase the potential impact of CYCLOPS project.

The second support activity is the Civil Protection systems analysis. Civil Protection systems are extremely heterogeneous both in operational models and resources. To better support them through a European wide infrastructure, an extensive study about their organization and resources is needed. This is carried out through the expertise of the Expert Groups. The Civil Protection expert panel provides the Business Process analyses, the Existing Analyses, and a set of significant use-cases. The Business Process analysis is an important element to analyze the needs of the different Civil Protections and also to compare them in order to identify common and peculiar processes. The Existing analysis provides a view of the human and technological resources available and used by the Civil Protection systems. This is useful both to identify the required enhancement to support an EGEE-based Grid platform and to analyze the problem related to the homogenization of resources.

The identification of significant use-cases is essential for the correct definition of system requirements. Use-cases should be significant in terms of usage scenario, involvement of organizations (research centers, data providers, etc.), interaction of human and technological resources. They should cover a wide set of possible applications of Grid technologies to Civil Protection applications. Moreover, some of them should be existing scenario that can be enhanced by the use of advanced technologies, while others should be new scenarios made possible by the existence of a Grid infrastructure. Taking into account all these elements, use-cases can drive the study of the research strategies for the design and development of the infrastructure.

Indeed basing on these preliminary analyses, the ICT experts can provide the system requirements for the research infrastructure supporting Civil Protection applications. The Expert Groups will pay particular attention to the problem of data security and policies that has both organizational and technical concerns.

The WP is divided in four tasks dedicated to analysis. T3.1 will provide the Business Process Analysis, T3.2 the Exiting Analysis, T3.3 the Use Cases and T3.4 the System Requirement Analysis. These analyses are also an input for WP4 and they are important to define Civil Protection community requirement for Grid platforms has high relevance to the Objectives of the Programme.

The WP Research and Innovation Strategies definition carries out the core activities of CYCLOPS project. Basing on the Civil Protection system requirements, and the EGEE existing and planned features, it defines the research strategies to enhance EGEE for enabling Civil Protection applications. Initially the EGEE middleware is deployed and configured on partner sites to build a Grid infrastructure. This is useful to test and evaluate the current release of EGEE in a Civil Protection setting. Using this infrastructure a study for the Civil Protection framework integration with the EGEE middleware is performed. This is useful for evaluating which part of the middleware need to be enhanced. Subsequently it is possible to analyze in detail the required enhancement of the platform. Considering the current and planned features of EGEE, the existing research on Grid of new generation, the existing infrastructures for Earth Science systems, like Spatial Data Infrastructures (SDIs), the strategies for future researches are defined.

The resulting strategies are summarized in form of Request for Enhancement (RFE) to EGEE community, reporting the main features that need to be improved and the fields where greatest research effort has to be planned. Moreover innovation strategies are proposed to the Civil Protection communities to guide future acquisition in order to support advanced applications through Grid-based technologies. In short, this WP provide the guidelines for the future convergence of Civil Protection and EGEE communities through research and development projects aiming to the design and implementation of a research infrastructure for Civil Protection, and potentially GMES, applications.

The WP is divided in six tasks. The first four are dedicated to a detailed analysis of using EGEE/EGEE-2 platform in a Civil Protection context. T4.1 is dedicated to the installation of the EGEE platform in the real context of the Civil Protection agencies members of the project. T4.2 is a preliminary activity to highlight weaknesses of current EGEE platform implementation in supporting Civil Protection applications. T4.3 analyzes the EGEE extensions needed to fully support Civil Protection applications. Finally T4.3 is dedicated to analyze the porting of applications in the EGEE platform. All this tasks result in a Request for Enhancement for EGEE document that is an important result for the Relevance to the Objectives of the Programme.

T4.5 and T5.6 are dedicated to the definition of R&D strategies and innovation strategies for Civil Protection agencies, and are important output to increase the potential impact of the project since they prepare two important aspect of future exploitation: the startup of future R&D projects in different contexts and to guide innovation actions for Civil Protection agencies.

The Dissemination and Exploitation WP defines the activities aimed to spread the results of CYCLOPS project towards different communities. It is detailed in 6.2 section.

### Risk analysis and contingency plans

#### Threats identification

As any technological project, CYCLOPS must face many possible threats. Some of them have a negligible effect on the project due to their very low probability or to their minimum impact. Others are to be considered, because their probability is high or their effect is heavy.

In particular we identify some possible threats that need to be investigated:

- Human: CYCLOPS, as a study and analysis project, is based on the high expertise of persons active in the expert groups. Consequently the experts are a valuable resource for the project. The absence of some of them, due to illness, other activities, etc. can have a negative impact on the project;

- Procedural: CYCLOPS involves many different organisations. Problems in the procedures of some of them can affect the project (e.g. failures of accountability, internal systems and controls, organisation, etc.). One type of procedural threat, related to changes in the organization, operational models and procedures of Civil Protections during the project extent is particularly important since they are a vital input for the project.

- Project: in the course of the project problems can arise from cost over-runs, jobs taking too long, insufficient product or service quality, etc.

- Technical: CYCLOPS is a technology project. Advances in technology or modifications in the technological context can make it ineffective and reduce the values of the results;

#### Risk estimation

Concerning the Human threats, the absence of members of the Expert Groups due to other activities must be considered having medium to high probability. The risk is reduced due to the fact that Expert Groups are not full-time involved in the CYCLOPS project and consequently they can coordinate their effort on CYCLOPS and on other projects and activities. Anyway the potential high impact of their missing on the project needs to plan proper risk management actions.

The procedural threats related to the internal functioning of partners are considered with low probability due to the reliability of the organisations involved in the CYCLOPS project. The special threat of possible changes in the organisations, operational models and procedures of Civil Protections requires a risk management plan due to its potential high impact on the project.

Project threats are considered with medium probability as for any project of this kind. Since they directly affect the project results, risk management actions have to be defined.

Technical threats are considered highly probable. CYCLOPS is a project covering some of the most advanced topics in science and technology. Specially the continuous upgrade of environmental monitoring systems and the progresses in the information and communication technologies can modify the context of the project during its time extent. In particular Grid technologies, that are the core technologies in the project, are undergoing a fast evolution that the project must consider.

#### Risk management

Risk management is worked out through two integrated approaches:

- Risk counteract, to minimize the risk probability whenever possible;

- Contingency plan, to minimize the effects of risk occurrence;

Concerning the Human threats, the risk management is based on project management activities. In particular the working group will be redundant with the participation of more than one member of each organization, allowing to easily compensate for temporary absences. For the Expert Groups that are less continuously involved in the activities but more critical for the project, a strategy to minimize the absence is based on an advance scheduling of meeting and required contributions. Whenever the absence is prolonged, a temporary or permanent substitution of the expert person is required.

The procedural threats due to possible changes in the Civil Protection organizations are faced through the continuous monitoring provided by the Civil Protection Expert Group. Moreover the project results are based on the use-cases and scenario provided by that Expert Group made of members who are aware of future evolutions of their specific systems and presumably of the European and international context.

Project threats are faced by the continuous activity worked out in the Project Management Work Package. The threats identification and management are specific activity of that WP.

Technical threats management is based on their immediate occurrence detection. The presence of Expert Groups about both Civil Protection and ICT sectors provides high confidence about a continuous monitoring of Civil Protection applications and ICT evolution allowing to direct the project efforts towards the future scenarios. In particular, concerning Grid technologies that are at the core of project initiatives, a partner (INFN) is one of the main actors in the European and international scenario, and one specific WP is dedicated to the coordination of CYCLOPS with EGEE, a key project in the European Grid evolution scenario.

## 7.2 Work planning and timetable

Fig. 2 shows the planned timing of the Project expressed in form of a Gantt chart. reporting the time extent of the Work Packages.

Fig.  2 GANTT chart of the CYCLOPS Project

As the Gantt shows, the Project Management WP covers the entire duration of the project that is 24 months. The Project Setup extends for the first three months. After that, the Civil Protection Systems analysis WP starts, covering eight months. When the Civil Protection systems analysis is concluded, the Research and Innovation Strategies definition WP can begin. It lasts for ten months. The Coordination with EGEE Project WP covers the 18 months of the previous two core project activities. Finally, the Dissemination and Exploitation WP covers the entire project duration. In particular, the last three months are dedicated to the dissemination of the results.

## 7.3 Graphical presentation of work packages

In fig.3 the PERT diagram showing the interdependencies between the components (Work Packages, Milestones, Tasks) is depicted.

|  | Tasks |  |  | Milestones |
| --- | --- | --- | --- | --- |
| T1.1 | Project Management |  |  |  |
| T1.2 | Definition of the Working Group |  | START | Start of Project |
| T1.3 | Definition of Civil Protection Expert Group |  | M1.1 | Working Groups set up |
| T1.4 | Definition of Technical Expert Group |  | M1.2 | Project ready to start support activities |
| T1.5 | Setup of the collaborative environment |  | M2.1 | Dissemination and training plan ready and published |
| T2.1 | Dissemination and tutorial of the EGEE middleware to the GMES community |  | M2.2 | EGEE presented to the GMES community |
| T2.2 | Civil Protection Framework and EGEE middleware evolution coordination |  | M3.1 | Civil Protection System description available |
| T3.1 | Business Process analysis |  | M3.2 | System Requirements available |
| T3.2 | Existing Analysis |  | M4.1 | EGEE infrastructure deployed |
| T3.3 | Use-cases analysis |  | M4.2 | EGEE Integration analyzed |
| T3.4 | System Requirements Analysis |  | M4.3 | EGEE enhancement analyzed |
| T4.1 | Implementation of a Grid infrastructure for Civil Protection |  | M4.4 | Application porting analyzed |
| T4.2 | Study of Civil Protection framework integration with EGEE Grid middleware |  | M4.5 | Research and innovation strategies investigated |
| T4.3 | Study for a Civil Protection infrastructure to enhance EGEE middleware |  | M5.1 | Dissemination started |
| T4.4 | Analysis of Civil Protection applications porting |  | M5.2 | Project results disseminated |
| T4.5 | Research Strategies definition |  | END | End of Project |
| T4.6 | Innovation Strategies definition |  |  |  |
| T5.1 | Project start dissemination |  |  |  |
| T5.2 | Dissemination planning |  |  |  |
| T5.3 | Project activities dissemination |  |  |  |
| T5.4 | Project results dissemination |  |  |  |

Fig.  3 - PERT chart of CYCLOPS Project

The PERT highlights how in the initial phase some tasks can be performed in parallel, while the final phases are mainly serial. This is an important input for the Project Management since it points out that a major attention is required to monitor WP4 and WP5 to avoid delays blocking following tasks and activities.

## 7.4 Work package list

| Work-package No | Workpackage title | Lead contractor No | Person-months | Start month | End month | Deliv-erable No |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Management | 1 (DPC) | 4,50 | 0 | 23 | D1 D3 |
| 2 | Coordination with EGEE activities | 2 (INFN) | 21,50 | 3 | 20 | D5 D7 D10 D13 D17 |
| 3 | Civil Protection systems analysis | 4 (DDSC) | 29,00 | 3 | 10 | D6 D8 D9 D11 |
| 4 | Research and Innovation Strategies definition | 3 (IMAA) | 42,25 | 11 | 20 | D14 D15 D16 |
| 5 | Dissemination and Exploitation | 7 (SNBPC) | 21,75 | 0 | 23 | D2 D4 D12 D18 D19D20 D21 |
|  | TOTAL |  | 119,00 |  |  |  |

## 7.5 Deliverables list

| Del. No | Deliverable name | WP No | Lead Participant | Estimated person-months | Nature | Dissemination level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1 | Project Presentation | 1 | 1 (DPC) | 0.25 | R | PU | PM1 |
| D2 | Project open conference | 5 | 7 (SNBPC) | 0.5 | O | PU | PM1 |
| D3 | Perspective on cooperation with existing projects and initiatives | 1 | 1 (DPC) | 0.25 | R | RE1 | PM2 |
| D4 | Dissemination Plan | 5 | 7 (SNBPC) | 1 | R | RE1 | PM3 |
| D5 | Training events plan | 2 | 2 (INFN) | 0.5 | R | RE1 | PM3 |
| D6 | Business Process analysis document | 3 | 4 (DDSC) | 1 | R | PU | PM5 |
| D7 | “EGEE cookbook: a guide for Civil Protection Grid users” document | 2 | 2 (INFN) | 1 | R | PU | PM6 |
| D8 | Existing Analysis document | 3 | 4 (DDSC) | 0.5 | R | RE1 | PM6 |
| D9 | Use-cases document | 3 | 4 (DDSC) | 0.5 | R | RE1 | PM7 |
| D10 | First Training Workshop | 2 | 2 (INFN) | 0.5 | O | PU | PM7 |
| D11 | System Requirements document | 3 | 4 (DDSC) | 1 | R | PU | PM10 |
| D12 | Mid-term project workshop | 5 | 7 (SNBPC) | 0.5 | O | PU | PM12 |
| D13 | Second Training Workshop | 2 | 2 (INFN) | 0.5 | O | PU | PM13 |
| D14 | “EGEE Request for Enhancement” document | 4 | 3 (IMAA) | 1 | R | PU | PM16 |
| D15 | “Toward a Grid - Guidelines for Innovation Strategies for Civil Protection Systems” report | 4 | 3 (IMAA) | 1 | R | RE1 | PM20 |
| D16 | “Research Strategies for the development of a Civil Protection E-Infrastructure” report | 4 | 3 (IMAA) | 1 | R | PU | PM20 |
| D17 | Dissemination and coordination activity final report | 2 | 2 (INFN) | 0.5 | R | RE1 | PM23 |
| D18 | Project results presentation | 5 | 7 (SNBPC) | 0.5 | R | PU | PM23 |
| D19 | Final Plan for using and disseminating knowledge | 5 | 7 (SNBPC) | 1 | R | RE1 | PM23 |
| D20 | Report on raising public participation and awareness | 5 | 7 (SNBPC) | 0.5 | R | RE1 | PM23 |
| D21 | Project final conference | 5 | 7 (SNBPC) | 0.5 | O | PU | PM23 |

1) The access is public after explicit request. The identification is the only restriction applied since the Consortium does not deny the access to any project deliverable.

## 7.6 Work package descriptions

WP 1 Management

| Workpackage number : | 1 |  | Start date or starting event: |  |  |  | PM0 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Type |  | Management of the Consortium activities |  |  |  |  |  |  |
| Participant id: |  | 1 DPC | 2 INFN | 3 IMAA | 4 DDSC | 5 CP-CH | 6 TEI-CR | 7 SNBPC |
| Person-months per participant |  | 1,50 | 0,50 | 0,50 | 0,50 | 0,25 | 0,75 | 0,50 |

Objectives - To coordinate the support activities; - To provide financial and administrative management; - To provide regular progress reports to the Commission; - To resolve conflicts; - To collect reports about related initiatives and consequently to stimulate their consideration in the project evolution; - To deal with IPR; - To maintain the project web site up to date; - To setup expert and working groups; - To setup the collaborative environment; - To monitor project progresses and results

Description of work This Work Package deals with the Management of the project. The main tasks of the work package are: the overall coordination of the project activities, the management of knowledge and intellectual property, the management of collaboration with similar international initiatives, the management of any action arising in the project. CYCLOPS management activity will cover important project aspects, such as: quality plan, management reports and cost statements. An effective management and decision making organization is utilized to achieve such tasks; it is fully described in the B5 paragraphs. Such specific structure is designed to deal with the problem of a number of geographically distributed partners with light project management resources. To meet this challenge the management of individual work packages has been devolved to experienced Workpackage Managers, appointed by the lead partner in each of the work packages. An important role of CYCLOPS management will be to ensure the effective and enabling availability of the work developed by EGEE and related initiatives at the National level. Eventually, a key task of CYCLOPS management is the set up of working and expert groups (i.e. civil protection and technical expert groups). As a support action complementing the EGEE project toward the creation of a Grid-based infrastructure for Civil Protection applications, the CYCLOPS project involves many different actors with diverse expertise and role. To achieve an effective cooperation between them, we need to properly setup an organization made of human and technical resources that is able to facilitate the cooperation throughout the duration of the project. In particular this specific management activity aims to the creation of the workgroups and expert groups, and to provide the technical system that assists the collaborative work. The WP 1 is made of five tasks: T1.1 Project Management This task cover the day-by-day activities required for the project management including: - the co-ordination of the technical activities through the actions of the Technical Management Board; - the overall legal, contractual, ethical, financial and administrative management, including deliverables collection and timely issue to the Commission and reporting; - co-ordination of knowledge management and other innovation-related activities; - maintenance of any consortium agreement; - resolution of conflicts; - monitoring of progress and success of the project through the collection of review and assessment internal reports from all WPs (including WP1), their evaluation and planning of response actions to possible problems; T1.2 Definition of the Working Group (WG) The Working Group is in charge of carrying out the support activities. The WG works in team using the collaborative environment set up as result of T1.5. It can be further divided in work teams for accomplish well-defined sub-tasks. The WG consults the expert groups on specific issues. This task aims to set up an effective Working Group assuring that the human resources effort is adequate to the project both in quantity (person-months allocated to CYCLOPS) and quality (expertise of single members and of the WG as a whole). At most one person for each partner is member of the WG, while other members will be selected externally to the Consortium. The WG is defined taking into account the proposals of each partner. It is responsibility of the PMB to manage the evolution of the WG during the project extension. T1.3 Definition of Civil Protection Expert Group (CPEG) The Expert Groups are made of persons with high expertise in a specific domain who are not involved full-time in the Project. The experts act as consultant for the project on specific issues to assure the quality of the actions. In particular the Civil Protection experts provide knowledge about the typical business processes and internal working of the different Civil Protections involved in the project. This task aims to define the CPEG. Typically one member for each Civil Protection involved in the project is part of the CPEG. T1.4 Definition of Technical Expert Group (TEG) The TEG is composed of members with expertise in information and communication technologies and their applications in the environmental, Earth Observation and Civil Protection sectors. The TEG provides knowledge about the technologies and resource available for Civil Protection and GMES applications. This task aims to define the TEG. T1.5 Setup of the collaborative environment Since the quality of the project is highly dependant on the possibility to conduct the activities at the European level, the project requires strict cooperation between persons located in different sites, with particular reference to the WG members who are in charge of the day-to-day activities. Although meetings between WG and EG (Experts Group) members will be scheduled during the project extension, the availability of collaborative tools makes easier the cooperation. This task aims to set up a set of tools for collaborative work. In particular the following services will be made available: - project web site; - mailing lists and discussion forums; - project document repository; - collaborative editing environment; - audio/video conferencing tools; Moreover the WP includes activities aimed to evaluate and assess progresses and results as regards the Operational Goals 1.1, 1.2 and 1.3. The results of these activities will be documented in quarterly internal reports for the Project Management Board.

Deliverables D1 (PM1) Project Presentation This deliverable consists of a brief project presentation in English, written in a style which is accessible to the non-specialist. It is designed to be used both for WWW publishing and other media distribution D3 (PM2) “Perspectives on cooperation with existing projects and initiatives” report This deliverable outlines how CYCLOPS relates (or plan to relate) to the main existing projects and initiatives in the contexts of Grid technologies, Civil Protection and GMES. It defines the actions required during the project extension to make these relationships effective and fruitful.

Milestones and expected result M1.1 (PM0) Start of Project This is the starting point of the project M1.2 (PM1) Working Groups set up Persons continuously involved in the project are identified. A team is in charge of setting up the collaborative environment. M1.3 (PM3) Project ready to start support activities The tools useful for collaborative work (mailing list manager, web site, document repository) are active. The experts of Civil Protection systems and the expert of ICT for Civil Protection and GMES applications are identified.

Justification of financing requested A total amount of 3 PM will be dedicated to specific project management activities. Travel costs. During the first three months 1 PM will be deployed for setting up expert groups, working group and the collaborative work environment. Collaborative work equipment and software.

WP 2 Coordination with EGEE activities

| Workpackage number : | 2 |  | Start date or starting event: |  |  |  | PM3 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Type |  | Activities specific for the Support Action |  |  |  |  |  |  |
| Participant id: |  | 1 DPC | 2 INFN | 3 IMAA | 4 DDSC | 5 CP-CH | 6 TEI-CR | 7 SNBPC |
| Person-months per participant |  | 1,25 | 11,75 | 3,25 | 1,75 | 0,00 | 1,75 | 1,75 |

Objectives - to disseminate the Grid concepts and the EGEE middleware into the Civil Protection community - to establish a two way communication channel between CYCLOPS and EGEE projects, in order to keep updated the Civil Protection community about EGEE middleware news and evolution, and to allow GMES community to provide feedback to EGEE community

Description of work T2.1 Dissemination and tutorial of the EGEE middleware to the Civil Protection community This activity aims to organise, in cooperation whenever possible with the EGEE project corresponding activity, dissemination and training events where the current architecture of the EGEE middleware and its planned evolution will be presented to the Civil Protection community in order to establish the starting point for future design of a Civil Protection -and potentially GMES- Grid infrastructure. T2.2 Civil Protection Framework and EGEE middleware evolution coordination The GMES framework enabling on a Grid infrastructure requires the coordination with the EGEE activities in order to reach a valuable synergy between the projects. CYCLOPS members developing the GMES Grid framework must be kept continuously updated about new EGEE middleware functionalities implemented by the EGEE project, at the same time need to give feedback to EGEE developers highlighting the weakness encountered in the Grid middleware and suggesting possible improvements for satisfying their requirements. Moreover the WP includes activities aimed to evaluate and assess progresses and results as regards the Operational Goals 5.1 and 5.2. The results of these activities will be documented in quarterly internal reports for the Project Management Board.

Deliverables D5 (PM3): Training events plan This deliverable describes the scheduling (date, duration), organization issues (sites, equipments to be used), content and attendants’ profiles for the planned training events. D7 (PM6): EGEE cookbook: a guide for Civil Protection Grid users This deliverable is a guide to the use of EGEE platform for Civil Protection users. It introduces the Grid technologies, their possible applications for Civil Protection, and describes EGEE platform. It will be prepared taking into account the target audience using a style accessible to non-specialists for the sections which are not addressed to technicians. D10 (PM7) First training workshop This deliverable consists of a workshop directed to the Civil Protection community which will include theoretical lectures, debates and round tables discussion, case studies, practical exercise, to focus the proper knowledge and the skills to use the GRID computing infrastructures. The material of the workshop will be made available through the project website. D13 (PM13) Second training workshop This deliverable consists of a workshop directed to the Civil Protection community. It is analogous in structure to the previous workshop but its content will be different according to the Training Events Plan. The material of the workshop will be made available through the project website. D17 (PM23): dissemination and coordination activity final report This deliverable is a document reporting the results of the dissemination of EGEE towards the Civil protection community, and about the coordination between the EGEE and CYCLOPS activities.

Milestones and expected result M2.1 (PM3): dissemination and training plan ready and published The required activities to disseminate EGEE in the Civil Protection community are established and clear. M2.2 (PM6): EGEE explained to the Civil Protection community At this stage Civil Protection community is aware of the potentiality of EGEE platform. It is ready for its evaluation in the context of Civil Protection applications and for providing useful contribution to its evolution.

Justification of financing requested 0.5 FTE will be deployed for this activity by INFN for planning the dissemination and training events and producing the corresponding material and documentation; a total effort of 0.5 FTE will be deployed by other partners, to contribute to the activities; travel costs for participating in dissemination and training events; events organisation.

WP 3 Civil Protection systems analysis

| Workpackage number : | 3 |  | Start date or starting event: |  |  |  | PM3 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Type |  | Activities specific for the Support Action |  |  |  |  |  |  |
| Participant id: |  | 1 DPC | 2 INFN | 3 IMAA | 4 DDSC | 5 CP-CH | 6 TEI-CR | 7 SNBPC |
| Person-months per participant |  | 9,75 | 1,50 | 3,25 | 5,00 | 1,25 | 3,25 | 5,00 |

Objectives - Business process analysis of the Civil Protection systems involved in the project - Existing Analysis for each Civil Protection systems involved in the project - Use-cases definition - System requirements analysis

Description of work This Work Package aims to the description of the requirements of a grid-based infrastructure for Civil Protection applications. This study requires some preliminary steps to fully understand the working of the diverse Civil Protection systems, their technological resources and infrastructures, the main use-cases and scenarios. This WP is made of the following tasks: T3.1 Business Process analysis EU countries adopt very different Civil Protection systems. They have different responsibilities, and they are based on diverse models. This task carries out a Business Process analysis of the Civil Protections systems active in the partner countries. This analysis should highlight the internal processes and the interactions with external entities such as public bodies, research centers, data and knowledge providers. The study should pay particular attention to the cross-boundary activities, since they could gain the greatest advantage by a shared infrastructure. The objective of the study is the identification of common and particular characteristics that could affect functional and non-functional requirements. T3.2 Existing Analysis EU Civil Protection systems use different scientific and technological infrastructures and services. In a European-wide view, this infrastructures need to be integrated and enhanced. This task aims to collect information about the resources (information systems, communication services, computing resources, etc) commonly used by the different Civil Protection systems involved in the project. The work will be carried out also preparing a form to be filled by technical reference persons of the Civil Protection agencies involved in the project. The results allow to evaluate the available resources in quantity and quality as regards grid technology adoption. T3.3 Use-cases analysis This task aims to identify and describe a set of significant use-cases that could be ported, improved or even made possible by using Grid technologies. This common or visionary use-cases should be representative of typical scenarios of Civil Protection. This task is performed through the strict cooperation of the Expert Groups whose overall expertise (in CP agencies work and Grid/Information&Communication technologies) assures the identification of use-cases relevant for the objective of the project. Since the objective of this study is to help in the definition of the system requirements, the selected set of use cases should consider, for example, one or more of the following issues: high computing and storage requirements (that could be provided by grid technologies), cross-border applications (for interoperability problems), spatial data management, real-time and near-real-time requirements, data policy and security, etc. T3.4 System Requirements Analysis Basing on the T3.1, T3.2 and T3.3 results, this task provides the functional and non-functional requirements of a Grid-based infrastructure for enabling Civil Protection applications. This study is the basis for researches on grid infrastructure addressed by future projects. Examples of functional requirements to be considered are: the support to control sensors networks and acquisition systems, the sharing of geo-spatial information; the support of strict data policy and security; the implementation of knowledge-based services. Examples of non-functional requirements to be considered are: time of response (especially for RT and NRT services); service level agreement (example for time-of-response/accuracy negotiation); quality of service (resource prioritization and reservation). Moreover the WP includes activities aimed to evaluate and assess progresses and results as regards the Operational Goal 4.1. The results of these activities will be documented in quarterly internal reports for the Project Management Board.

Deliverables D6 (PM5) Business Process analysis document This deliverable describes the Civil Protection agencies involved in the project. In particular it explains their responsabilities in the national context, the internal working model, the relationships with other national and international bodies, the organizational structure and so on. D8 (PM6) Existing Analysis document This document describes the technical resources (both equipment such as computing, storage, communication, etc. and technical staff) available at each Civil Protection agency involved in the project, in the perspective of Grid technology adoption. D9 (PM7) Use-cases document This document details a set of significant use-cases that could be ported, improved or even made possible by using Grid technologies. It is based on the Business Process analysis document and it is a fundamental input for the definition of the User Requirements. D11 (PM10) System Requirements document This document describes the functional (what the system should do, i.e. data sharing, distributed processing, etc.) and non-functional (how the system should provide services, i.e. response time, throughput, etc.) requirements of a Grid-based infrastructure for enabling Civil Protection applications.

Milestones and expected result M3.1 (PM7) Civil Protection System description available A complete description of different Civil Protection Systems and typical use-cases are available. M3.2 (PM10) System Requirements available The system requirements for a Grid-based infrastructure supporting Civil Protection applications are available for the definition of research strategies.

Justification of financing requested An effort of 3.5 FTE will be deployed for this activity mainly by Civil Protection agencies. Scientific partners contribute to system requirement analysis. Travel costs.

WP 4 Research and Innovation strategies definition

| Workpackage number : | 4 |  | Start date or starting event: |  |  |  | PM11 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Type |  | Activities specific for the Support Action |  |  |  |  |  |  |
| Participant id: |  | 1 DPC | 2 INFN | 3 IMAA | 4 DDSC | 5 CP-CH | 6 TEI-CR | 7 SNBPC |
| Person-months per participant |  | 6,25 | 5,50 | 11,00 | 6,50 | 0,00 | 6,50 | 6,50 |

Objectives To define the research and innovation guidelines toward the definition of a e-Infrastructure for Civil Protection applications.

Description of work The previous WPs provide the requirements for a Grid infrastructure supporting Civil Protection applications and the EGEE platform current and foreseen capabilities. Starting from this point it is possible to define the research strategies to plan an enhancement of EGEE in order to support Civil Protection applications. T4.1 Making of a Grid infrastructure for Civil Protection The EGEE middleware is installed and configured at the Civil Protections sites for test purposes. A minimal set of Grid elements needs to be deployed to form a dedicated Grid test-bed: 1 UI (User Interface), 1 RB/BDII (Resource Broker/Berkeley Database Information Index), 1 VO (Virtual Organisation) server, 1 RLS (Replica Location Server), 2 CEs (Computing Elements), 2 SEs (Storage Elements), 2 WNs (Worker Nodes). After setup, the test-bed must be maintained in operation, and continuously kept updated with the most recent EGEE releases, which might introduce new middleware functionalities. T4.2 Study of Civil Protection framework integration with EGEE Grid middleware Basing on the System Requirements analysis, this activity carries out a study about the possible integration of the Civil Protection framework with the EGEE middleware. This is a preliminary activity to highlight weaknesses of current EGEE platform implementation in supporting Civil Protection applications. It is dedicated to define which issues should be addressed by future researches aimed to the enhancement of EGEE architecture and implementation. T4.3 Study for a Civil Protection infrastructure to enhance EGEE middleware Basing on the results of T3.1, this activity analyze the EGEE extensions needed to fully support Civil Protection applications. In particular some topics need to be addressed: - Real-time and Near-Real-Time support; - Spatial Data Infrastructures and Grid integration; - Security and Data Policies enabling; - Sensor networks and acquisition systems control; - Knowledge-based Grid services; - Interoperability with other existing or planned infrastructures (SDIs, security, eGov, etc.); Other topics could (and probably will) arise from the analysis performed in the previous WPs. The study provides information about generic Grid technologies and more specific hints about the EGEE middleware components evolution. T4.4 Analysis of Civil Protection applications porting on the top of the new infrastructure This activity performs the analysis of the possible implementation of existing Civil Protection applications, or new applications derived by the defined use-cases, on the new infrastructure. This study highlights possible problems deriving from the integration of legacy resources (applications, data, etc.). T4.5 Research Strategies definition This activities aims to define the research strategies that will allow the design and implementation of the Grid infrastructure for Civil Protection. The results of this activities could be useful both for: - EGEE project, to guide the future middleware development in order to support Civil Protection and possibly other GMES sectors applications; - Specific projects aiming to the design and development of the e-Infrastructure for Civil protection applications; This strategic task takes the results of WP3 and T4.1-T4.4 to define which are the issues requiring R&D efforts toward the implementation of a Grid infrastructure for Civil Protection applications. After the definition of a general framework, for each specific domain where weaknesses are emerged, possible R&D activities are proposed estimating the effort, possible problems, and the context in which the activities could be started (existing projects and activities in the sector). T4.6 Innovation Strategies definition The possible future existence of a Grid for Civil Protection applications will affect Civil Protection infrastructures design and development. This activity aims to provide guidelines for the innovation strategies of Civil Protection systems in order to prepare the adoption of Grid-based platform (namely EGEE and its evolution). These guidelines provide the general framework for the adoption of an EGEE/EGEE-2 based grid infrastructure and specific requirements for the hardware, software and human resources to be allocated. This study will allow to Civil Protection agencies to take their planned innovation actions taking into account a future evolution toward Grid-based platform, increasing the re-use of hw/sw resources. Moreover the WP includes activities aimed to evaluate and assess progresses and results as regards the Operational Goals 4.2 and 6.2. The results of these activities will be documented in quarterly internal reports for the Project Management Board.

Deliverables D14 (PM16) “EGEE Request for Enhancement” document This document details which enhancements would be required to EGEE platform to fully support Civil Protection applications. It is designed as a fundamental input for EGEE (and future EGEE-II) project evolution. D15 (PM20) “Toward a Grid - Guidelines for Innovation Strategies for Civil Protection Systems” document This deliverable describes how the planned adoption of Grid technologies can affect the innovation strategies of Civil Protection agencies. It is designed as an instrument for guiding future equipment acquisition, and technical staff enhancement in the view of Grid technology adoption. D16 (PM20) “Research Strategies for the development of a Civil Protection E-Infrastructure” document” This document describes the research strategies to be followed for the design and implementation of a complete Civil Protection E-Infrastructure. It reports the results of the analysis and studies carried out by CYCLOPS project highlighting the open issues where more R&D activities are required to implement services and tools for Civil Protection applications on the top of a Grid-infrastructure.

Milestones and expected result M4.1 (PM13) EGEE infrastructure deployed The EGEE infrastructure is deployed for test and evaluation purposes M4.2 (PM15) EGEE Integration analyzed The possibility to adapt EGEE platform for supporting Civil Protection applications is evaluated. M4.3 (PM 16) EGEE enhancement analyzed Possible weaknesses of EGEE for supporting Civil Protection applications are investigated. M4.4 (PM18) Application porting analyzing Problems related to the porting of old applications is analyzed M4.5 (PM20) Research and innovation strategies investigated Research and Innovation strategies for EGEE and Civil protection systems enhancement are made clear.

Justification of financing requested An effort of 4 FTE is estimated; travel costs

WP 5 Dissemination and Exploitation

| Workpackage number : | 5 |  | Start date or starting event: |  |  |  | PM0 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Type |  | Activities specific for the Support Action |  |  |  |  |  |  |
| Participant id: |  | 1 DPC | 2 INFN | 3 IMAA | 4 DDSC | 5 CP-CH | 6 TEI-CR | 7 SNBPC |
| Person-months per participant |  | 4,25 | 2,25 | 2,25 | 4,25 | 2,25 | 2,25 | 4,25 |

Objectives To make the project existence and main results widely available to communities concerned with GRID and Civil Protection world in Europe. Objectives are to have a large community informed about the CYCLOPS concept and aware of the potential benefits, and to build the future development on an extended basis of users. The promotion/dissemination will support EC in program decision for FP6 rationale and long term plan.

Description of work T5.1 Project start dissemination Promotion activity and disseminating knowledge about the initiative and promoting the research, studies in order to progressively enhance the users base. Organization of a project open conference will present the project objectives to a large community including the relevant user groups, scientific bodies, EC authorities, national and European decision makers, and potential selected non-EU representatives. This activity aims to promote the concept of the project in order to raise awareness, create interest and encourage participation / follow-up actions. T5.2 Dissemination planning This task is dedicated to draw a dissemination plan, to identify target audiences, to detail actions, timing, procedures and actions for the dissemination activities, the expected benefits, and describe which methods of dissemination will be used by the partners. This plan is for the project regular information and exploitation of the results. It will also be used by all partners as a tool to record events and activities that take place during the life of the project. The key elements structuring the plan are: - Users: a consideration of who would benefit from learning about the findings, leading to define scope and characteristics of the potential users of the dissemination activities; - Content: type of messages to be released; - Source: information source and adaptation; - Medium: capabilities and resources that will be required to deliver the information in the most effective conditions and access rules; - Availability: information quality and update. The plan will be endorsed by the partners and submitted to the European Commission for approval. T5.3 Project activities dissemination This activity is targeted to inform constantly about the progress of the project for its full duration and provide feedback to the project. - Elaborate a promotion/dissemination plan - Manage the specification, development and maintenance of a project Web site, structured for wide communication, including restricted access when needed. - Elaborate adequate messages and communication materials with respect to targeted people and envisaged event - Write a newsletter about the project situation and significant results, at least every 6 months (with additional special issues if needed) - Assist in the preparation of the annual CYCLOPS workshop - Interface with the external bodies and find ways to integrate CYCLOPS presentation and information in existing official publications, seminars, workshops - Maintain the agenda of conferences, workshops in relation with the CYCLOPS activities - Develop and maintain a knowledge data base of the project T5.4 Project results dissemination This activity aims to disseminate the results of the project to proper target audiences (Civil Protections, research centres, SMEs,etc.) The partners are committed to maximize the project impact. Dissemination will be continuous throughout the project time frame, and requires the development of a dissemination strategy, shared by the EC and the project manager board, giving clear responsibility to one partner in implementing this strategy. One of the most significant aspects of this strategy is to generate dissemination material in different format and for different media to reach the intended target audiences. This is a list of documents that will be produced for general communication support actions: - Brochure, summary paper: 3 to 4 illustrated pages describing the objectives of the project ; - Poster: a large sized and visually impressive poster will be produced for display at exhibitions, workshops and conferences; - Newsletter distributed on a regular basis (6 months): a sort of logbook summarizing the activities and significant outcomes from the project, including meetings agenda, events and communication actions; - Description sheet of the case study: this is a very concentrated technical and operational information form about the studies, functions, input/output, operations, performances; - Logo: identity created for the project to facilitate clear and consistent communications. The logo will be used on all documentation, promotional/publicity literature, exhibition boards, CD-ROM, and on the project web site. T5.5 Exploitation This activity aims to define the plan for the exploitation of CYCLOPS results. The CYCLOPS E-Infrastructure are dedicated to risk management actors (Civil Protection services, land planning and risks prevention services, etc...) at various territorial levels (European, National, Regional) and in different countries with different organisations and needs and will have to be flexible and adapted to the needs of this community. In particular, the exploitation is ensured by a network of operators “distributed” in the different European countries or regions. This scheme will be necessary adapting to the specificities of each country, region and bodies, implementing the research and the studies. Moreover the WP includes activities aimed to evaluate and assess progresses and results as regards the Operational Goals 5.3 and 6.1. The results of these activities will be documented in quarterly internal reports for the Project Management Board.

Deliverables D2 (PM1) Project open conference This deliverable consists of a conference planned to meet Grid, Civil Protection and GMES experts broaden the opportunities for dialogue and discuss the EGEE platform for Civil Protection applications also towards other national and transnational organization. D4 (PM3) Dissemination Plan The Dissemination Plan describes the actions to be taken for an effective dissemination of CYCLOPS during the entire project extension. It defines the scheduling of dissemination for each phase (raise of awareness, project activities dissemination, project results dissemination) taking into account a typical set of key factors (namely Users, Content, Source, Medium, Availability). D12 (PM12) Mid-term project conference This deliverable consists of a workshop planned to disseminate CYCLOPS activity and to collect useful comments for future direction of the project. For this conference an update of the CYCLOPS reference architecture will be available. D18 (PM23) Project results presentation This document is a report collecting the CYCLOPS project results for dissemination towards different interested audience such as Grid communities, other Civil protection agencies, but also national and international initiative and projects, SMEs, etc. It includes training activities reporting and results . D19 (PM23) Final Plan for using and disseminating knowledge The Final Plan for using and disseminating knowledge will describe the participants’ actual achievements in dissemination and their plans at that time for the exploitation of their results - for the consortium as a whole, or for individual participants or groups of participants. The Plan for using and disseminating knowledge is maintained through the lifetime of the project. D20 (PM23) Report on raising public participation and awareness This deliverable is a document reporting the extent to which actors beyond the research community have been involved to help spread awareness and to explore the wider societal implications of the proposed work. It includes the content provided in the training sections It includes training activities reporting and results . D21 (PM23) Project final conference This deliverable consists of a conference planned to present the CYCLOPS results to many different communities: scientific and technological, Civil Protection, GMES and Earth Observation.

Milestones and expected result M5.1 (PM3) Dissemination started The dissemination plan is clear: the what, when, how, by whom and to whom (target audiences) of dissemination activities are decided. It will be decided which dissemination activities will be part of the proposed action and which will follow only after the end of the project. The project start and objectives are disseminated through several ways (web site, newsletter, etc.) M5.2 (PM24) Project results disseminated The results of CYCLOPS project are disseminated to different targets, and initiatives for the full exploitation through future specific R&D projects are undertaken.

Justification of financing requested An effort of less than 1 FTE is estimated for a total amount of 70k€ (7k€*10); travels; costs for events organizations, publications, conference participations for a total amount of 80k€

# 8. Project resources and budget overview

## 8.1 Efforts for the project

The Project effort is summarized in the Project Effort Form. It shows that management activities count for about 3.6% of the total budget and they do not exceed 7% of each participant budget. The core activities (WP3 and WP4) require the 60% of the budget (about 24% and 36% respectively for WP3 and WP4), while the coordination and dissemination activities count for the remaining 36% (18% each for WP2 and WP5).

Concerning the amount of required financing, it should be considered that the work is mainly made of study and analysis activities. This implies that the most part of resources are human resources involved in working and expert groups. Their effort can be measured in man-months (MM) of FTE (Full-Time-Employers) units. An average cost around 7,000 €/MM (20% overheads included) is considered for estimation. This should be considered made of: a weighted average of two different personnel cost categories such as engineers (for working group) and researchers/scientists (for working and expert groups); travel costs; other minor costs (publications, conference fees, equipment).

On a global view, the core activities (WP3 and WP4) and the coordination activity (WP2) require a total effort of about 90 MM in 18 months (see Gantt chart below). This is estimated considering a working group of 10 involved part-time in the project.

Concerning the participants budgets, the form shows that, generally, Civil Protection agencies are mainly involved in the WP3 (Civil Protection systems analysis) and scientific partners (IMAA and TEI-CR) are mainly involved in WP4. It is important to note that the CP-CH budget is substantially lesser than other Civil Protections authorities. This is due to the fact that many activities related to the Greek Civil Protection system are performed by the scientific partner (TEI-CR). On the contrary, DDSC and SNBPC directly contribute to research and innovation strategies definition. These choices depends on the organization and internal resources of the different Civil Protections authorities. DDSC and SNBPC are national agencies, while CP-CH is the Civil Protection Unit of a local public body.

Finally, INFN is obviously involved in the coordination activity to complement EGEE project, but it also provides contribution to WP4.

SSA Project Effort Form

(expressed in person-months)

|  | DPC | INFN | IMAA | DDSC | CP-CH | TEI-CR | SNBPC | TOTAL ACTIVITIES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities specific for the Support Action |  |  |  |  |  |  |  |  |
| WP 2 - Coordination with EGEE activities | 1,25 | 11,75 | 3,25 | 1,75 | 0,00 | 1,75 | 1,75 | 21,50 |
| WP 3 - Civil Protection systems analysis | 9,75 | 1,50 | 3,25 | 5,00 | 1,25 | 3,25 | 5,00 | 29,00 |
| WP 4 - Research and Innovation Strategies definition | 6,25 | 5,50 | 11,00 | 6,50 | 0,00 | 6,50 | 6,50 | 42,25 |
| WP 5 - Dissemination and Exploitation | 4,25 | 2,25 | 2,25 | 4,25 | 2,25 | 2,25 | 4,25 | 21,75 |
| Total’specific activities ‘ | 21,50 | 21,00 | 19,75 | 17,50 | 3,50 | 13,75 | 17,50 | 114,50 |
| Consortium management activities |  |  |  |  |  |  |  |  |
| WP 1 - Management | 1,50 | 0,50 | 0,50 | 0,50 | 0,25 | 0,75 | 0,50 | 4,50 |
| Total management | 1,50 | 0,50 | 0,50 | 0,50 | 0,25 | 0,75 | 0,50 | 4,50 |
| TOTAL per PARTICIPANT | 23,00 | 21,50 | 20,25 | 18,00 | 3,75 | 14,50 | 18,00 |  |
| Overall TOTAL EFFORTS |  |  |  |  |  |  |  | 119,00 |

SSA Project Effort Form

(expected budget in € for activities in which participants are involved)

|  | DPC | INFN | IMAA | DDSC | CP-CH | TEI-CR | SNBPC | TOTAL PARTICIPANT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Support activities |  |  |  |  |  |  |  |  |
| WP 2 - Coordination with EGEE activities | 8.000,00 | 82.000,00 | 22.000,00 | 12.000,00 | 0,00 | 12.000,00 | 12.000,00 | 148.000,00 |
| WP 3 - Civil Protection systems analysis | 68.000,00 | 11.000,00 | 23.000,00 | 35.000,00 | 8.000,00 | 23.000,00 | 35.000,00 | 203.000,00 |
| WP 4 - Research and Innovation Strategies definition | 44.000,00 | 39.000,00 | 77.000,00 | 45.000,00 | 0,00 | 45.000,00 | 45.000,00 | 295.000,00 |
| WP 5 - Dissemination and Exploitation | 30.000,00 | 15.000,00 | 15.000,00 | 30.000,00 | 15.000,00 | 15.000,00 | 30.000,00 | 150.000,00 |
| Total support activities | 150.000,00 | 147.000,00 | 137.000,00 | 122.000,00 | 23.000,00 | 95.000,00 | 122.000,00 | 796.000,00 |
| Management activities |  |  |  |  |  |  |  |  |
| WP 1 - Management | 10.000,00 | 3.000,00 | 3.000,00 | 3.000,00 | 2.000,00 | 5.000,00 | 3.000,00 | 29.000,00 |
| Total management | 10.000,00 | 3.000,00 | 3.000,00 | 3.000,00 | 2.000,00 | 5.000,00 | 3.000,00 | 29.000,00 |
| TOTAL ACTIVITIES | 160.000,00 | 150.000,00 | 140.000,00 | 125.000,00 | 25.000,00 | 100.000,00 | 125.000,00 | 825.000,00 |

## 8.2 Overall budget for the project (Forms A3.1 & A3.2 from CPFs)

The spreadsheet below reflects the CPF A3.1 form

| Nr | Partner | Cost model |  | SA (€ x 1.000) | Management (€ x 1.000) | TOTAL (€ x 1.000) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | DPC | AC | Direct cost | 130.833 | 10.000 | 140.833 |
|  |  |  | of which Subcontracting | 35.000 |  | 35.000 |
|  |  |  | Indirect cost | 19.167 |  | 19.167 |
|  |  |  | TOTAL elegible cost | 150.000 | 10.000 | 160.000 |
|  |  |  | EC CONTRIBUTION | 150.000 | 10.000 | 160.000 |
| 2 | INFN | AC | Direct cost | 122.500 | 3.000 | 125.500 |
|  |  |  | of which Subcontracting |  |  |  |
|  |  |  | Indirect cost | 24.500 |  | 24.500 |
|  |  |  | TOTAL elegible cost | 147.000 | 3.000 | 150.000 |
|  |  |  | EC CONTRIBUTION | 147.000 | 3.000 | 150.000 |
| 3 | CNR-IMAA | FC | Direct cost | 114.167 | 3.000 | 117.167 |
|  |  |  | of which Subcontracting |  |  |  |
|  |  |  | Indirect cost | 22.833 |  | 22.833 |
|  |  |  | TOTAL elegible cost | 137.000 | 3.000 | 140.000 |
|  |  |  | EC CONTRIBUTION | 137.000 | 3.000 | 140.000 |
| 4 | DDSC | AC | Direct cost | 105.000 | 3.000 | 108.000 |
|  |  |  | of which Subcontracting | 20.000 |  | 20.000 |
|  |  |  | Indirect cost | 17.000 |  | 17.000 |
|  |  |  | TOTAL elegible cost | 122.000 | 3.000 | 125.000 |
|  |  |  | EC CONTRIBUTION | 122.000 | 3.000 | 125.000 |
| 5 | CP-CH | AC | Direct cost | 19.167 | 2.000 | 21.167 |
|  |  |  | of which Subcontracting |  |  |  |
|  |  |  | Indirect cost | 3.833 |  | 3.833 |
|  |  |  | TOTAL elegible cost | 23.000 | 2.000 | 25.000 |
|  |  |  | EC CONTRIBUTION | 23.000 | 2.000 | 25.000 |
| 6 | TEI-CR | AC | Direct cost | 79.167 | 5.000 | 84.167 |
|  |  |  | of which Subcontracting |  |  |  |
|  |  |  | Indirect cost | 15.833 |  | 15.833 |
|  |  |  | TOTAL elegible cost | 95.000 | 5.000 | 100.000 |
|  |  |  | EC CONTRIBUTION | 95.000 | 5.000 | 100.000 |
| 7 | SNBPC | FC | Direct cost | 101.667 | 3.000 | 104.667 |
|  |  |  | of which Subcontracting |  |  |  |
|  |  |  | Indirect cost | 20.333 |  | 20.333 |
|  |  |  | TOTAL elegible cost | 122.000 | 3.000 | 125.000 |
|  |  |  | EC CONTRIBUTION | 122.000 | 3.000 | 125.000 |
|  | TOTAL elegible cost |  |  | 796.000 | 29.000 | 825.000 |
|  | EC CONTRIBUTION |  |  | 796.000 | 29.000 | 825.000 |

Since even the co-ordinator will receive less than 150.000 for the first reporting period, all partners must produce audit certificates only at the end of the project as stated by the Special Clause 39:

“Notwithstanding the provisions of Article 7.2 of this contract, contractors requesting a Community financial contribution for one or more reporting periods of less than €150,000, need not submit an audit certificate, until the cumulative request for Community financial contribution is equal to or exceeds €150,000 for the reporting periods for which an audit certificate has not yet been submitted. In all cases an audit certificate shall be submitted at the latest 45 days after the final reporting period. This final audit certificate shall cover all period/s for which an audit certificate has not been previously submitted. [Decision DL/2005/1150]

The spreadsheet below reflects CPF A3.2 estimated breakdown per reporting period

| WP | Leader partner number | PERIOD 1 (1 - 12 months) 1 YEAR | PERIOD 2 (13 - 24 months) 1 YEAR | Totale Project |
| --- | --- | --- | --- | --- |
| WP 1 | 1 (DPC) | 14.210 | 14.210 | 28.420 |
| WP 2 | 2 (INFN) | 80.440 | 81.100 | 161.540 |
| WP 3 | 4 (DDSC) | 198.940 | 0 | 198.940 |
| WP 4 | 3 (CNR-IMAA) | 28.910 | 260.190 | 289.100 |
| WP 5 | 7 (SNBPC) | 73.500 | 73.500 | 147.000 |
|  | Totale | 396.000 | 429.000 | 825.000 |

## 8.3 Management level description of resources and budget

Financial Information whole duration of the project

|  |  | management activities |  | Co-ordination or support activities |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Prt. N° | Cost Model | Costs (€) | Requested grant to the budget (€) | Costs (€) | Requested grant to the budget (€) | Costs (€) | Requested grant to the budget (€) |
| 1 | AC | 10.000 | 10.000 | 150.000 | 150.000 | 160.000 | 160.000 |
| 2 | AC | 3.000 | 3.000 | 147.000 | 147.000 | 150.000 | 150.000 |
| 3 | FC | 3.000 | 3.000 | 137.000 | 137.000 | 140.000 | 140.000 |
| 4 | AC | 3.000 | 3.000 | 122.000 | 122.000 | 125.000 | 125.000 |
| 5 | AC | 2.000 | 2.000 | 23.000 | 23.000 | 25.000 | 25.000 |
| 6 | AC | 5.000 | 5.000 | 95.000 | 95.000 | 100.000 | 100.000 |
| 7 | FC | 3.000 | 3.000 | 122.000 | 122.000 | 125.000 | 125.000 |
| Total |  | 29.000 | 29.000 | 796.000 | 796.000 | 825.000 | 825.000 |

The following table details the project budget:

|  |  |  |  | PERIOD 1: 1- 12 MONTHS (1st year) |  |  |  | PERIOD 2: 13-24 MONTHS (2nd year) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP | Work Package Name | Leader partner number | man months | personnel | Travel | subcontracting | Total perdiod 1 | man months | personnel | Travel | subcontracting | Total perdiod 2 | Total man months | Total project |
| WP 1 | management | 1 (DPC) | 2,15 | 12.760 | 1.450 | 0 | 14.210 | 2,35 | 11.260 | 1.450 | 1.500 | 14.210 | 4,50 | 28.420 |
| WP 2 | Coordination with EGEE activities | 2 (INFN) | 10,85 | 73.040 | 7.400 | 0 | 80.440 | 10,65 | 72.700 | 7.400 | 1.000 | 81.100 | 21,50 | 161.540 |
| WP 3 | Civil protection System analysis | 4 (DDSC) | 29,00 | 142.140 | 20.300 | 36.500 | 198.940 | 0,00 | 0 | 0 | 0 | 0 | 29,00 | 198.940 |
| WP 4 | Research and Innovation Strategies definition | 3 (CNR-IMAA) | 4,35 | 25.960 | 2.950 | 0 | 28.910 | 37,90 | 233.640 | 26.550 | 0 | 260.190 | 42,25 | 289.100 |
| WP 5 | Dissemination and Exploitation | 7 (SNBPC) | 10,65 | 58.000 | 7.500 | 8.000 | 73.500 | 11,10 | 58.000 | 7.500 | 8.000 | 73.500 | 21,75 | 147.000 |
|  |  | Total | 57 | 311.900 | 39.600 | 44.500 | 396.000 | 62 | 375.600 | 42.900 | 10.500 | 429.000 | 119 | 825.000 |

# 9. Other issues

## Gender issues

There are no particular gender issues arising from this initiative apart from those that have been affecting the European research community from the beginning. Indeed, female representation in Information Technology (engineering, mathematics and computer science) is far behind other academic activities, such as arts, literature and even medical/biological studies.

Gender issues are therefore not related specifically to the CYCLOPS Project activities but are dramatically inherent to Information Technology communities.

CYCLOPS will support parity through its different activities by promoting gender equality to Human Resources Management decision makers.

The following tables state that no sensitive ethical question are raised by the proposed project:

Ethical issues checklist

| Does your proposed research raise sensitive ethical questions related to: | YES | NO |
| --- | --- | --- |
| Human beings |  |  |
| Human biological samples |  |  |
| Personal data (whether identified by name or not) |  |  |
| Genetic information |  |  |
| Animals |  |  |

Table B. Proposers are requested to confirm that the proposed research does not involve:

- Research activity aimed at human cloning for reproductive purposes,

- Research activity intended to modify the genetic heritage of human beings which could make such changes heritable

- Research activity intended to create human embryos solely for the purpose of research or for the purpose of stem cell procurement, including by means of somatic cell nuclear transfer.

| Confirmation : the proposed research involves none of the issues listed in Table B | YES | NO |
| --- | --- | --- |
|  |  |  |

# Appendix A - Consortium description

## A.1 Participants and consortium

### Participant roles

The CYCLOPS Consortium consists of seven partners from four EU member countries:

- Dipartimento di Protezione Civile (DPC) [Italy];

- Istituto Nazionale di Fisica Nucleare (INFN) [Italy];

- Istituto di Metodologie per l’Analisi Ambientale (IMAA) [Italy];

- Direction de la Défense et de la Sécurité Civiles  (DDSC) [France];

- Prefecture of Chania  (CP-CH) [Greece];

- Technological Educational Institute of Crete (TEI-CR) [Greece]

- Serviço Nacional de Bombeiros e Protecção Civil (SNBPC) [Portugal]

Four of them (DPC, CP-CH, DDSC and SNBPC) are national or regional authorities in charge of Civil Protection activities, two of them (IMAA and TEI-CR) are scientific partners active in GMES and Earth Observation research activities and in ICT applications for those sectors. The last one (INFN) is the scientific partner for Grid technologies research and applications.

The Civil Protection agencies provide the description of the Civil Protection systems, the definition of typical use-cases both for:  a) testing the EGEE infrastructure in GMES applications and b) investigating possible and required enhancements.  They play also an important role in the dissemination activities toward other national organizations and institutions involved in GMES activities and toward their counterparts in other countries. DPC, as the project coordinator, is also responsible of management activities; DDSC is responsible of the specific Work Package dedicated to Civil Protection analysis and SNBPC is responsible of project setup phase.

The scientific partners provide the expertise and knowledge in the scientific and technological domains interested by CYCLOPS: GMES and related sectors, and Grid technologies.

IMAA and TEI-CR have an important experience in the use of Information and Communication Technologies (ICT) for advanced environmental applications. Thus they are the partners committed to relate the Grid expert partner, INFN, and the users (Civil Protection agencies). Their main contributions regard the definition of the system requirements of the Grid platform for GMES applications, and the test and study activities for the definition of the research and innovation strategies. They are also in charge of the dissemination of CYCLOPS in their scientific community. In particular, IMAA is responsible of the studies activities for defining the research and innovation strategies and TEI-CR is responsible of dissemination and exploitation.

INFN is member of EGEE Project with great expertise in Grid technology applications to the  e-Sciences. It plays the key role of coordinating the CYCLOPS efforts with the EGEE activities. This internal dissemination and coordination activity is fundamental for CYCLOPS success. Moreover INFN gives an important contribution to the system requirements analysis, and to the study for research and innovation strategies definition.

As the Partner Description Forms below show, the Consortium is made of partners with complementary expertise and characteristics.

The four Civil Protections authorities are chosen considering their internal organization, geographical position and existing relationships. In particular, the Italian, French and Portuguese Civil Protection authorities are examples of national agencies, while the Greek partner is a local agency (Greek prefectures are public bodies with a specific Civil Protection Unit in charge of making decisions on Civil Protection measures and co-ordinating Civil Protection authorities and competent services in case of local disasters). This allows to consider two different organization models, with different scenarios that could affect the enabling infrastructure. Indeed a relevant aspect is held by the role of the different European civil protection structures involved as participants in the framework of the project, mainly concerning with the general heterogeneity existing among both operative structures and infrastructures employed to support the decisional system. Based on such item, further interesting contribution, emerging from the expected results, refers to the opportunity to reinforce the European civil protection system by ensuring data and information exchange in real time as well as the increasing in the computational features of the forecasting models providing a direct support from the research and institutional subjects not strictly involved in the procedures but capable to enable a suitable data-flow. The opportunity to identify uniform procedures in the pre-operative and operative controlling chain allows in creating a common knowledge and behaviour of the civil protection systems in order to define an optimized communicational network that is extremely needed to manage risks and disasters. Moreover, the presence of agencies from neighbour countries (France and Italy) with strong relationships between them, allows to investigate cross-borders issues examining transnational Civil Protection scenarios.

The GMES scientific partners (IMAA and TEI-CR) have a great expertise both in the environmental monitoring, Earth Observation and GMES sectors and  in the application of advanced ICT to these sectors. Moreover, the existing relationships, both mutual and with Civil Protections authorities involved in the project, greatly simplify the CYCLOPS planned activities.

INFN is an important partner chosen for its great experience in the implementation and widespread use of large-scale Grid platforms specially in the e-Science sector. It is suited to establish a liaison between the scientific GMES community and the Grid technology community.

The following table summarize the participants roles. It shows the main contributions to WPs for each participant.

Participant main contributions for Work-Packages

| Particip. No. | Participant Acronym | WP 1 Management | WP 2 Coordination with EGEE activities | WP 3 Civil Protection systems analysis | WP 4 Research and Innovation Strategies definition | WP 5 Dissemination and Exploitation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | DPC | Project Management/ WP leader | Contribution in the EGEE dissemination | Major contribution for Business Process Analysis, Existing Analysis, Use Cases Definition | Contribution for testing EGEE infrastructure and porting of Civil Protection applications | Major contribution to the deliverables;dissemination towards Civil Protection communities |
| 2 | INFN | Contribution | WP leader | Contribution for System Requirements definition | Main contribution for the definition of the EGEE Requests for Enhancements | Dissemination towards Grid communities |
| 3 | IMAA | Contribution | Major contribution for reporting required middleware enhancements | Contribution for the Use-Cases and System Requirements definition | WP leader, main contribution for studying a Civil Protection Grid infrastructure and R&D strategies definition | Dissemination towards Earth Science community |
| 4 | DDSC | Contribution | Contribution in the EGEE dissemination | WP leader, contribution for Business Process Analysis, Existing Analysis, Use Cases definition | Contribution for testing EGEE infrastructure and porting of Civil Protection applications | Major contribution to the deliverables; dissemination towards the Civil Protection communities |
| 5 | CP-CH | Contribution | None | Contribution for Business Process Analysis, Existing Analysis, Use Cases definition | None | Dissemination towards Civil Protection communities |
| 6 | TEI-CR | Contribution | Contribution in the EGEE dissemination | Contribution for Business Process Analysis, Existing Analysis, Use Cases and System Requirements definition | Contribution for R&D strategies definition | Dissemination towards Civil Protection communities |
| 7 | SNBPC | Contribution | Contribution in the EGEE dissemination | contribution for Business Process Analysis, Existing Analysis, Use Cases definition | Contribution for testing EGEE infrastructure and porting of Civil Protection applications | WP leader, dissemination towards Civil Protection communities |

### Participants description

#### Dipartimento della Protezione Civile (DPC)

##### Description

The Dipartimento della Protezione Civile (Department of Civil Protection) is a division of the Italian Presidenza del Consiglio dei Ministri, and represents the national authority in charge of civil protection activity. Its fields of interest are planning, prevention and management of every type of risk all over the national territory. It plays the role of coordination of all the forces operating on Italian territory such as Italian Army, Navy, Air force, National Fire Department, Police authority, regional and local authorities, in order to warranty the safety for human life.  Further, the new asset of the civil protection is approaching to an operative and functional model mainly based on the concept of “real time risk prevention and management”, assumed as the time needed to actuate urgent actions for the safeguard of people and goods, as well as to replace the life condition pre-existing to the natural or human disaster. Then, the main target is to develop a “prevention system”, thought in the wide sense of forecasting, monitoring, overseeing, active contrast and early management of emergency, through the integration of surveying and modelling tools as well as shared informational system in real time, among all the “actors” involved in civil protection activities. The Italian Department of Civil Protection (DPC) was involved in many different European projects such as Formidable, Egeris, European, INTERREG IIC, Platform of New Technologies for Civil Protection. Currently, the DPC is involved in CARPE DIEM and RISK-AWARE project. Moreover, DPC is also involved within VI Aerospace GMES “Eurorisk-Preview” both for fire and volcanic risks topics and within the research projects SPREAD, ERAS and FIRESTAR on forest fire detection and prevention. Finally, DPC is represented as a Forest Fire Research project Evaluator within the European Commission General Research Directorate on Natural Disasters.

##### Resources deployed

The Italian Government establishes The National Alert System for Risks Management (NASRM) and states that such an early warning system has to be provided by the National Department of Civil Protection (NDCP) and by the Regional Civil Protection Authorities (RCPA) through a national network of Centres for Forecasting and Surveillance of Effects (CFSE) which may act along with the support of Centres for Technological and Scientific Services (CTSS).  CFSEs are the operative units able to collect, processing and exchange every type of meteo, geo, hydro, hydro-geo, marine, volcanic, seismic, etc. data and information, gathered from modelling outputs and monitoring systems and shared  within the national civil protection network supporting the NDCP and RCPA decisions. Such CFSE, and the operative personnel working in, are the main resources to be involved in the project for co-ordinating activities and to define the requirements for the GRID system as well as to validate the output products to be inserted in the pre-operational and operation chain.

##### Principal Investigator

Dr. Bernardo De Bernardinis is General Director of the Risk Planning, Assessment and Prevention Office at the Italian National Department of Civil Protection. He is Professor at University of Basilicata, Roma “Tor Vergata” and Cagliari in Fluid Mechanics and Hydraulics, Member of the Environmental Impact Assessment National Committee  (Italian Ministry of Environment); Member of the Technical Committee for the Italian national programmes for “Potenziamento delle reti di monitoraggio meteo-idropluviometrico” and “Rete nazionale dei radar-meteorologici”; Member of the GMES Steering Committee. He is author of about 70 papers concerning fluid mechanics, hydraulics, river hydraulics, environmental planning and management, natural hazards and risk management. He is advisor in several national and international research activities as well as he is scientific responsible in projects involving the Department of Civil Protection, universities, research centers, public and private land management enterprises.

#### Istituto Nazionale di Fisica Nucleare (INFN)

##### Description

The INFN - the National Institute of Nuclear Physics - is an organization dedicated to the study of the fundamental constituents of matter, and conducts theoretical and experimental research in the fields of subnuclear, nuclear, and astroparticle physics. It was founded in 1952, and owns 4 National Laboratories and 19 Divisions (Sezioni) operating in strong synergy with the Physics Departments at all major Italian Universities. The INFN workforce includes about 2000 of its own employees, and almost 2000 university employees involved in research conducted by the Institute. INFN has a long tradition of dissemination and training, dedicated both to the scientific community and to the general public. INFN has a long pioneering experience in the implementation and widespread use of large-scale Grid platforms. Since the year 2000 INFN is involved in many national and international Grid projects. It played a main role in DataGrid, DataTAG, LCG, Coregrid, GridCC and EGEE projects, with responsibilities in the Grid workload management services, interoperability between European and US Grids, and Grid resource access services. INFN runs a Production Grid for Scientific Application (http://grid-it.cnaf.infn.it/) based on the EGEE middleware, composed of more than 800 CPUs and 100 TB of storage resources distributed in more than 20 sites in Italy. INFN Grid is part of the wider EGEE Grid which collects about 130 sites spread around Europe.

INFN is partner of some new project approved by Th 6th Framework Program, like EUMEDGRID, EUCHINAGRID, BIONFOGRID and ETICS. Some INFN GRID new Projects have been approved and will be founded by the Italian Ministry for Research.

INFN in coordinating a Consortium initiative for the Open Middleware Enabling Grid applications in Italy (c-OMEGA).

##### Resources deployed

The project implementation requires the deployment of a small pilot dedicated Grid test-bed where to install and test the GMES applications in the Grid environment. Such a test-bed will be based on the up to date existing EGEE middleware, no middleware developments are planned within the scope of the CYCLOPS project.  The Grid dedicated test-bed will consist of a minimal set of Grid elements:

1 UI (User Interface), 1 RB/BDII (Resource Broker/Berkeley Database Information Index), 1 VO (Virtual Organisation)  server, 1 RLS (Replica Location Server), 2 CEs (Computing Elements), 2 SEs (Storage Elements), 2 WNs (Worker Nodes), for a total of 10 bi-processor PCs.

Human resources are required in order to carry out:

- the dissemination activity to explain the EGEE Grid middleware to GMES community and application experts

- the setup, the management and the operation control of the Grid dedicated test-bed;

- the study, joint with the GMES application experts, on how to interface the GMES applications to the EGEE middleware;

##### Principal Investigators

Dr. Mirco Mazzucato is Director of INFN-CNAF (Centro Nazionale per la Ricerca e Sviluppo nelle Tecnologie  Informatiche e  Telematiche). He is involved in many initiatives on Grid technologies at national and international level. Currently,  he is member of the Grid Deployment Board (GDB) and INFN representative in the CERN LHC Computing Grid project; member of the Management Board and of  the Executive Committee of the FP6 Grid infrastructure project EGEE; Head of the Research Unit 4 of the FIRB MIUR Grid.it project; Italian Delegate at the European IST Committee and of the e-Infrastructure Reflection Group (e-IRG); Member of the International Grid EU-US coordination group. He was Member of the Management Boards of the FP5 European Projects DataGrid and DataTAG; INFN national coordinator of many HEP experiments based at CERN: NA16, NA27 and DELPHI; Head of the Team who set up in 1988 the DELPHI INFN Farm for the offline productions, one of the world pioneering examples of CPU clusters based on commodity components (Digital workstations connected via Ethernet); Member of the DELPHI Management Board from1993 to 2000 as coordinator of the offline computing activity; Chairman of the CERN LHC Computing Board from 1996 to 2000; Chairman of the CNTC  the Committee which has fostered the introduction of the new computing technologies in INFN from 1998; President of the INFN Computing Committee from 1998 to 2001; General Chair of the Computing in High Energy Physics (CHEP) Conference 2000 ; Member of CHEP Advisory Board in 2001 and 2003 and Chair of the Grid Computing session in 2001; Member of the SC2002 program committee. He is author of more that 250 publications.

#### Istituto di Metodologie per l’Analisi Ambientale (IMAA)

##### Description

IMAA-CNR is an Operational Center of the Civil Protection, and is a member of OGCE. Its research focuses on information and communications technologies (e.g. Spatial Data Infrastructures) to harmonize, manage and share Earth Sciences data and information in the framework of Information Society applications. Besides, IMAA has complete chains to receive, archive and process NOAA-HRPT and MSG-HRIT data; there exists a long-term historical AVHRR archive consisting of more than 8 years of co-located imagery, soon available on-line via Web. IMAA gained specific knowledge and experience on international tools and standard related to Earth Sciences data access and interoperability, such as: OPeNDAP, THREDDS, netCDF, ncML., ESML and GML. As a matter of fact, IMAA has contributed to several middleware specifications, such as: UNIDATA THREDDS, ncML and ncML-GML. IMAA participates in several international projects, like the 6FP projects: GRIDCC “Grid-enabled Remote Instrumentation with Distributed Control and Computation”, EUORORISK/PREVIEW, the NoE GMOSS (Global Monitoring for Security and Stability) and the IP NEEDS  (“New Energy Externalities Developments for Sustainability”), and THREDDS/DLESE funded by the American NSF. IMAA is one of the initiator (along with UCAR, NASA and George Mason University) of the OGC Interoperability Experiment GALEON (Geo-interface to Atmosphere, Land, Earth, Ocean netCDF), which aims ad experimenting the OGC WCS to implement Earth Sciences and GIS communities interoperability. Jointly with the Italian Dept. of Civil Protection and the Ministry of Environment, IMAA is in charge of the INSPIRE SDIC, called INTERO (Italian National earTh & Environment Research cOmmunity) in order to provide requirements and suggestions on Earth Sciences Real Time data and services for INSPIRE. IMAA is a consultant of the Italian Ministry of Environment to design and implement the National Cartographic System. IMAA is heavily involved in the GMES (Global Monitoring of Environment and Security) initiative at the National and International level.

##### Resources deployed

IMAA is equipped with advanced resources for Earth Sciences applications. In particular the following material resources will be made available to CYCLOPS Project:

- Infrastructure for storage, sharing and processing of Earth Observation Data:

- Storage area network (9 TB on-line);

- 5 Network Attached Storage (800 GB each);

- Cluster HPC LINUX 16+2 nodes;

- Tape Library LTO, 30 TB;

- Communication facilities (1-10 Gb/s);

- Web-based publishing system for data products;

- NOAA/HPRT receiving station;

- MSG/HRIT receiving station;

- AVHRR images historical archive;

IMAA will also provide human resources with expertise in the ICT application to GMES and Earth Sciences in order to contribute to:

- system requirement analysis;

- the definition of research and innovation strategies, and related work package management;

- dissemination activities;

##### Principal investigators

Dr Stefano Nativi He is in charge of the Operative Unit of CNIT (the Italian National Interuniversity Consortium for Telecommunications) at IMAA-CNR and member of its Scientific Council. He is professor (with no-track position) at the University of Florence (“Web Services management” for the degree in Information Engineering) and at the University of Padua (“Land Management Systems” for the degree in Informatics). He is member of the Italian Scientific and Technological Committee for GMES (CTSG). He is the representative person of IMAA–CNR, in the Open Geospatial Consortium (ex OpenGIS). He represents Italy –as an expert- in the standardization work of the CEN Technical Committee 287 for establishing a European Spatial Data Infrastructure. He is part of the Metadata Core Drafting Team for the European INSPIRE initiative (his role is: link with GMES+ Grid). He is the CNR representative in the INTERO (Italian National earTh & Environment Research cOmmunity) SDIC (Spatial Data Infrastructure Community) for INSPIRE. He has been Distinguish Visitor at the l’NCAR/UCAR/ UNIDATA working on the subject: “Interoperable Data Systems” in the field of geospatial information and Earth sciences. He has been PI and co-PI of numerous projects funded by the Italian Space Agency (ASI) and the EC. His scientific interests include the multi-disciplinary sector of ICT for  Earth Sciences applications.

Prof. Vincenzo Cuomo Since 1987 he has been a full professor of Physics at the University of Basilicata's Faculty of Engineering. He is the director of the new Institute of Methodologies for Environmental Analysis (IMAA) and is the chairman of the  Potenza (Italy) Research Area of the Italian National Research Council (CNR). 	He is  member of GMES Italy “Steering Committee” and he has been Italian member of GMES “Data Policy” Working Group during GMES initial period (2001-2003). He is member of the “Commissione Grandi Rischi da Incendi Boschivi” – Protezione Civile (Risk Committee for Forest Fires of Civil Protection). He is Italian member of AIE agreement “Energy and Tecnology System Assessment Project”. He is PI for the European Organization for the Exploitation of Meteorological Satellites (EUMETSAT) within the framework of the development of the IASI high resolution satellite interferometer which will be launched with the METOP mission. He is responsible of the stream “Energy systems modelling and internalisation strategies, including scenarios building” in the IP NEEDS  (“New Energy Externalities Developments for Sustainability”) and is involved in many European Project as: Eurorisk Preview, GRIDCC, GMOSS, Earlinet Network, etc. He is member of the “Fondazione IDIS” that is performing the project “Città della Scienza” in Naples. He is the promoting  the Industrial Research Project “Development of industrial district of Earth Observation” (PON 200-2006). He is responsible of  the University of Basilicata section in the National Inter-University Atmospheric and Hydrospheric Physics Center (CINFAI). He is member of the National Inter-University Telecommunications Consortium (CNIT) Scientific Council. He has been member of the Scientific Committee of Italian Space Agency (ASI) and he is or has been chair of many projects in the framework of ASI activities. He has been responsible of many projects in the framework of U.E., ESA, EUMETSAT and IEA activities.

##### Selected publications of the IMAA staff:

S. Nativi, J. Caron, E. Davis and B. Domenico, “Design and implementation of netCDF Markup Language (NcML) and its GML-based extension (NcML-GML)”, in printing on the Computers & Geosciences Journal, Elsevier Publication.

S. Nativi, L. Bigagli, P. Mazzetti, V. Cuomo, 2004, “Applying SOA to Earth Observation: the COS(OT) experience”, Proceedings of ICTTA’04, Damascus (Syria), April 2004, IEEE Press, ISBN 0-7803-8482-2/04, 2004.

B.Domenico, J.Caron, E.Davis, R.Kambic and S.Nativi, May 2002, "Thematic Real-time Environmental Distributed Data Services (THREDDS): Incorporating Interactive Analysis Tools into NSDL", Journal of Digital Information, Vol.2 Issue 4, May 2002.

#### Direction de la Défense et de la Sécurité Civiles (DDSC)

##### Description

The Direction de la Défense et de la Sécurité Civiles (Directorate of Civil Defence and Safety) belongs to the Ministry of Interior and it is the French Civil Protection. The Director of Civil Defence and Civil Protection manages and coordinates the services responsible of:

- Planning, coordination and implementation of civil defence measures, protection of civilian population, prevention of civilian hazards of any kind, planning of civil defence and civil protection endeavours;

- Rescue actions oriented towards safeguard of persons and goods, during peace as well as in crisis times;

- Intervention forces of Civil Protection ;

- Assistance to local rescue and fire fighting services;

- Promotion of civil protection training and professional education of fire fighter commissioned officers.

Civil protection is a mission led by the DDSC and following the territorial organisation and involving several actors such as medical services, police, flood alert centres etc.

The International Relations Department liaises with the European commission and its sister organisations in Europe, and supervises usage of new technologies for civil protection.

##### Resources deployed

The DDSC will take part to the Project Board with a high-rank professional fire-fighter officer. A commissioned professional officer shall take part to the Civil protection expert group whereas a geomatics engineer shall take part of the technical expert group. This latter task may be subcontracted to a Research and Development entity already conversant with GRID technology and e.g. hydrology. Such staff have experience in previous projects funded under national scheme such as the PACTES co-operative work for flood management or the PAREFEU fire management application. Furthermore the DDSC may provide a series of cases studies and would be interested in a demonstrator. DDSC would liaise with other institutions such as meteorological or flood alert services, scientific laboratories in hydrology or seismology and  volcano observatories as needed, using the relationship set in the context of the EURORISK activity.

##### Principal Investigator

Colonel Philippe Nardin is the head of the International relations department of DDSC. He has a thorough knowledge of France and European civil protection systems. He supervised the study “platform of new technologies for civil protection” and he is the chairman of the steering committee of the EURORISK PREVIEW and RISKEOS projects relating to GMES.

P. Nardin and J. Béquignon. “La plate-forme des nouvelles technologies pour les protections civiles européennes” , proc. Euro  Mediterranean Seminar on New technologies and civil protection, Madrid, 6_8 October 2003

#### Civil Protection of Chania Prefecture (CP-CH)

##### Institute description

Within the competence of CP-CH lies the regional planning and organization of state services aiming to the protection of citizen's life, health and property from natural hazards, technological accidents and other disasters, causing emergency situations during peace period and to the protection of cultural heritage, historical buildings and monuments, the resources and the infrastructure. On May 2002, a new Law (N. 3013) upgraded the role of Civil Protection in Greece, emphasizing the importance of citizen protection and assigning roles to local authorities. The national CP authorities cooperate with the CP directorates in the 13 regions, the CP departments in the 54 prefectures and the CP offices in the municipalities of the country. All competent authorities at prefecture level are parts of the CP system. Among them, Fire Brigade, Coast Guard, Police, Emergency Medical Care Service, Armed Forces, Earthquake Planning and Protection Organization, Network Services and Meteorological Service are included. Finally, CP-CH cooperates with CP General Secretariat for the development of the National System for Volunteer Organizations in the field of Civil Protection due to the fact that volunteers and Volunteer organizations have a significant role in emergencies.

##### Resources deployed

CP-CH's staff and infrastructure will be involved in the frame of the proposed project in order to gear, at all stages of the development of GRID system its main activities: Readiness of the personnel and means of civil protection. Elaboration of available scientific information for the mobilization of resources in case of emergencies. Coordination of emergency planning, response and recovery actions in emergencies at prefecture level. Implementation of the Annual National Planning at prefecture level in cooperation with competent authorities. Preparation of special reports for every major disaster (revisions, amendment and improvement of existing proposals are included). Assess information on weather forecasting and other precursory phenomena related with natural hazards, for the early notification and warning of the competent authorities and the general public. Public information and awareness at prefecture level. Organization and promotion of volunteer organizations work in the field of CP. Cooperation with the competent authorities towards preparing plans and regulations in the field of prevention at prefecture level. Programming of the necessary annual provisions of means and human resources in cooperation with competent authorities at prefecture level. Support and promotion (coordination, planning) of the research, education and training in the field of CP. Participation to the Civil Protection Emergency Operation Center, a unit functioning on a 24/24h basis, equipped with communication systems (including mobile units that can be transported by C-130 aircraft) and directly connected with the competent services all over the country.

##### Principal Investigator

Mr. George Agorastakis (born on 1952) is Vice-Prefect of Prefecture of Chania in Crete. He holds B.Eng. in Mechanical Engineering and has for many years professional service and experience in industrial management, electromechanical constructions and installations and public works. Last years is mainly devoted, as coordinator, in the development planning and the submission and execution of many development programs and projects (especially for energy resources, environmental planning, management and protection) for Chania Prefecture.

#### Technological Educational Institute of Crete (TEI-CR)

##### Description

The Geophysics and Seismology Laboratory of the Technological Educational Institute of Crete (TEI-CR-GSL) has been ceaselessly contributing to the advancements made the past 10 year in the field of Geophysics and Seismology in Crete. In the course of its activities over the years, a better understanding of the seismicity and the seismic risk of various areas of South Aegean were accomplished. At the same time a large number of microzonation studies contributing in seismic hazard mitigation were performed and many local seismic station networks for monitoring and determining the seismotectonic regime of the certain areas- were deployed. Certain applications of theoretical aspects of seismology to Greek data resulted in revised and/or local seismic intensity and seismic energy attenuation laws and in the determination of seismic source parameters for a large number of events. In recent years, major advances were made ίn the field of Geophysics, due mainly to the application of dynamic, seismic, electromagnetic and magnetotelluric methods. Emphasis was imposed on the application and of modern methodologies, e.g. seismic and geoelectric tomography, high resolution seismic reflection. TEI-CR-GSL is concerned both with the understanding the cause and mechanism of earthquakes and with determining the structure of the earth's interior, using seismic waves and other geophysical methods. The group includes seismologists, geophysicists and rock physicists. The mission of TEI-CR-GSL is to: Operate a network of seismic stations in the Crete region; Analyze the data obtained with the Crete seismic network; Compile data on historic and current earthquake activity in and around the region of Crete, exchange of information on earthquake activity in S. Aegean with other Research Institutes and Universities; Provide for education of the public in matters related to seismicity and earthquake risk in the Crete  region; Carry out grant- and contract- supported research on earthquake problems.

Geophysics and Seismology both theoretical and applied are major areas of expertise, in which TEI-CR-GSL has accumulated years of experience. TEI-CR-GSL employs the most advanced technology available in Seismology and Geophysics. As a multidisciplinary quantitative research field, the new advances in electronics and computer technology are immediately adapted into the projects being carried out. Our greatest research strengths are in network seismology, tectonics, earthquake source physics, earthquake hazard research, exploration seismology, and theoretical seismic wave propagation, Seismicity and Aftershock Studies, Engineering Seismology, Earthquake Site Effect Evaluation, Earthquake Risk and Seismic Hazard Evaluation, Mapping of Earthquake Faults by Remote Sensing & GIS Applications, Seismic Data Processing, Modelling and Inversion. TEI-CR-GSL maintains a seismological network over the entire region of Crete and S. Aegean (frontal part of the Hellenic Arc). Its research staff also has extensive experience with rapid deployment, maintenance and analysis of temporary networks for seismological and engineering studies. Such expertise has been expanded through participation in national and international research programmes.  TEI-CR-GSL  is able to offer its services in: Seismic Risk investigations in rural and/or urban areas and at sites of major infrastructures; Microzonation studies for seismic hazard mitigation in cities or other populated areas; Studies of seismic precursors tracing in areas of high or low seismic activity; Seismic source and strong ground motion research for designing major infrastructures; Seismotectonic studies for the location of active faults; Structure vulnerability due to potential seismic load in conjunction with soil category; Designing emergency response scenarios to potential earthquake disaster in specific regions; Seminars, lectures and publications aimed to inform the public on earthquakes and on the means of protection and hazard mitigation; Geophysical research; Problem solving in engineering seismology and geology i.e. identification of the depth and topography of the base rock for the foundation of major bridges, dams and port infrastructures; Seismic tomography studies, Geoelectric tomography studies, Cross-hole, Seismic refraction and Seismic reflection studies.

The development of the research in Geophysics and Seismology to high and exemplary standards is a scientific target and a strategic objective of the research group in TEI-CR-GSL. The Laboratory has an extensive and indigenous experience in the design, construction and maintenance of geophysical instrumentation and telemetric networks for surveys in seismic and volcanic areas and the continuous monitoring of geophysical fields. TEI-CR-GSLs research team to be involved in this project comprises an effective blend of highly qualified scientists in the research topics of seismology-geophysics, geophysical instrumentation and geo-informatics. The accumulated experience of the members of the Greek research team is a consequence of their extensive involvement in large number of national & international research programs, in co-operation with European and Japanese Universities and Research Institutes. Over the last five years the researchers of TEI-CR-GSL group have participated in the following research projects:

- Study of the ULF electromagnetic phenomena related to earthquakes (INTAS99);

- Contribution to seismic hazards using seismic and electromagnetic observations Greek-Russian R&T collaboration, General Secreteriat of Research & Technology;

- An expert system for the environmental monitoring and management in Crete , Region of Crete, MARMARA Earthquake Rehabilitation Project, MEDA-EU;

- Seismic Hazard in the frontal part of the Hellenic Arc. A contribution to Seismic protection of the old Venecian city in Chania-Crete” (Archemedes Project- Greek Ministry of Education);

- Non-linear mathematical problems in Geophysics and wave propagation, (Archemedes Project- Greek Ministry of Education);

- Study of the active tectonics in the Hellenic Arc using geophysical methods (Pythagoras Project- Greek Ministry of Education);

- Seismotectonics and Geodynamics of the South part of the Hellenic arc  (Pythagoras Project- Greek Ministry of Education).

##### Resources deployed

TEI-CR-GSL is equipped with state-of-the-art hardware and highly sophisticated data analysis software. The hardware comprises integrated complete systems for geophysical prospection with electric, electromagnetic and seismic methods; networked seismological stations; ULF/ELF/VLF-electromagnetic monitoring stations; numerous data processing workstations and a cluster of 16 networked personal computers supervised by a Sun Blade server for solving complex mathematical problems in parallel processing and configured in such a way to be ready to participate in forthcoming “Global Grid”. TEI-CR-GSL makes use of a suite of GIS, GPS, Remote Sensing, and database management system software packages and tools for geospatial data collection, information analysis and modelling, GIS development, implementation, and processing; also there are available in TEI-CR-GSL advanced analysis and 2D and 3D modelling software for electric and electromagnetic data, as well signal processing packages. In order to solve the problems and address the issues related to the proposed project implementation, TEI-CR-GSL will provide its multidisciplinary scientific personnel with expertise in the fields of Geophysics, Seismology, GIS, Remote Sensing, Land-Use and Land–Management, Natural Disasters Management, Physical Geography, Geo-environment and Natural Resources Monitoring, Data Management Systems and Electronic Engineering.

##### Principal Investigator

Dr. Filippos Vallianatos (born on 1963) is Professor of Geophysics & Natural Hazards in the Technological Educational Institute of Crete with expertise in the fields of Physics of the Earth’s Interior, Geo-Seismo-Electromagnetism and Earthquake Prediction Research. He is the author or co-author of more than 70 papers in international journals and conference proceedings, guest Editor in Physics & Chemistry of the Earth and Annali di Geofisica and has served as reviewer in numerous scientific magazines.

A.Tzanis and F.Vallianatos, 2003. “On the nature, scaling and spectral properties of pre-seismic ULF signals”,  Natural Hazards and Earth Systems Sciences, vol. 3.

F.Vallianatos, V.Lapenna, V.Troyan, N.Smirnova, Y Kopytenko, V.Korepanov and T.Matiashvili, 2002. “Study of the ULF electromagnetic phenomena related to earthquakes: Strategy of the SUPRE project”, in Seismo Electromagnetics (Lithosphere-Atmosphere-Ionosphere Coupling) monograph (Ed. M. Hayakawa), published by Terra Scientific Pub, Tokyo.

L.Telesca, V.Cuomo, V.Lapenna and F.Vallianatos, 2000. “Self-similarity properties of seismicity in the Southern Aegean area”, Tectonophysics.

#### Serviço Nacional de Bombeiros e Protecção Civil (SNBPC)

##### Descrizione

The existing Portuguese Service for Fire & Civil Protection – SNBPC - is the result from the merge in 2003 of 3 others services: National Service for Civil Protection, National Service for Fire and Fire-fighters, National Commission for Forest Fires. The mission of SNBPC is:

- To prevent and mitigate the risks associated with severe accidents and disasters and attenuate the effects resulting from this situations

- To coordinate and supervise all the operational activities carried on by the Portuguese fire-fighters

- To assess and give accordance to studies, projects and plans in respect with safety against fire in all kind of facilities and buildings and verify and inspect in loco their observance

- To give direction and coordinated the activities of emergency response at national and district level

##### Resources deployed

4 seniors technicians and respective structure; office, communications and computing equipment.

##### Principal Investigator

Dr. José Norberto Fernandes graduated in 1985 in Geography and Regional Planning, with a specialization in Geographic Information Systems (GIS). All professional activity centred on Information Technologies, being consultant in GIS area on different levels technical, academic and political.

SNBPC, “Civil Protection at Home”, prevention user’s manual.

SNBPC, “Fire prevention for all”, user’s manual.

## A.2 Sub-contracting

CYCLOPS will make use of subcontracting services for specific studies and for dissemination and learning activities. In particular DDSC would liaise with other institutions such as meteorological or flood alert services, scientific laboratories in hydrology or seismology and  volcano observatories as needed in the study activities of the project. DPC will consider subcontracts to a Research and Development entity already conversant with GRID technology working on multidiscliplinary sectors (e.g. hydrology) and also for promoting CYCLOPS dissemination and learning.

## A.3 Third parties

The Consortium does not consider third parties activities.

## A.4 Funding of third country participants

The Consortium does not consider funding of third country participants.

# Appendix B -  Glossary

This glossary reports a brief description of the main concepts related to the present document.

| Term | Acronym | Description |
| --- | --- | --- |
| Global Monitoring for Environment and Security | GMES | The "Global Monitoring for Environment and Security" (GMES) is a joint initiative of European Commission and European Space Agency. It represents in simple terms a concerted effort to bring data and information providers together with users, so they can better understand each other and agree on how to make environmental and security-related information available to the people who need it. A challenge for GMES is to gather relevant data and provide innovative, cost-effective, sustainable and user-friendly services, which will enable decision-makers to better anticipate or integrate crisis situations issues relating to the management of the environment and security. [www.gmes.info] |
| Spatial data Infrastructure | SDI | The term "Spatial Data Infrastructure" (SDI) is often used to denote the relevant base collection of technologies, policies and institutional arrangements that facilitate the availability of and access to spatial data. The SDI provides a basis for spatial data discovery, evaluation, and application for users and providers within all levels of government, the commercial sector, the non-profit sector, academia and by citizens in general.The word infrastructure is used to promote the concept of a reliable, supporting environment, analogous to a road or telecommunications network, that, in this case, facilitates the access to geographically-related information using a minimum set of standard practices, protocols, and specifications. The applications that run "on" such an infrastructure are not specified in detail in this document. But, like roads and wires, an SDI facilitates the conveyance of virtually unlimited packages of geographic information. [GSDI, “Developing Spatial Data Infrastructures: The SDI Cookbook”] |
| INfrastructure for SPatial InfoRmation in Europe | INSPIRE | INSPIRE is a European Commission initiative which intends to trigger the creation of a European spatial information infrastructure that delivers to the users integrated spatial information services. These services should allow the users to identify and access spatial or geographical information from a wide range of sources, from the local level to the global level, in an inter-operable way for a variety of uses. The target users of INSPIRE include policy-makers, planners and managers at European, national and local level and the citizens and their organisations. Possible services are the visualisation of information layers, overlay of information from different sources, spatial and temporal analysis, etc. [inspire.jrc.it] |
| Real Time/Near-Real-Time | RT/NRT | According to IEEE a real-time system is “a system whose correctness includes its response time as well as its functional correctness." This means that the system doesn't just perform its task; it needs to do it in a timely manner. The required response time depends on the application supported by the system. Near-Real-Time refers to looser requirements about the system time response. |
| Grid |  | The term Grid refers to technologies that allow "coordinated resource sharing and problem solving in dynamic, multi-institutional virtual organizations”. In particular, according to a modern view, a Grid is a system that: a) coordinates resources that are not subject to centralized control b) using standard, open, general-purpose protocols and interfaces c) to deliver nontrivial qualities of service. [I. Foster, “What is the Grid? A Three Point Checklist”, GridToday] |
| Service Oriented Architecture | SOA | The term SOA refers to an application architecture within which all functions are defined as independent services with well-defined invokable interfaces which can be called in defined sequences to form complex processes. In a modern view SOA is typically implemented using Web Services Technologies (XML, SOAP, WSDL,etc.) |

Workpackage number: WP 1 – WP n.

Number of the contractor leading the work in this workpackage.

Relative start date for the work in the specific workpackages, month 0 marking the start of the project, and all other start dates being relative to this start date.

Relative end date, month 0 marking the start of the project, and all ends dates being relative to this start date.

Deliverable number: Number for the deliverable(s)/result(s) mentioned in the workpackage: D1 - Dn.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Research relating to cancer treatment of the gonads can be financed