SIXTH FRAMEWORK PROGRAMME

RESEARCH INFRASTRUCTURES

COMMUNICATION NETWORK DEVELOPMENT

Contract for:

SPECIFIC SUPPORT ACTION

Annex I - “Description of Work”

Project acronym: EU-IndiaGrid

Project full title: EU-IndiaGrid: Joining European and Indian Grids for eScience Network Community

Proposal/Contract no.:

Related to other Contract no.: (to be completed by Commission)

Date of preparation of Annex I: 14 June 2006 (Version 2.3)

Start date of contract: (to be completed by Commission)

Versions

| Version | Date | Notes |
| --- | --- | --- |
| 1.3 | 1-6-06 | First Version sent to P.O. |
| 1.4 | 4-6-06 | Section 7: Corrected errors and inconsistencies in WP descriptions , WP List and List of deliverables Corrected for some inconsistencies and completed the other global tables Corrected inconsistencies in the WP descriptions Section 8 Corrected in WP5 effort description some inconsistencies with respect to WP Description in section 7 Inserted totals per WP and per expense typology in the SSA effort tables Appendix: Added P12 (TIFR Mumbai) profile Updated Cambridge University Profile Added chapter on funding of third countries Everywhere Corrected several mistypes and improper formatting |
| 1.41 | 7-6-06 | Section 2 Legal statement on Training and Education inserted in footnote (and taken away footnote in WP6 description) Section 7 Corrected in SOW WP5 for inconsistencies related to the new application on Weather and Earth Scinces, inserted some lines about opening to new applications Section 8 New effort table, with some changes in ICTP effort on WP5 and WP6 a 0.1 PM reduction of INFN in WP6, a redistribution of TIFR effort between WP6 and WP5. The table complies now with budget defined by the EU Commission Appendix Renumbered chapters in the Appendix according to the guidelines |
| 1.5 | 8-6-06 | Section 7 & 8 Modified ICTP effort on WP5-WP6 description Modified WP6 accordind to discussion with PO |
| 1.6 | 8-6-06 | Everywhere: modified some expressions to comply with guidelines Section 7 Modified D5.2 Updated Effort table (PM and budget) budget table was not updated in the previous version, now it contains the correct budget for EU funds, PM effort table: added unfunded for GARR on WP1, changed PM cost for NCBS on NCBS input (change in WP5) Updated WP descriptions according to effort table: WP1 added 2 pm unfunded for GARR WP3: corrected PM effort GARR (was 18 instead of 10) WP4: corrected error in BARC effort, moved some PMs from WP4 to WP5 for TIFR WP5: updated PMs according to effort table for NCBS moved to WP5 some PMS from WP4 for TIFR WP6: taken 0,1 PM funded from INFN Updated List of Workpackage and list of deliverables Appendix Corrected paragraph formatting Inserted key personnel Metaware |
| 1.7 | 9-6-06 | Overall corrections for inconsistencies Changes to combine TIFR Mumbai and NCBS Bangalore as one Participant. This is a decision of the legal office since the legal entity is TIFR. Now partners are eleven TIFR includes two institutes: TIFR-MUMBAI and NCBS Bangalore. In order to better explain the activity of each Institute in the Statement of work and in the Workpackages descriptions the separation between TIFR Mumbai and NCBS Bangalore has been kept. |
| 1.8 | 12-6-06 | Inserted Effort table with the same information as in the CPF |
| 1.9 | 12-6-06 | Overall corrections (Roberto) |
| 2.0 | 13-6-06 | Further corrections (Alberto) |
| 2.1 | 13-6-06 | Further corrections on WP6 following the discussion at 12-06-06 phone meeting with PO (Alvise, Stefano, Silvana, Roberto) |
| 2.2 | 13-606 | Further corrections everywhere (Alberto) |
| 2.3 | 14-6-06 | Version Sent to P.O. |

Table of contents

1	Project summary	8

2	Project objectives and the state of the art	10

2.1	Overview	10

2.2	State of the Art	11

2.3	Objectives	14

3	Participants list	19

4	Relevance to the objectives of Communication Network Development	20

5	Potential impact	22

5.1	Contribution to standards	22

5.2	Contribution to policy developments	22

5.3	Risk assessment and related communication strategy	23

6	Project management and exploitation / dissemination plans	25

6.1	Project management	25

6.1.1	Roles and responsibilities	25

6.1.2	Information flow	27

6.1.3	Project website and mailing lists	27

6.1.4	Meetings	27

6.1.5	Documents	27

6.1.6	Conflict management	28

6.2	Plan for using and disseminating knowledge	28

6.3	Raising public participation and awareness	29

7	Workplan – for the whole duration of the project	30

7.1	Introduction – general description and milestones	30

7.2	Work planning and timetable	30

7.2.1	Work Breakdown Structure (WBS)	30

7.2.2	Statement of Work (SoW) per Workpackage	31

7.3	Graphical presentation of work packages	45

7.3.1	Interdependencies diagram	46

7.4	Workpackage list (full duration of project)	47

7.5	Deliverables list (full duration of the SSA)	48

7.5.1	Milestones and expected results summary table (full duration of project)	50

7.6	WORKPACKAGE DESCRIPTION (FULL DURATION OF PROJECT)	51

7.6.1	Workpackage 1 description	51

7.6.2	Workpackage 2 description	53

7.6.3	Workpackage 3 description	56

7.6.4	Workpackage 4 description	58

7.6.5	Workpackage 5 description	60

7.6.6	Workpackage 6 description	63

Total	68

8	Project resources and budget overview	69

8.1	Efforts for the project	69

8.2	Overall budget for the project	72

8.3	Management level description of resources and budget	74

8.3.1	WP1 - Project administrative and technical management	74

8.3.2	WP2 –Building an eScience Network Community	74

8.3.3	WP3 –Network Planning and Support	74

8.3.4	WP4 – Pilot grid infrastructure	74

8.3.5	WP5 –Applications	75

8.3.6	WP6 – Dissemination and Networking events	75

8.4	Materials and facilities	75

8.5	Travels	77

9	Other issues	78

9.1	Ethical issues	78

9.2	Gender issues	78

9.3	Policy issues	79

a.1 APPENDIX - Participants and the consortium	80

A1.1 Preliminary table of Leaders	80

P01 - Coordinator -  Istituto Nazionale di Fisica Nucleare (Italy) - INFN	80

Profile	80

Role in the project	81

Key Personnel	81

P02 - Partner -  Metaware SpA (Italy) - MTW	82

Role IN the Project	83

Key Personnel	83

P03 – Consortium GARR (Italy) - GARR	84

Profile	84

Role in the project	84

Key Personnel	85

P04 – The Abdus Salam International Centre for Theoretical  Physics (ICTP)	85

Profile	85

Role in the project	86

Key Personnel	86

P05 - Cambridge University	87

The Cambridge eScience Centre	87

Role in the Project	88

Key Personnel	88

Profile	90

Role in the project	90

Key Personnel	90

P06 – Tata Institute of Fundamental Research (TIFR)	91

Tata Institute of Fundamental Research (TIFR) Mumbai, India	91

Profile	91

Role in the project	91

Key Personnel	92

National Centre for Biological Sciences, Bangalore, India (NCBS)	93

Profile	93

Role in the project.	93

Key Personnel	93

P07 – ERNET India	94

Profile	94

Key Personnel	95

P08 - Department of Physics, University of Pune	96

Profile	96

Role in the project	96

Key personnel	97

P09- SAHA Institute Calcutta	97

Profile	97

Role in the project	97

Key Personnel	97

P10-  Centre for Development of Advanced Computing Bangalore	97

Profile	97

Role in the project	98

Key Personnel	98

P11 Bhabha Atomic Research Centre (BARC), Mumbai, India	101

Profile	101

Role in the project	102

Key Personnel	102

A.2  Sub-contracting	104

A.3 Third parties	104

A.4 Funding of third country participants	104

A.5 Events Planner	105

# Project summary

EU-IndiaGrid aims to make available a common, interoperable Grid infrastructure to the European and Indian Scientific Community, in order to support existing EU-Indian collaborations in eScience and promoting new ones. In line with the support  goals of the Research Infrastructures activity area of the European Union Sixth Framework Program, EU-IndiaGrid will hence enable the interconnection between the most relevant European Grid infrastructure, EGEE, and the Indian Grid. The partners of this project are prominent actors on the European and Indian e-Infrastructures scene: Italian National Institute for Nuclear Physics (INFN, project coordinator), Metaware SpA, Consortium GARR - the Italian Academic and Research Network (GARR), the Abdus Salam International Centre for Theoretical Physics (ICTP), the Cambridge University, the Indian Tata Institute for Fundamental Research (“TIFR”, with an Institute in Mumbai and the National Centre for Biological Sciences, “NCBS”, in Bangalore), the Indian Education and Research Network (ERNET), the University of Pune, the SAHA Institute Calcutta, the Centre for Development of Advanced  Computing (C-DAC), the Bhabha Atomic Research Centre.

The major objectives of EU-IndiaGrid can be summarized as follows:

- To offer an effective answer to the demanding computing needs of several common EU-India research projects, supporting the interconnection and interoperability of  EGEE with the Indian Grid infrastructure for the benefit of eScience applications;

- To identify and aggregate actual and potential user communities for the newly implemented common infrastructure and promote its use through a specific outreach and dissemination programme;

- To develop synergies between scientific research and industrial communities, in order to foster the deployment of grid techniques in research and industrial applications within the Indian subcontinent.

# Project objectives and the state of the art

## Overview

EU-IndiaGrid main goal is to support interconnection between the most relevant European Grid infrastructure (EGEE) and its thematic and regional extensions and Indian Grid to make a common infrastructure available to support data processing for eScience application areas where strong collaborations already exist between Europe and India.

Such common Grid infrastructure is intended to provide a concrete answer to specific requirements of several existing EU-India collaborative projects, characterized by very demanding computing needs; in the meanwhile, it is expected to trigger the use and development of Grids in India across a number of application areas, and foster the creation of new Euro-Indian collaborations in eScience.

Existing and potential user communities in eScience and Industry will be identified, contacted and involved in the project, through a specific outreach and dissemination programme, ultimately aiming to create a EU-IndiaGrid community bringing together over 300 organisations from Research, Industry and Science.

Pilot applications in Biology, High Energy and Condensed Matter Physics, and Earth and Atmospheric Sciences will be deployed on the newly implemented infrastructure in order to validate it and will furthermore be a first set of case histories which can be used in the dissemination of the Project.

The principal objectives of EU-IndiaGrid are:

- To support the interconnection and interoperability of the prominent European Grid infrastructure (EGEE) with the Indian Grid infrastructure for the benefit of eScience applications;

- To identify and aggregate research, scientific and industrial communities which may benefit from the use of Grid technology resulting in an eScience Network Community published on the EU-IndiaGrid portal;

- To promote the use of advanced Grid technologies within the created Network Community relying on pilot applications in Biology, High Energy and Condensed Matter Physics and Earth and Atmospheric Sciences, and specific outreach and dissemination activities;

- To disseminate European EGEE-II Grid technology achievements in India and leverage on Indian Grid experiences and skills;

- To deliver three workshops, a project conference and four training events in strategic areas in India and Europe with major potential user communities (each workshop will have 100-150 participants).

The results of the project will be:

- To develop synergies between scientific research and industrial communities with ongoing Grid technology developments with the creation of an eScience Network Community;

- To increase international co-operation through the validation of the pilot intercontinental infrastructure which will act as a driving force at disseminating the results of the successful EGEE grid infrastructure in India endorsing the introduction of new user communities;

- To offer an effective answer to the demanding computing needs of several common EU-India research projects and, at the same time, foster the deployment of grid techniques in research and industrial applications within the Indian subcontinent;

- To bring together over 500 organisations from research, industry and science communities to exchange experiences during the workshop and training events for an appropriate dissemination and outreach activity.

## State of the Art

There is a substantial number of initiatives in Europe involved in deploying and operating the European-wide e-Infrastructure with the GEANT2 and EGEE-II Projects leading the way. These initiatives cooperate with national programs at European and extra-European level. Interchanges and agreements, based on existing or new collaborations between Europe and other countries support a progressive extension of the present e-Infrastructures.

Implementing a Grid-enabled infrastructure would be of strategic relevance to foster collaboration between researchers from Europe and India in a wide range of scientific areas.

The main initiatives, in Europe and India, relevant for the  EU-IndiaGrid project activity are listed below.

GÉANT and GÉANT2 (http://www.geant.net/)

DANTE and the European NRENs first deployed the initial GÉANT network in 2001. Today it forms the world’s largest research and education network with over 3,500 academic and research centres in 33 Countries being connected with an overall capacity across the network in excess of 120 Gbps. GÉANT is the 6th generation of European research network and has been funded in part by the EC’s Fifth Framework Programme since November 2000 with 28 European NRENs as participants and DANTE as the coordinating Partner. EC funding support through the 5th EC Framework Programme continued up to November 2004. GÉANT2, the successor to GÉANT, was officially launched on 15 June 2005

EGEE and EGEE-II (http://public.eu-egee.org, http://www.eu-egee.org)

The vision of the EGEE (Enabling Grids for E-sciencE) Integrated Infrastructure Initiative (I3) is to create and deploy Grid technologies to enable the widespread uptake of eScience applications throughout the European Research Area. EGEE, a two years project started in April 2004, gathers 70 institutions in 27 countries, federated in regional Grids. EGEE is now in full production mode, and with over 200 sites with a total of more than 20000 CPUs and 5PB of storage is currently one of the largest international Grid infrastructures ever assembled. EGEE aims to cover a wide variety of applications sectors, starting from High Energy Physics and BioMed and expanding to Earth Sciences and other application sectors.

EGEE applications and middleware (http://egee-na4.ct.infn.it, http://www.glite.org)

The latest version of gLite,  the EGEE middleware, is deployed on a large amount of sites in Europe. These sites are grouped in several national or regional grids federated in a European wide infrastructure largely used from several user communities.

The applications ported on the EGEE infrastructure by these communities cover different scientific fields, such as:

- Physics with the High Energy Physics (HEP) experiments at LHC;

- Biomedicine with applications like GATE, CDSS, and WISDOM;

- Earth Science with applications like SPECFEM3D;

- Astrophysics, with applications like MAGIC and PLANCK;.

- Computational Chemistry, with applications like GEMS .

GILDA (https://gilda.ct.infn.it)

The INFN GILDA virtual laboratory for grid knowledge dissemination has originally been developed and successfully used in the context of the EGEE Project and will be exploited as well within the EU-IndiaGrid framework.

GILDA is a complete and fully functional grid infrastructure, providing a number of tools which can be regarded as key enabler of dissemination and application support activities, including:

- A testbed consisting, as of today, of 20 sites located in 3 continents;

- A dummy Certification Authority;

- A dummy Virtual Organization;

- A complete set of user documentation;

- A complete set of grid portals (the GILDA Grid Tutor and the GILDA Grid Demonstrator);

- A full set of demonstrative applications that can be used to impress and stimulate attendees to dissemination events.

GARUDA (http://www.garudaindia.in)

The National Grid Computing Initiative, GARUDA is a collaboration of science researchers and experimenters from 45 Institutes on a nation wide grid of computational nodes, mass storage and scientific instruments. It provides the  network connection  and the computing resources to several pilot grid applications.

State of the Art of Grid middleware and applications in India

GARUDA, the Indian grid computing initiative started by the Centre for Development of Advanced Computing (C-DAC) in 2005.  The project aims at strengthening and advancing scientific and technological excellence in grid and peer to peer technologies by creating a nation wide test bed for the research and engineering of technologies, architectures, standards and applications in grid computing.  GARUDA also brings together all potential research, development and user groups who can contribute to the development of this national initiative.

At this stage, the Proof of Concept (PoC) phase of the project made considerable progress and in the final stage of deploying the high speed communication fabric that will connect 45 research laboratories and educational institutes spanning across 17 major Indian cities.  The multi-service network with total backbone throughput of 2.43 Gbps is expected to support not only the data traffic requirements of high performance computing applications but also other requirements such as IP based collaborative environments enabled through video conferencing tools such as Access Grid.

Besides the communication fabric, the other major components of GARUDA include computing resources, grid middleware tools to support program development, collaborating environment, data management, grid monitoring and management, access portals and specialized problem solving environments which are under different stages of development.

Many applications of national importance will be deployed on the GARUDA grid.  At this stage the major focus is given to applications on national disaster management and bioinformatics.

In national disaster management application, C-DAC, in association with a partner research institution, will mine data from a network of sensors deployed over vast disaster prone regions and upload it to GARUDA as critical input to forecast models appropriate to various stages of disaster management.  This will enable timely dissemination of key information to user agencies for effective mitigation and relief measures.

The Bioinformatics Resource and Application Facility (BRAF), already running on C-DAC’s PARAM Supercomputing Facility, is accessible to the bio-informatics research community involved in “in silico” molecule identification and new drug discovery.  These applications require tremendous computational cycles and huge amount of storage.  Efforts are underway to grid enable these applications in order to make use of grid resources beyond those available at any single location.

GARUDA is managed by C-DAC with the Grid monitoring centre located in Bangalore. C-DAC Bangalore is a EU-IndiaGrid project partner. All the project partners in India are involved in the GARUDA project and have a considerable grid middleware know-how. Most of them are official members of the GARUDA collaboration.

In addition some typical EGEE pilot applications are available such as those of the High Energy Physics experiments at LHC. Each experiment at LHC (Large Hadron Collider), which is currently under development at CERN, and will start operations in 2007, will collect data in the order of several hundreds of MBytes per second. Such data will be widely available to all the collaborators in Europe and worldwide, provided that a good connectivity and a compatible grid infrastructure is available. Groups of Indian scientists (within the ALICE and CMS communities) already actively participate in these experiments.

Recently, one of the project partners, the Bhabha Atomic Research Centre, has initiated the “DAE Grid” project. BARC works under Department of Atomic Energy (DAE), Government of India. To start with various R&D centers of DAE such as BARC-Mumbai, VECC-Kolkata, CAT-Indore and IGCAR-Kappakam have been interconnected (2/4 Mbps) via dedicated links and four major applications such as Grid-Portal for sharing High-end computers, Collaborative Tools for interactive working, remote backup and Portal for Information Sharing are being developed. In the next phase all 33 DAE locations will be brought under DAE-Grid. The “DAE Grid” project will eventually connect more than 33 locations across the country (including other project partners as SAHA Kolkata and TIFR Mumbai ) with an aim to bring grid networked computing to research labs and industry. DAE Grid aims at strengthening and advancing scientific and technological excellence in the area of Grid technologies. To achieve its objective, DAE-Grid brings together a critical mass of well established researchers from 33 laboratories and academic institutions that have planned an ambitious program of activities.  BARC has also signed an MOU with INFN in February 2006 to establish a Grid Research Hub in Mumbai and carry out advanced research in Grid Computing middleware development and deployment of scientific applications using Grid Computing in collaboration with INFN.

Other applications in development in the Indian area could gain a significant improvement from a grid infrastructure. These new applications and potential users could be identified by WP2 with its survey.

## Objectives

The EU-IndiaGrid initiative is proposed as a Specific Support Action (SSA) in the area of “Communication Network Development – e-Infrastructure – Grid Initiatives” of the FP6 Programme. EU-IndiaGrid aims to foster the integration and interoperability of the Grid infrastructures in Europe and India for the benefit of eScience applications and worldwide Grid initiatives, in line with the support of the intercontinental extension of the European Research Area (ERA). Coupled with this, EU-IndiaGrid will promote the use of advanced grid technologies by new potential research and industrial users.

This objective will be achieved first identifying and aggregating the potential users within an eScience Network Community and, in turn, promoting the use of advanced grid technologies relying on pilot applications in Biology , High Energy and Condensed Matter Physics, and Earth and Atmospheric Physics and specific outreach and dissemination activities.

EU-IndiaGrid is proposed by a consortium of eleven partners which complement each other on the proposed objectives: Istituto Nazionale di Fisica Nucleare (“INFN”, Italy), Metaware SpA (“MTW”, Italy), GARR (“GARR”, Italy), International Centre for Theoretical Physics, (“ICTP” International Org.), Cambridge University (“CAM”, UK), Tata Institute for Fundamental Research, India, (“TIFR”, with an Institute in Mumbai and the National Centre for Biological Sciences, “NCBS”, in Bangalore), ERNET (“ERNET“, India), Pune University, (“Pune”, India), SAHA Institute Calcutta, (“SAHA”, India), Centre for Development of Advanced Computing (CDAC, India), Bhabha Atomic Research Centre, Mumbai (“BARC” India).

INFN, ICTP, CAM, TIFR, Pune, SAHA, CDAC,BARC, bring their significant involvement on Grid applications and technologies specifically in the chosen domain areas, Metaware brings its industrial networking involvement of community building and delivery of specific events whilst GARR and ERNET  provide the pilot Grid infrastructure network support.

The objectives of the project can be grouped into two main areas:

- a significant contribution to the creation of an eScience community, by means of suitable dissemination and outreach activity and the porting of existing and new applications on the intercontinental Grid;

- the support of an interoperable grid infrastructure that will enable the Grid operations between Europe and India.

The general objectives outlined above break down into the following ones:

- To support the interconnection and interoperability of the prominent European Grid infrastructure (EGEE) with the Indian Grid infrastructure for the benefit of eScience applications.

EU-IndiaGrid will leverage on the existing infrastructure provided by the research networks such as: the Gigabit Pan-European Research & Education Network (GEANT) and the Indian Education Research Network (ERNET) to exploit the initiatives of high speed intercontinental network connections, and work in synergy with them for the optimisation of network usage in agreement with the objectives of the Communication Network Development scheme. This objective will be mainly addressed within WP3 (in synergy with T2.3, Relationships with other projects) and will be reported in deliverables D3.1, D3.2, and D3.3.

In addition, it will propose to interconnect the major European Grid-based infrastructure, namely EGEE, with the corresponding ones in India, contributing to the creation of a “virtual Grid-based research space”. This objective will be the main WP4 task and will be reported in deliverables D4.3.

The output will be the provision of effective solutions to the demanding computing needs of several common EU-India research projects and at the same time foster the deployment of grid techniques in research and industrial applications within the Indian subcontinent.

- To identify and aggregate research, scientific and industrial communities which may benefit from the use of Grid technology resulting in an eScience Network Community published on the EU-IndiaGrid portal.

Project dissemination and outreach activity will contribute to spread the awareness of Grid developments among new research and industrial communities, improving the effectiveness of the Grid infrastructure for new applications and promoting scientific and industrial development. The objective will identify and aggregate Grid Infrastructures, Research & Industry Communities and SMEs not already included in Research Infrastructure initiatives. This will be represented as a principal task in WP2 and will be reported in deliverables D2.1 and D2.2.

EU-IndiaGrid will involve, as early users, the communities already engaged in Grid Applications (such as Biology and High Energy Physics) stimulating a larger participation and the introduction of new communities and applications. This objective will be the principal WP5 task and will be reported in deliverables D5.1, D5.2, D5.3, D5.4, and D5.5.

The output will be a qualified creation of an eScience Network Community interested in pursuing grid deployments and in trans-national co-operation to meet their organisational goals. The interaction of these individuals will be facilitated via the EU-IndiaGrid community portal.

- To promote the use of advanced Grid technologies within the created Network Community relaying on pilot applications in Biology, High Energy and Condensed Matter Physics, and Earth and Atmospheric Sciences,  and specific outreach and dissemination activities.

Several research activities already set up between Europe and India have strong requirements of analysis of large quantities of data and huge amounts of computing power. EU-IndiaGrid looks to foster interoperability of solutions across different disciplines to achieve broader scale uptake of Grid technology across user communities, involving, amongst others, those applications which are able to produce and process large quantities of scientific relevant data. This objective will be the main WP5 task and will be reported in deliverables D5.1, D5.2, D5.3, D5.4, and D5.5.

The identified pilot applications will act as forerunners providing  direct and indirect support in establishing a pilot intercontinental Grid infrastructure, supporting existing “Grid aware” applications and, at same time, fostering new applications.

The objective integrates the existing Grid infrastructures in Europe and India to reach new levels of scientific collaboration and promoting the eScience applications in India. This objective will be part of WP1, WP4 and WP6 tasks and will be reported in deliverables D1.1, D1.2, D1.3, D4.3, D6.1, D6.2, and D6.3.

Moreover, EU-IndiaGrid will harmonise European and Indian eScience user requirements in terms of resources needed, Grid services, and application software adapting the present best practices and tools (Virtual Organisations, Certification Authorities, Security, Policies, etc.) This objective will be addressed within WP1 and WP4  tasks and will be reported in the deliverables D1.2, D1.3, and D4.3.

The output will be increased international collaborations through the validation of the pilot intercontinental infrastructure which will act as a driving force at disseminating the results of the successful EGEE grid infrastructure in India endorsing the introduction of new user communities.

- To disseminate European EGEE Grid technology achievements in India and leverage on Indian Grid experiences and skills.

EU-IndiaGrid will take advantage of the already available middleware developed by other Grid Projects such as EGEE and make use of established common practices in the deployment of such large infrastructures. Moreover, the integration into the wider European and Indian infrastructures will provide the research and education community of the two regions with transparent access to a huge world-wide amount of storage and computing resources than currently available in separate environments. This will allow for a new scale of powerful applications and availability of a larger number of scientific databases to an enormous potential number of researchers.

EU-IndiaGrid will disseminate the results of successful European Grid infrastructures, like EGEE, in India creating awareness regarding Grid developments. This objective will represent the main WP6 task and will be reported in deliverables D6.1, D6.2, and D6.3.

The output will be the creation of an extensive network of individuals with increased awareness of European grid infrastructures, coupled with knowledge on Indian expertise and know-how to reinforce real collaborations in the future under RTD projects or commercially oriented initiatives.

- To deliver three workshops, a project conference and four training events in strategic areas in India and Europe with major potential user communities (each workshop will have 100-150 participants).

Perform dissemination and outreach activities among  communities which are not yet aware of the benefits of a Grid Infrastructure through networking and training events & workshops, promotional material, technical cookbooks and hands-on demonstrations. This objective will represent the main WP2 and WP6 tasks and will be reported in deliverables D2.1, D6.1, D6.2, and D6.3.

The initiative will significantly contribute to the creation of a human network in the area of Grids, eScience and e-Infrastructures between Europe and India, promoting the existing and creating new international collaborations.  This objective will be part of WP1, WP2, and WP6 tasks and will be reported in the deliverables D1.1, D1.2, D1.3,  D2.1, D2.2, D6.1, and D6.2, D6.3.

The results of the project will be fed back to the relevant groups developing Grid middleware, such as: Globus, EGEE-JRA1, etc.. This objective will be addressed within WP1 task and will be reported on the deliverables D1.1, D1.2, and D1.3.

The output will be to bring together over 300 organisations from research, industry and science communities. In order to exchange experiences during workshops and training events, case studies, lessons learnt, and potential benefits will be featured.

# Participants list

List of Participants

| Partic. Role* | Partic. No. | Participant name | Participant short name | Country | Date enter project ** | Date exit project ** |
| --- | --- | --- | --- | --- | --- | --- |
| CO | 1 | Istituto Nazionale di Fisica Nucleare | INFN | Italy | M1 | M24 |
| CR | 2 | Metaware | MTW | Italy | M1 | M24 |
| CR | 3 | GARR | GARR | Italy | M1 | M24 |
| CR | 4 | International Centre for Theoretical Physics | ICTP | Italy | M1 | M24 |
| CR | 5 | Cambridge University | CAM | UK | M1 | M24 |
| CR | 6 | TATA Institute for Fundamental Research | TIFR | India | M1 | M24 |
| CR | 7 | ERNET India | ERNET | India | M1 | M24 |
| CR | 8 | Pune University, India | PUNE | India | M1 | M24 |
| CR | 9 | SAHA Institute Calcutta, India | SAHA | India | M1 | M24 |
| CR | 10 | Centre for Development of Advanced Computing | CDAC | India | M1 | M24 |
| CR | 11 | Bhabha Atomic Research Centre | BARC | India | M1 | M24 |

# Relevance to the objectives of Communication Network Development

EU-IndiaGrid addresses the objectives of the Communication Network Development call for Research Infrastructures 2004-2006 Work Program and aims to support a pilot grid infrastructure between EU and India.

As it is well known, the impact of Grids in the fields of Research and Industry is expected to be dramatic in the next few years and to enable the development of such infrastructure for eScience is one of the focal points of the Communication Network development programme. EU has already spent a considerable effort to set up not only an experimental Grid infrastructure, but a production level one; the first user communities arose and the level of awareness and competence increased as well. Within the EU, important steps have been taken in such direction since the first pioneering projects such as DATAGRID. Currently, the EGEE/EGEE-II project represent the major undertaking in this field and it is surrounded and integrated  by a number of thematic, national and regional initiatives, such as the INFN-Grid, HELLASGRID and SEE-GRID2 projects. From these experiences, EU has achieved a considerable level of expertise that brings it to a leading role in Grid implementation and usage and makes possible new ways of Research, giving a first impulse to the development of a real set of eScience facilities in Europe and beyond.

The EU-IndiaGrid initiative is intended to build upon and exploit such expertise working in synergy with the existing e-Infrastructures.

The project will capitalize the experience gained by EGEE and other Grid projects and represents a valid opportunity to “promote a further breadth and depth to the collaboration amongst researchers in Europe and beyond”.

The partners experience and involvement in the main national and European Grid initiatives will allow the project to “enhance, complement and exploit synergies with the relevant national and international initiatives”.

Therefore, the EU-IndiaGrid project sets itself in the perspective of a virtuous interaction, “Cross-fertilisation and optimisation of synergies between GÉANT, Grids, test-beds and Research Infrastructures in general” which is considered as a crucial factor for the success of the Communication Network Development scheme, especially in the field of Grids.

The EU-IndiaGrid initiative will in a first phase support a pilot infrastructure to be tested by a set of applications, which have been carefully selected among the number of research activities and experiments currently carried on in collaboration between Indian and European scientists. Some of those experiments are already grid-enabled, but they are not interconnected, so the EU-IndiaGrid initiative will work towards the creation of an integrated “virtual Grid-based research space” across Europe and India. In the meanwhile, the pilot applications will begin immediately to profit for the new infrastructure and will hopefully act as a catalyst of the involvement of new applications and user communities, contributing to “enhance the “inclusiveness”” of the research network infrastructure.

More specifically the project can contribute to the following objectives, in the Grid Initiatives area of the Communication Network Development Scheme:

- Promote complementary work vis-à-vis national Grid-Programmes in Europe in view to add value to National Grid Initiatives and support the creation of a network of Grid Support Centres in Europe.

- Interconnect major Grid-based experimental infrastructures in Europe with the corresponding ones in the world, e.g. US, Asia-Pacific region and others. Contribute that way to the creation of a “virtual Grid-based research space” across world regions.

The participation of national and international research centres and the relationships with the major European  Grid and network projects allows the EU-IndiaGrid initiative to  address also the specific requirements for grid infrastructures within the Communication Network Development Scheme:

New initiatives should link and build upon existing ones in the same area. The strategic ambition of deploying a fabric of Grid-based e-Infrastructures in Europe calls for the involvement, amongst others, of stakeholders able to produce or process large quantities of scientific relevant data (such as national Research Centres or International Organisations in the different research fields).

Relevance to the Specific Support Action Instrument

EU-IndiaGrid is using the Specific Support Action Instrument, since it aims to “complementing the implementation of the FP” within European Grid initiatives. Such Instrument is especially appropriated as regards to the aims of fostering and promoting “dissemination, transfer, exploitation, assessment and/or broad take-up of past and present programme results”, such as the EGEE achievements and as well as “prepare future community RTD activities”.

Such objectives will be exploited within WP3, 4 and 5 as regards to the set-up and operation of the pilot infrastructure and the interworking of experts groups. WP5, in synergy with the activity of WP2 and the dissemination activities proposed in WP6, will also promote the development of new research and innovation strategies through fostering the growth of new regional applications.  Finally, WP6 will deal with the organization of workshops and events so as to disseminate and transfer the project achievements.

# Potential impact

## Contribution to standards

The EU-IndiaGrid consortium will engage relations with the EU policy maker bodies such as eIRG, ESFRI, and NNG groups (see below) and will harmonise its activities in collaboration with the European Commission’s deliveries of white papers relevant to the goals of EU-IndiaGrid. Coupled with this, from an Indian perspective, having on board the principal players working on Grid expertise will allow the consortium to stay abreast of developments going on in India. The consortium members will communicate with ESFRI and eIRG members to synergise on the developments made and to allow the policy makers to contribute actively to the dissemination and networking activities planned. Regarding the contribution to standard activities, the project will pursue collaboration with Pan-European efforts namely EGEE-II to ensure the interoperability of the infrastructure and services, to ensure in turn that user communities are able to seamlessly access resources both within and outside those provided through EGEE-II and related Grids. The specifications will be closely linked so as to achieve the similar policy formats, service definitions, architecture, tools etc. Moreover, WSRF and other Globus/GGF standards will be closely observed and fed back into. The relationship with EGEE-II will be of particular value in this context where EGEE-II will act as a strong link with international Grid efforts, including the Global Grid Forum (GGF). From the networking perspective, IPv6 efforts (especially those conducted by the EUChinaGRID Project) will be closely monitored so as to achieve full compatibility of deployed middleware with IPv6 services. Again, active participation in quick requirements capture and fast feedback to the EGEE-II and OMII-Europe middleware developers will indirectly contribute to international standards.

## Contribution to policy developments

The specific activities carried out by EU-IndiaGrid, specifically within the High Energy & Condensed Matter Physics, Biology and Earth and Atmospheric Science domains will both reinforce the user communities’ engagement as well as stimulate Grid policies in these areas. EU-IndiaGrid will be able to showcase related research results in complementary European activities.

A number of the participating partners are active in related projects which will play a big role in the project whilst, at the same time, the project will analyse ways of opening dialogue with new initiatives.

The current deliverables of the project such as: the EU-IndiaGrid state of the art in Security & Certification Authority Report (D4.1), the interoperability report (D4.3), network provisioning and assessment of infrastructure operations (D3.3), sustainable actions report (D2.2) and the proposed network connectivity roadmap (D3.2) will provide valuable insight for the European Commission, national Ministries and Regional & National Authorities in charge of Structural funds to analyse how support may be best implemented at a National & at an European level and ultimately at an intercontinental level. The results of the reports will allow regional governments to understand what funding initiatives may take place in the future to help support the science & industry communities.

Next Generation Grid (NGG)

The consortium members will understand the progress made and see how the project may leverage off the development within the Next Generation Grid (NGG) expert group, set up in 2004 by the European Commission, to develop a European vision for Grid research. The expert group is comprised of leading figures from the Grid research academic community and from industry.

## Risk assessment and related communication strategy

No potential risks for society/citizens associated with the project were identified. The following is a specific risk assessment as related to the project itself. The consortium foresees the following risks during its implementation and contingency measures in case these risks actually take place.

High bandwidth network connectivity not available between Europe and India

One of the major risks of this project is related to the availability of high bandwidth network connectivity between Europe and India: as a matter of fact, the project is based on the assumption that sufficient bandwidth will be delivered thanks to existing intercontinental connectivity initiatives. Although, in principle, some Grid activities would be indeed possible without high bandwidth direct links, the actual situation would not guarantee high performances, especially where large amounts of data are involved.

In order to mitigate this risk, a special attention will be devoted to Euro-Asian current and foreseen connectivity projects and initiatives within the framework of T2.3 (Synergies with related Projects & initiatives). This task is especially conceived to liase with pertinent connectivity initiatives and organize joint meetings to coordinate efforts and ensure that the EU-IndiaGrid user’s requirements are taken into account during the network planning. Governments and appropriate organizations will be addressed with ad-hoc communication and lobbying activities aimed at awakening them to the importance and benefits of such network and grid infrastructures to sustain strategic collaboration between Europe and India.

Financial problems for participants attending the International workshops and Training events

Attendance to all the focused events organised should be, in principle, free of charge. All the materials, consumables and logistic costs have already been foreseen in the budget estimation, indicated within the external costs of the project. However in the event that workshops are run at a loss, the consortium may consider charging a small fee to participants to avoid a budgetary shortfall.

The consortium has ensured an intense, results-oriented networking workshop agenda comprising a two-half day event to save on organisation’s absence from the office for no more than one full day.

Financial problems for the consortium members to host  the EU-IndiaGrid workshops & training events

The consortium partners and members have appropriate premises and would be willing to host the networking workshops, so savings will be made here. If a suitable premise were not available within the partners’ countries a small budget has been set aside for hire charges in the event that a suitable premise is not found. Budget has been set aside to cater for the logistics to each of the events organised and for any printed material delivered. In the event that workshops are run at a loss, the consortium may consider charging a small fee to participants to avoid a budgetary shortfall.

Lack of motivation for participation in making up part of the User Communities

The EU-IndiaGrid consortium will target key decision makers and players and will work upon the support derived from projects such as: EGEE-II, SEE-GRID2, DANTE, GEANT2, TEIN2, BELIEF, MONSOON, etc. Letters of Support have been collected, to make up a vibrant and active user community very early on in the project and by utilising success stories of e-Infrastructure deployments will ensure greater attendance also to the events. In addition, the consortium members have access to databases with a significant number of RTD and industrial contacts who have expressed interest or participate already in EU RTD e-Infrastructure co-operation.

Cultural Differences

EU-IndiaGrid will tackle cultural and linguistic barriers, going beyond technical aspects. The consortium members have worked closely with Indians in the past, so they fully appreciate cultural differences particularly well. Moreover, English is a widely-spoken language in India which will reduce linguistic problems.

Lack of participants to the focused events

To entice an appropriate number of participants to attend the international workshops & training events, the consortium will introduce enticers on the EU-IndiaGrid portal providing certain market studies, pertinent documents in advance to registered members only. Post event, conference documentation will be available to registered community members in the secure area of the portal. In addition, the consortium has set-aside a subsidised amount of funding to invite pertinent guest speakers to cover a part of their travel expenditures to the four different focused events.

Lack of developing country organisations in future IST calls

The consortium has structured the organisation of two international workshops and a project conference in India and one in Europe due to the support offered from the Indian partners with the goal of establishing trans-European Research consortia and encouraging R&D Project participation to future IST projects. There is a risk that there are not enough future project ideas exchanged on the portal and at the focused networking gatherings. In this case, the consortium will strengthen its promotional and dissemination activities and increase the success story case study visibility. The consortium will also contact existing e-Infrastructure NoEs and IPs, funded under FP6, to assess how many wish to initiate a competitive call with the emerging economies to promote further international co-operation.

# Project management and exploitation / dissemination plans

## Project management

INFN, the co-coordinating partner will manage the project. Apart from its core activity in the field of High Energy and Particle Physics, INFN has been involved for years in large networking activities, both at the national and international level. In Italy, INFN managed the National Research and Education Network for over ten years, while at the European level it was involved in a number of large projects, such as TEN34, TEN155 and GEANT. In reference to Grids, INFN is one of main promoting partners of DataGRID – the first EU-approved project in the Grid area – and is currently taking part in EGEE, outstanding infrastructure project of the current FP; on the national side, INFN is the coordinator of Grid.it, the Italian grid infrastructure for research, which is one of the major projects financed by the Italian Ministry of Education, University and Research.

(1) PM

(WP1 Manager)

(5) TM

WP3

Manager

WP4

Manager

(6)  PTB

WP2

Manager

Task 1

Manager

Task 2

Manager

Task n

Manager

WP5

Manager

(2) DPM

(3) PO

(4) PMB

Related

Projects

EU

Commission

WP6

Manager

Figure 1 – Project Management Structure

The project management structure of EU-IndiaGrid is conceived to create an international collaborative environment dealing with traditional project management problems and, in the meanwhile, taking into account some critical issues, which are distinctive of the present document (i.e., the remarkable distance between the European and Indian actors, which implies mobility issues, timing, and cost constraints). The management structure is schematically shown in the above figure.

### Roles and responsibilities

- (1) A Project financial and administrative Manager (PM), appointed by the Coordinating Organization and reporting to the Project Management Board (PMB see next point 4), will undertake the direction and administrative management of the project, implementing decisions of PMB and taking decisions between board meetings. He/she will also be responsible for communication between the Project and the EU and for coordination with other Grid initiatives.

(2) A Deputy Project Manager (DPM), nominated by the Indian partners, will closely collaborate with the PM, acting in his/her stead on a regional basis. The DPM will also be the first point of reference within the project management for all Indian Partners. He is a member of the project Management Board

(3) A Project Office (PO), will work in close coordination with the PM and the DPM, providing support to the operational management and the logistics of the project.

To minimize travel expenses and travel time, also taking into account the relevant geographical distances among partners, the larger part of the communication among participants will be via electronic mail. Therefore the availability of easily accessible and up-to-date information on all relevant issues and activities and a constant monitoring of the effectiveness of the communication will be critical aspects for the success of the initiative. These will be duties of the PO, as well as the organization of the annual EU external reviews.

(4) A Project Management Board (PMB), composed of one management representative from each partner and the PM, will specifically deal with items that affect the contractual terms of the project and strategic decisions. The PMB is formally entitled for the decision making related to the budget, the strategic objectives, possible changes and amendments, exploitation agreements. It will as well be responsible for taking remedial action in the event of missed milestones, taking in consideration advices from the technical board.

The PMB will also be responsible for conflict resolution in accordance with the contract and all the specific provisions envisaged within the Consortium Agreement(see section 5.1.3),

The Chair of the PMB will be elected and appointed each year, while the PM (who will be an ex-officio member with voting rights) will act as secretary. Only partners will have right of vote within the PMB, while possible Third Parties will be however provided with the full documentation.

The project management board will normally communicate via email and eventually via phone/video-conference. It is expected that no more than two or three meetings per year will be needed; exceptional meetings could however be called by the PM on request by more than one of the partners for serious motivations.

(5) A Technical Manager (TM), proposed by the PM and nominated by the PMB, will be responsible for decision making related to technical issues. He/she will chair the Project Technical Board (see point 6) and work in close collaboration with it, and will be responsible for reporting to the PM. A deputy Technical Manager, to be appointed during the first PMB meeting, will help the TM in all his/her activities; the DTM should be a representative of the Indian parties, to facilitate coordination among the European and Indian sides of the project and to provide to the all Indian Partners a first point of reference regarding technical issues.

(6) A Project Technical Board (PTB), constituted of the WP Managers (see point 7), chaired by the TM, and reporting to the PMB, will take decisions on technical issues and will be responsible for the production of deliverables.

Under the direction of the PM, the technical board will be responsible for the overall technical management of the project, i.e. the implementation strategy, the choice of techniques, the monitoring of results and quality. When necessary, the PTB will consult experts for advice and will propose corrective actions (to the management board) in the event that partners fail to meet their commitments or in case of missed milestones and/or deliverables.

(7) A leader for each workpackage (WP manager), appointed by the partner responsible for the WP, will coordinate the work of the tasks of the workpackage itself and will be responsible for the related milestones and deliverables.

The work package managers, in coordination with the project administration, will be responsible for generating quarterly progress reports, which will report the progress made in each task and the consumption of resources. These reports will be submitted to the EC Commission. Whenever possible, in order to maximize the efficiency in the project management and to reduce travel costs, the WP manager will coincide with one of the members of the PMB (according to the needs of the activity and the profile of the person in charge)

(8) A leader for each task (Task manager), designated by the partner who leads that activity in agreement with the WP manager concerned and the Technical Manager, will coordinate the work within the specific tasks assigned to him/her.

Deputies will be appointed to help the Workpackage and Task managers; as a general rule, if a leader is from Europe, his deputy will be, whenever possible, from India and vice-versa: this will help in co-ordinating Partners taking in consideration distance problems.

### Information flow

All the information flow, which will be an important part of the day-by-day activity of the project, will be organized by means of electronic tools, to maintain a strong cohesion of the project despite of the considerable distance between the Countries involved. A Project Management Database, Facsimile, Postal Service, e-Mail, Mailing lists, Templates for Meetings Agendas, Meeting Minutes, Reports and Costs statements will be the basic tools to be put in place for information bookkeeping and flow. Besides, a project website will be settled with security levels, in order to interface individuals with the basic tools.

### Project website and mailing lists

Project website and mailing lists will be the main tool of communication.

A password protected project website will be set up before the commencement of the project to host reference documents and materials, intended to support the collaborative work of participants for the negotiation phase. A password-protected area will be however available for the uses of project participants.

Two mailing lists will be activated (EU-IndiaGrid-partners@EU-IndiaGrid.org & .eu EU-IndiaGrid-eb@EU-IndiaGrid.org & .eu) to facilitate the exchange of information within the project community. Functional mailing lists and other collaborative tools will be set-up with the beginning of the project activities to facilitate communication and collaboration among Partners.

### Meetings

Project meetings, supported by means of the electronic tools described above, will be one of the key tools for the running of the project. They will be held either face-to-face, by phone conference or by videoconference, focusing on tools such as VRVS and Skype (to reduce, when possible, loss of time and travel expenses). Meeting in person is however considered one of the most effective ways of strengthen the collaboration of groups of people so geographically dispersed and thus having few occasions to improve the  human network that is one of the objectives of this project.

The following face-to-face meetings are planned.

- Kick-off Project meeting.

- International workshops: three over a twenty four months period, to be held in Europe and India. When possible, such workshops will be held in conjunction with related initiatives, to maximize the attendance (see WP6 work plan).

- Quarterly PMB meetings (when possible, in conjunction with the project workshops and/or EU reviews).

- Monthly Technical Board Meetings.

A calendar with the dates of ordinary meetings will be agreed yearly at the kick-off meeting and at the last meeting of the first year.

### Documents

Regarding documentation, the Work Package Leader is responsible to see that the deliverable is drafted according to the technical and formal requirements. For all the documents a simple naming scheme will be activated with in the form EU-IndiaGrid [Type]-[WP/PM/GEN]-[Number] [Date]. An archive of template documents will be available on the project website to facilitate the production of all the relevant documents and deliverables. A monthly or bi-monthly newsletter will be published on the project web site and distributed to the partners and to external interested institutions via email.

### Conflict management

Normally it is expected that conflicts among project partners will be resolved amicably, or simply asking for advice to the PM, TM and their deputies. In case a conflict arises which cannot be settled in this way, the PMB will have the responsibility of its resolution, taking in consideration the policies stated in the Consortium Agreement, to be signed by all Partners prior to the commencement of the project.

PMB members will hear the parties and will decide about the conflict by voting on a simple majority. The PMB chair has the casting vote. As a general rule, such process will take place during normal PMB meetings (held both face-to-face or via phone-conference or videoconference) but, in case of urgent businesses, it can be carried out via email as well, provided that all voting members are timely informed about reasons and circumstances of the conflict. In case of plain seriousness, special PMB can be called to discuss the matter.

If, for some reason, a dispute cannot be solved in this way either, parties can decide to resort to arbitration, which shall finally settle the matter and be binding upon the parties.

An arbitration committee will be appointed in accordance with the procedure described in the Consortium Agreement, which shall set out in the award the detailed grounds for its decision and shall faithfully apply the terms of the Contract and of the Consortium Agreement itself.

## Plan for using and disseminating knowledge

A Project Management Database, Facsimile, Postal Service, e-Mail, Mailing lists, Templates for Meetings Agendas, Meeting Minutes, Reports and Costs statements are the basic tools that will be put in place for information bookkeeping and flow. Besides, a project website will be settled with security levels, in order to interface persons with the basic tools.

The already mentioned meetings are key tools for the running of the project. They will be physical meetings, by phone conference or by videoconference. As explained above, a calendar with the dates of ordinary meetings will be agreed yearly at the Kick-off Meeting and at the last meeting of the first year.

Specific actions will be undertaken to successfully disseminate project results. These include:

- Establishing close relationship with European Infrastructure projects such as EGEE-II, OMII-Europe and with organisations involved in the development of Grid infrastructures in EU and worldwide.

- Follow up European and worldwide standards as they emerge within international bodies like the Global Grid Forum (GGF).

- Organization of and participation in conferences, workshops and knowledge dissemination events, so as to disseminate the project results to the potentially interested vast communities of scientists and researchers in India.

- Co-ordination of dissemination activities by project partners in the academic and research communities of the participating countries.

The project will facilitate the spread and exchange of technical expertise between all participating countries, which already possess strong but isolated clusters of knowledge in the relevant areas.

Project will also facilitate the exchange of information between the participating countries and the rest of the world, via close interactions with worldwide Grid efforts and projects. This interaction between the associated participants of the project is envisaged to promote the integration of the research communities of the region to the European Research Area (ERA).

## Raising public participation and awareness

A number of measures will be taken to raise the level of awareness both of actual and potential Grid users and of a wider audience about the EU-IndiaGrid infrastructure and services. A global communication strategy will be deployed during the first project months, to identify key actors in India and segment this target to ensure that all relevant stakeholders are addressed with appropriate language and contents.

A rough a priori segmentation (to be defined during the proceedings of the works) shows two macro-categories that will be of strategic relevance to the achievement of such objective and the corresponding communication tools:

- Grid users (to be segmented in synergy with WP2) and potential users will be mainly addressed with tutorials, technical publications (i.e., cookbooks, etc.), mailing lists, online collaborative tools, technical and project workshops and Conferences.

- Governments, funding bodies and companies will be mainly addressed with ad hoc events (such as a Policy development workshop), public website, bulletins and press releases, project Conferences. The central web server will be a major vehicle for mass exposure of the project to the online community. Email lists, bulletins and online collaborative tools will all be used to draw potential users into the EU-IndiaGrid community.

The EU-IndiaGrid workshops will be used to target a wider audience in the academic and commercial sectors and may include demo sessions to showcase the latest developments of the EU-IndiaGrid infrastructure and services and ways to benefit from them; on the other hand, tutorials and technical workshops will be addressed to the EU-IndiaGrid community.

It must be highlighted that organizing on-site events will allow to deliver dissemination and outreach activities to a larger audience and, at the same time, to ease a critical issue of the project, i.e., the visas: the project conferences, workshops and tutorials will be therefore organized in India  whenever possible, while the organization of national Grid events will be encouraged and supported.

# Workplan – for the whole duration of the project

## Introduction – general description and milestones

The European Commission in the 5th Framework Program invested significant resources in developing new powerful Network and Grid Infrastructures. This process was continued in FP6 and a step forward was proposed for the structuring of European Research Area. EU-IndiaGrid also looks towards the 7th Framework Programme on supporting Research Infrastructures for 2007-2013 which clearly aims to boost EU research potential and its exploitation at a global level. The EU-IndiaGrid work plan has been designed keeping in mind that the results of such large investments of resources can serve as basis  for an intercontinental activity which can profit from existing infrastructures and is capable of providing relevant added value to the largely recognised successes of such programs.

The project is articulated in one management work package (WP1) and five work packages (WP2-WP6)  dedicated to support activities. WP2 has the task of  identifying new users, both in research and industry areas, keep relationships with other relevant projects, identify sustainable actions, deals with requirements capture and analysis. WP3 supports the  networking connectivity plan and the liaison with the relevant networking projects.  WP4 deals with Grid middleware and interoperability of the European and Indian Grid infrastructure. WP5 deals with supporting applications deployment. WP6 deals with outreach and dissemination.

## Work planning and timetable

A first level of analysis of each WP is given below with the Work Breakdown Structure (WBS), followed by the Statement of Work per Workpackage and the project’s GANTT and PERT charts, and the risk analysis. The WBS was defined in such a way that each workpackage is broken down into a number of self-standing and manageable tasks. The aim was to achieve manageability at the coarsest possible level - so as not to introduce an unnecessary management overhead and dependencies - while keeping the distinct tasks technically and logically separate.

### Work Breakdown Structure (WBS)

| WP1 | Project administrative and technical management |
| --- | --- |
| 1.1 | Administrative management |
| 1.2 | Technical management |
| WP2 | Building an eScience Network Community |
| 2.1 | Community building identifying researchers & RTD performers interested in Grid Infrastructures |
| 2.2 | Community building identifying industries, SMEs & international performers interested in Grid Infrastructures |
| 2.3 | Relationships with other projects & initiatives |
| 2.4 | Sustainable Actions |
| WP3 | Network Planning Support |
| 3.1 | Network connectivity plan |
| 3.2 | Network Support |
| WP4 | Pilot grid infrastructure operational support |
| 4.1 | India-Grid and EGEE interoperability |
| 4.2 | Harmonisation of Authorisation and Security Policies |
| 4.3 | Operational Support of Advanced Services |
| 4.4 | Promote the development of existing and new grid infrastructures in India |
| WP5 | Applications |
| 5.1 | EGEE applications (ALICE, CMS) |
| 5.2 | Biology applications |
| 5.3 | Condensed matter physics applications |
| 5.4 | Earth and Atmospheric Sciences |
| WP6 | Dissemination & Networking Events |
| 6.1 | Pan-European & trans-European Promotion & Dissemination Activities |
| 6.2 | International Networking Workshops |
| 6.3 | Training Events |
| 6.4 | Follow-up activities (evaluation of events) |
| 6.5 | EU-IndiaGrid Portal Development & Maintenance |

Figure 2: Work Breakdown Structure

### Statement of Work (SoW) per Workpackage

#### WP1- Project administrative and technical management

The consortium management activities have been described in detail in section 6. The work-program, for practical reasons, has been divided in two activities. Activity 1.1 is devoted to the financial and administrative management of the project. This activity will involve mainly the Project Manager, the Project Office and the Project Management Board. Activity 1.2 is related to the technical management of the project. This activity will involve mainly the Technical Manager, the Project Manager and all WP managers. The relative budget has been distributed accordingly to these responsibilities. The general rule applied to this WP is a consequence of the previous experience of the Partners and is calculated as 7 percent of total EU contribution. This figure was used in WP1 for all partners, while in some cases this was reduced to balance out the management effort.

Apart from the activities which are strictly related to the project management, this  work package will tackle, in strict coordination with others pertinent work packages, all horizontal actions relevant to the project general objectives (especially O1, O2, and O3), as well to its identity and presentation to the public. Furthermore, liaison activities with other related projects (i.e., for example, EGEE-II and GARUDA, but also with local initiatives) will be as well carried out, in coordination with the project dissemination and outreach activities (WP6).

#### WP2- Building an eScience Network Community

This work package primarily focuses on bringing together a community of Indian and European researchers and industrialists interested in learning more about EU-India grid infrastructures, specifically in the fields of High Energy Physics, Condensed Matter Physics & Material Sciences Area, Biology & Medical applications including Atmospheric Physics and Climatology; the latter being particularly pertinent in India with ongoing studies to which Europeans would like to evolve further.

##### Database of Contacts

The consortium will amalgamate all the contacts through a unique access point on the web site of the project. A registration process is necessary to attend the training and workshops – these contacts would then automatically be listed in the database. The database, made up of Indian and European Grid related Research & Industrial contacts, organised in topic to facilitate ease of navigation, and to which all registered members may access to find other contacts even once the project has terminated.

All consortium members will expect each of the partners to raise awareness of the significance of the web site and the registration facilities in both Europe and in India and considering the range of organisations involved in the project from Industrial SMEs, Research and Academic institutions, there should be a balanced mix of communities.

Both ICTP and CDAC have a large network of contacts with scientists and scientific institutions in India. These institutions will be contacted and actively invited to indicate their interest, plans in the area of the grid and related technologies; this information will be entered in  the database.

A number of the existing members collaborate already on related projects with specific emphasis on bringing Industry closer to Grid and are certainly closely linked to a network of international contacts which are useful to:

- Increase Community development;

- Invite as guest speakers at the workshops and to the project conference;

- Invite as tutors for the training events;

- Contact for participant recruitment in general.

##### Public Deliverables

There are a series of deliverables which would make for very interesting read for the public. A way to achieve increased Community membership could be to offer public versions of the deliverables, available as downloads from the website upon registration.

Considerations to make here are the series of interesting public documents which will be released in the future from other EU funded projects, such as the Research & Industry Handbook on e-Infrastructures developed in the EU project BELIEF or the Guide to Infrastructures which takes a close look at Europe's core e-Infrastructure projects (GEANT2, OMII-Europe, EGEE-II, and DEISA)  with a view to making the technology more comprehensible and better understood by potential users, we may include also results of EU-IndiaGrid in these documents.

The workpackage also considers sustainability actions where the consortium will take into consideration the co-operation efforts initiated through a presence at the workshops, from the onset of the project,  and at the training events. A general idea could be to make the website accessible to users once the project has terminated for updates on EU-IndiaGrid and to continuously build upon the Community.

Targeting Industry

The presence of a SME Industrial partner, as Metaware, within the EU-IndiaGrid project will be beneficial in opening a stronger channel with industry.

Metaware, which coordinates the BELIEF project (please see section under Related projects for further details) looks to bring together both the scientific and industrial communities in the fields of e-Infrastructures through its industrial partner, Engitech based in Ireland, the sister partner of the Engineering group, is putting together a research and Industry handbook on how research infrastructures can be deployed in industry. By compiling this, the BELIEF consortium has access to a number of industrial sources making up a pertinent industrial database who may be contacted on the developments of EU-IndiaGrid.

EGEE-II & Industry

In addition to this, Metaware is the leader of the Industry Forums (IF) of the EGEE-II project (2006 –2008) which aims at: facilitating the interaction between the project and industry, providing a two-way forum for communication between industry and the EGEE-II project and will thus be an important channel for dissemination. The IF will specifically target sectors that could benefit from the Grid, such as biomedical, pharmaceutical, earth observation, chemistry, finance, but have not yet taken up the opportunity to work with EGEE.

Coupled with this, Metaware is in contact with the Industry Task Force –(ITF) which will bring together representatives from industry who have shown a clear and active interest in working with EGEE-II and in deploying their industrial applications on the Grid. Metaware will leverage off these contacts to support the industrial contacts within EU-IndiaGrid.

EU-IndiaGrid may also look at having a presence at the future EU Grid technology days in both 2006 and in 2007, to report back to the EU Grid research community with a clear vision (from the content provided in the proposed Network connectivity roadmap) on the future of Grid.

EGEE-II Industry Days

Similarly, the consortium will watch out for the calendar of events within the organised EGEE-II Industry days which will be held every two months, lasting one-day and which will be domain based looking at 70-80 participants where specific case studies will be introduced. Once the topic is of interest to the consortium, it will ensure active and prominent attendance to help leverage off the industrial contacts there.

##### Industry Presence at the EU-IndiaGrid Training Days

The consortium will try to make the training element as effective as possible by including, where possible, an industrial case study from a European and Indian organisation to effectively show the deployment of the various applications.

The EU-IndiaGrid consortium will calendar in its schedule, the dates of concertation or cluster meetings organised by the EC to interact with the other related projects and to exchange knowledge, experiences and find common grounds for synergising for the future. Some related projects have been listed below.

##### Related Projects 1

###### 6DISS (http://www.6diss.org)

The 6DISS project is an FP6 SSA project which promotes IPv6 throughout the world. At present 6DISS is looking to be present at events in Africa, the Mediterranean, South America and the Balkans. The 6DISS project has a key contact in India and will put the EU-IndiaGrid consortium in touch with them to follow up on mutual interests.

6DISS is looking to be more active and present at the events in India. Of course they are very happy for us to mention their project in our events, and the target audiences may well be the same and there will be synergies, even though grid and IPv6 are different fields.

A mutual agreement has been reached for collaborative support to both projects (ie: visibility on project portal, representation at events and general promotion). The agreement will take the form of a signing of a Memorandum of Understanding (MoU).

Please view the calendar of events that 6DISS has planned and where EU-IndiaGrid may collaborate:

| Date | Event | Venue |
| --- | --- | --- |
| 4-5 Jul '06 | 21st TF-NGN Meeting | Ljubljana, Slovenia |
| 16-18 Jul '06 | IPv6DFI'06 | Silicon Valley, USA |
| 17-21 Jul '06 | 22nd APAN Meeting | Singapore |
| 9-14 Jul '06 | IETF 66 | Montreal, Canada |
| 26-29 Jul '06 | 6DISS Workshop (South & Central America) | Quito, Ecuador |
| 27 Jul - 4 Aug '06 | SANOG VIII | Karachi, Pakistan |
| 1-2 Aug '06 | IPv6TD | Bucharest, Romania |
| 21-26 Aug '06 | PacINET 2006 | Apia, Samoa |
| 1 Sep '06 | Global IPv6 Summit Philippines | Manila, Philippines |
| 11-14 Sep '06 | IEC Broadband World Forum | Vancouver, Canada |
| 2-6 Oct '06 | RIPE 53 | Amsterdam, The Netherlands |
| 16 Oct '06 | 6DISS Project Meeting #6 | Brussels, Belgium |
| 17-19 Oct '06 | 6DISS Training the Trainers Workshop | Brussels, Belgium |
| 31 Oct - 1 Nov '06 | Australian IPv6 Summit | Adelaide, Australia |
| 13-17 Nov '06 | Global IPv6 Summit France | Cannes, France |
| 21-23 Nov '06 | IST 2006 | Helsinki, Finland |
| 4-7 Dec '06 | Internet2 Members Meeting | Chicago, USA |
| 21 Feb - 2 Mar '07 | APRICOT 2007 | Bali, Indonesia |
| 27 Feb - 3 Mar '07 | APNIC 23 | Bali, Indonesia |

###### MONSOON

As a result of the EuroIndia2004 event organised in New Delhi back in 2004  (www.euroindia2004.org), Metaware established a substantial number of industrial contacts interested in ICT developments and furthering co-operations between Europeans and Indians (at least 65% of the database is made up of European and Indian industrial contacts). The latter is further enhanced through the FP6 IST project MONSOON which has organized specific events and one in particular on Grid activities in Bangalore resulting in an active contact Grid database list.

The EU-IndiaGrid project will look to engage support from the EU IST project MONSOON project (www.euroindia-it.org) which has a developed a list of Indian community members already, of which a number,  already make up part of the Grid Community in India.

###### GRID@ASIA

Grid@Asia will define a joint research agenda to address international Grid priorities relying on a core of leading European Grid research institutes. This initiative will be supported by Asian partners to ensure on-site organisations, enhanced visibility and the participation of high-profile industrial and scientific delegations. EU-IndiaGrid will leverage off their last and final event, particularly as there is a training component to define synergies.

###### BELIEF (Bringing Europe’s eLectronic Infrastructures to Expanding Frontiers)

By strengthening networking links between the Research, Scientific & Industrial communities, BELIEF is expected to provide Europe with a clear picture of the latest developments of e-Infrastructures showcasing the latest e-Infrastructure studies in India and in Latin America. BELIEF has seven events to organise where it would strongly value the presence of the EU-IndiaGrid project.

- BELIEF & EU-IndiaGrid Grid Synergies

The consortium sees the EU-IndiaGrid project working parallel and offering value add to the SSA project BELIEF through its domain specific links (predominantly in Biology Applications & Condensed Matter Physics Applications). BELIEF focuses on developing a focused, generic e-Infrastructures Community based on research & industry members and it is not limited to the topics chosen for EU-IndiaGrid project.

By focusing on specific application areas as well as incorporating the Training element in EU-IndiaGrid, which has not been planned within the BELIEF project, the European & Indian community of the EU-IndiaGrid project may benefit from an existing BELIEF community of international players and add considerable new members from the Indian side at the same time.

- BELIEF vs EU-IndiaGrid Event Synergies

BELIEF organises 1 specific international conference/exhibition on horizontal themes on the e-Infrastructure area in India in collaboration with its Indian partner ERNET.

This event, currently planned sometime for December 2006 will be able to leverage off the 2 targeted events that EU-IndiaGrid has planned & organised in India in January 2007 & September 2007 consecutively, in order to broaden a wider Indian audience and thus would further mark Indian Grid developments in the areas of both Biology, High Energy & Condensed Matter Physics and Earth and Atmospheric Physics on the international arena which are currently still unknown to many Europeans.

The conference organised in BELIEF will serve as paving the way in getting to know the right community in India to invite to the stand-alone events planned for the following months in 2007 for EU-IndiaGrid. As the event in India is made up of both plenary as well as parallel sessions, it may be wise to consider an EU-IndiaGrid session here on a focused topic to maximise audience and support from a national level with the aim of bringing in more industrial, key Indian players as well.

IST2006

BELIEF is currently organising a networking session during IST 2006 in Helsinki in November, this may be a prime opportunity to introduce EU-IndiaGrid to the IST community.

- BELIEF & Industry links for EU-IndiaGrid

Moreover, through its development of an international e-Infrastructures database of Industry link actors, BELIEF may support EU-IndiaGrid in introducing the European Industrial players to the Indian market of organisations working on grid developments for further exploitation and EU-Indian co-operation activities.

#### WP3 - Network Planning Support

The availability of an adequate network infrastructure represents a pivotal element for the development of Grid infrastructures. As a matter of fact, to work properly, Grid applications need a high throughput among the connected sites, to ensure the exchange of a large amount of data in limited time, which is especially crucial in case of applications with tight time constraints. One of the main requirements of the project is therefore the availability of a reliable and effective broadband network infrastructure, provided with opportune QoS policies. Such requirement should be satisfied both at the levels of the international connectivity and of the national backbone, in order to achieve the best results and to avoid bottlenecks.

a) International Connectivity

At the moment, no direct Research connectivity exists between the European Research networks and the ones of the Indian area and the overall connectivity situation does not seem ideal to adequately support the needs of such applications. However, this situation is bound to improve in the next few months thanks to the implementation of a direct link between GEANT2, the Pan-European high-bandwidth backbone, and ERNET, the Indian national Research and Education Network. A few months ago, DANTE, operator of GEANT2, submitted a call for tender for connectivity between the mentioned backbones; the procurement phase ended successfully and it is foreseen that operations will start in brief. Expressions of interest have been already collected to upgrade the new link in order to achieve a larger capability and the use of such link for grid operations may be regarded as a further boost in this direction.

On the other hand, it is still unclear whether EU-IndiaGrid will benefit from the ORIENT link, whose operations are foreseen to start during the current year. The ORIENT project aims at improving research and education IP connectivity between Europe and Asia, but topology of details are not yet available and it is therefore uncertain whether they will impact on the Indian region directly.

One of the main aims of the WP3 is hence to investigate limitations related to the current Europe-India network structure and perspectives of enhancement. Once gained a clear picture of the status quo, measures will be taken to pursue optimal networking solutions taking into account the peculiar requirements of the Grid pilot infrastructure and applications, thanks to close collaboration with existing (and possibly future) connectivity projects and lobbying Governments and other involved Organizations.

b) National backbone

ERNET is the largest nationwide terrestrial and satellite network in India, with points of presence located in research and education institutes across the country. Its backbone can provide connectivity in the range of Kbps to 155 Mbps, which in principle will be sufficient to enable grid operations. Anyway, other aspects as the bandwidth usage and the quality and capacity of links with  whom the single partner Organizations actually access the backbone must be taken into account, as well as specific requirements of grid users and applications.

The ERNET backbone implements IPv6, so interoperability issues should be taken into account as well.

ERNET contribution in WP3 will mainly impact on the provision of network connectivity and services at the national level and on the related user support.

WP activities will split in two tasks:

##### Network connectivity plan

The project will provide a plan in which, starting from the present status, the foreseen evolution of network connectivity and services will be described taking into account the EU-IndiaGrid applications and users special requirements. This activity will also liaise with pertinent Organizations and Projects and perform appropriate lobbying activities (in synergy with task 1.3), in order to obtain the fulfillment of such requirements. As mentioned above, the availability of high bandwidth connectivity is presently foreseen for the current year, while it is still uncertain whether EU-IndiaGrid will profit from other connectivity initiatives.

##### Network support

This activity will guarantee that network performances and services are in line with the specific needs of the pilot applications and will include user support activities to cope with network malfunctioning, accidents etc.

#### WP4 – Pilot Grid Infrastructure

A pilot grid infrastructure is already in place in India, the GARUDA National Grid Initiative (http://www.garudaindia.in). It is a collaboration of science researchers and experimenters from 45 Institutes on a nation wide grid of computational nodes, mass storage and scientific instruments. This work-package will aim at addressing  and identifying the interoperability issues between EGEE and GARUDA. A task of this work-package will be the identification of the most appropriate middleware solutions allowing to the two infrastructures to interoperate. The latest solutions from EGEE middleware will be considered..  This workpackage explicitly addresses objectives O1 and O3.

The work will be organized according to the following activities.

##### GARUDA - EGEE interoperability

This activity will start with a Comparison of GARUDA functional architecture and services with EGEE services and tools. The aim is to support a flexible and reliable infrastructure capable to guarantee a satisfactory service operative working level to the heterogeneous requirements of scientific communities.  Appropriate solutions for the interoperability of the two infrastructures will be studied and proposed.

##### Harmonization of Authorization & Security Policies

This activity will be dedicated to the harmonization and agreement of authentication and authorization security procedures for the Grid infrastructure. The aim is to agree on the common security policies and identify Indian Certification Authorities trusted from EU countries and trusting EU CAs. They will provide certificates for each scope member. Users can access their CA service through the proper WEB site. This activity will also carry out studies on the use of Virtual Organizations and related Grid tools in an Intercontinental environment: the usage of common VO infrastructures will be investigated and the relevant solutions, based on the present state of the art, will be proposed.

EU-IndiaGrid proposes the use of VOMS, an Authorization System for Virtual Organizations, where administrators can use an automatic procedure to insert and manage new members and new groups to their VO.

##### Operational support of Advanced Services

Usage of Advanced Grid tools and services will be extended in GARUDA making profit of the past experience of European partners and the acquired know-how of some Indian partners. Several middleware components can be taken from EGEE. Solution for grid monitoring will be studied and tested in order to ensure a production quality of the grid services which should be achieved within the first year of the project. Automatic installation and configuration of a grid monitoring tool, such as GridICE (http://gridice.forge.cnaf.infn.it/), will be published on a public link and the GridICE reports will be available on a section of the web portal. Necessary features of the Grid monitoring tool will be: automatic discovery of grid resources, monitoring of computing power, job load, storage load and queues availability, Site and VO views, grid services monitoring, and a geographical map of the grid resources.

A grid policy system (as G-PBox, http://infnforge.cnaf.infn.it/gpbox/) is necessary when concurrent accesses to resources can create conflicts. A comprehensive study to design or adopt an innovative model to share resources based on dynamic and scalable criteria is needed. This model will underline the necessity of a smart management of job submission through a filter based on the concept of policies, which acts on the Grid topology and their associated properties and not on the single resource names. This model should implement the following requirements: using a structured resource-use policy, providing an advanced and abstract mechanism to automate checking of resource use, defining dynamic rules immediately and automatically implemented by the resource manager, gathering useful users resources dynamic information, for example accounting, etc.

An accounting system like DGAS (DataGrid Accounting System, http://www.to.infn.it/grid/accounting/main.html) will be deployed. It will allow management of resource balancing between resources providers and resources consumers distributing "GridCredits" used as an exchange currency between users and resources.

The grid infrastructure will be used from the beginning by the pilot applications (High Energy Physics, Biology and Condensed Matter Physics, Earth and Atmospheric Sciences) but will be open and available to any new applications identified within the WP2 activity.

#### WP5 - applications

Many scientific areas are limited in their possibility of growth and evolution to eScience by inadequate   bandwidth connectivity and tools for the usage of large distributed resources.

Satisfying those requests is one of the main objectives of the European Research Area (see O2, O3, and O5).

To demonstrate the effectiveness of a grid approach in responding to these needs, this project has selected few applications, which are already based on collaborations between European and Indian researchers, to be the driving force of a feed-back process about the tools and middleware deployed with support from WP4 activity and in cooperation with WP2 and WP6 activities. The selected applications are a sample of those most demanding in terms of producing and processing large  quantities of data (see O3). Each application has an European partner and at least one Indian partner with consolidated collaboration in their research activity. All involved partners have already experience in the use of large computing resources and grid tools. All partners are involved in the major European and Indian grid infrastructure projects.

Following objective O3, and in cooperation with WP2 and WP6, WP5 will be open to new applications and users. To the three applications originally present in the proposal (High Energy Physics, Biology, Condensed Matter Physic)) a new one has been added: Earth and Atmospheric sciences. These fields are of particular interest in the region and, in some sense, the involvement of this application is a result already achieved by the project.

As illustrated in the TIFR profile, other potentially interested research areas within TIFR may profit of the grid infrastructure. In addition the high research and technical profile of all Indian partners will contribute to the extension of the user community.

##### EGEE Applications (ALICE, CMS)

The established user communities considered in this activity are those collaborating on the LHC (Large Hadron Collider) experiments in the field of High Energy Physics and sharing with them the applications. ALICE and CMS experiments at LHC, actually under construction at CERN, will start taking data in 2007 and a strong group of Indian scientists is actively participating to the experiments. The data collected by each experiment will be in the order of 100 MBytes per second (up to 1.2 GBytes per second in the case of ALICE) and will be widely available to all the collaborators in Europe and worldwide, provided that a good connectivity and a compatible grid infrastructure is available. ALICE and CMS are already EGEE supported applications. This activity is a simple extension of the EGEE work aiming to support these applications also on the interconnection to India. These applications, being already “gridified” in EGEE, will be of enormous importance in the first phase of validation of the interoperability and, on the other hand, will require a smaller amount of resources. The Indian partners for these applications (BARC, SAHA, TIFR) are involved both in the GARUDA National Grid Projects and in the “DAE grid” (Department of Atomic Energy grid) project.

##### Biology Applications - Systems Biology simulation tools and model databases on the EU-IndiaGrid.

The computational analysis of biochemical and biophysical information flow in cells is emerging as a major aspect of biology. This involves complex computer models with very large computational loads, as well as extensive referral to on-line data sources. The outcome of such efforts is a highly quantitative and predictive understanding of fundamental biological events. The proposal is to harness the EU-IndiaGrid to more effectively perform these calculations and to disseminate the data among the collaborators and any other interested researchers.

Biophysical models of cells such as neurons involve spatial subdivision of cells into many small compartments, each of which is electrically uniform. Each compartment typically represents many ion channel types, diffusion of certain ions, and inputs from other cells. A complex model of this kind may involve thousands of compartments. A large network model may require tens of thousands of such single cell models. A simulation of a few seconds may require a year of compute time unless the problem is decomposed over many nodes. The groups in this Consortium have performed several of such large simulations.

Biochemical detail in cells begins at the single compartment level with the representation of reaction-diffusion processes in cellular signal flow. Typical models involve hundreds of molecular species, for example to represent synaptic signal flow. Reaction-diffusion calculations are expensive. Further computational costs arise when calculations are done at the single-molecule level using Monte Carlo methods. These are typically required in very small cellular volumes. Because biochemical signalling events are slow, lengthy simulations may be required. The groups in this consortium have carried out simulations from many hours to years. Such calculations may indeed take a long time even on powerful clusters of machines.

Exchange of both these kinds of models is an essential part of the scientific process. There are several databases now extant for such models, and their size and use is rising rapidly. Two groups in this consortium run such databases, and anticipate heavy traffic in data exchange.

In summary, the participating groups from EU and India (Cambridge and NCBS)  have heavy computational and data loads which will greatly benefit from access to large computing infrastructure as well as high data exchange rates. The Indian group already has cluster computer resources which could participate in the grid effort. The specific support of the Cambridge eScience Centre will further contribute to this application activity.

##### Condensed Matter Physics Applications

The goal is to port on the computational grid  some of the scientific applications for ab-initio quantum simulations contained in the Quantum Expresso package (www.quantum-espresso.org) extensively used in condensed matter physics research group involved in this project. The package contains state-of-the-art parallel programs for quantum simulations of extended systems, up to a few hundred atoms.  Porting such a package on a computational grid is highly non trivial due to its intrinsic structure (large I/O requirements, tightly coupled parallelism just to cite a few).

The Quantum Expresso package is already used by a few tens of Indian scientists: in July 2006 a specific training workshop on this package  will be organised in Bangalore and it is likely that  a much larger community of Indian computational condensed-matter physicists will be using the package, and be therefore ready to take advantage of the advanced features of the computational grid.

The ICTP condensed matter group is also developing a new strategy for classical molecular dynamic simulations. This kind of simulations are generally less demanding in terms of portability on the grid, but would offer the opportunity to test and develop application-aware schedulers in order to best fit the available  computational resources. The advantage with respect to standard  grid schedulers (e.g., Condor) is that we would be given the chance to couple the  application performance model with the resource selection strategies, so as to finally provide enhanced performance for the application over the available Grid resources. The involved EU and Indian Institutes (ICTP and Pune) have a well established collaboration in this research domain and well developed grid expertise. The Pune University is involved in the GARUDA National Grid project as well.

##### Application of Modeling in Earth and Atmospheric sciences

In this section the project will address the partial requirements in two major areas viz. Earth and Atmospheric sciences.  In Earth Sciences, to study very large scale and complex earthquake research problems, seismologists, and earthquake engineers require to have seismological data sets from different regional areas, experimental results from different earthquake research laboratories, data processing/analysis software and above all the high performance computing resources. This can be achieved by sharing the resources through grid.  Currently, study of earthquake prone structures and their safety as well as seismic acoustic modeling for oil exploration are two major topics of interest to C-DAC.

In atmospheric modeling, high-resolution, long-duration simulations, climatology, ensemble, observations and satellite data for Monsoon studies by different research and operational institutes produce tens of petabytes of output. To be useful, this output must be made available to researchers nationwide, both at national laboratories and at universities, other research laboratories, and other institutions. For weather forecast models, creating and using accurate initial conditions and data assimilation is very crucial. Integration of global models output for regional weather forecast or coupling high-resolution meteorological output with air quality models for pollution forecast based on grid computing provides cost effective solutions.

The aim of this effort is to provide a platform that would ease the researchers in the areas of Earth and Atmospheric sciences to simulate various models either to use separately or to use in combinations to produce results that would enable them to understand the natural physical phenomena. A pilot study for the EU-IndiaGrid infrastructure will be consider in order to achieve the following.

- Seismic Acoustic Modeling code and a code for structural safety will be ported on to the grid (both GARUDA and EU-India global infrastructure) and validated for the purpose of oil exploration and for earthquake prone structures.

- In atmospheric sciences, application grid will be developed with global forecast models, regional atmosphere model regional ocean model and coupler component using heterogeneous HPC resources scattered across geographical locations.

- A sample workflow of the above mentioned models would also taken up as a pilot study.

##### Additional applications

Since one of the major goals of EU-IndiaGrid is to ease the adoption of grid technologies for eScience, the Project will also be open to any other additional applications of new communities eventually interested in using the project’s pilot infrastructure, where “additional” means not foreseen at the time of writing of this programme of work. The new communities will be indentified and their applications evaluated through specific questionnaires and surveys following the well established policy adopted in other Projects such as EUMedGrid and EELA.

#### WP6 - Dissemination & Networking Events

Within the framework of this WP, a number of measures will be undertaken in order to:

- Disseminate knowledge to communities which have already shown interest in Grids for their applications (i.e., the user communities already contacted by the partners and the ones which will be identified through WP2).

- Disseminate Grid achievements and benefits to a wider audience, in order to attract both new scientific communities or industrial entities which have not yet evaluated this technology as a possible opportunity;

- Create a human network covering both India and Europe, to spread both Grid awareness and know-how.

The work package comprises two major tasks:

  - Organization of three domain specific Workshops and a  General Project Conference which runs horizontal across all themes as well as extra topics previously not identified;

  - Organization of 4 extensive training events which will have, among the others,  the important goal of identifying and forming a group of grid trainers in India capable to increase the number of induction courses in India within the lifetime of the project.

And extra collateral and auxiliary ones, that support and consolidate the results of the previous ones:

- Trans-European promotion and dissemination activities;

- A Web portal;

- A set of evaluation and follow-up actions.

##### Workshops Objectives

The objectives of the three workshops and the Conference, to be organised in selected areas predominantly in India, chosen with the support of the consortium partners, will be an opportunity for both Europeans and Indians interested in the target disciplines selected to exchange knowledge, learn about each other’s developments, and look to see if there are potential collaboration opportunities in both research and commercial contracts for the future. The workshops lasting 2 days, comprising in the region of 70 to 100 participants, will each focus on a specific topic, which comprise:

- High Energy Physics Biology & Medical applications (inc. Industrial dimension);

  - These are the two main EGEE application areas, and have determined most of the evolution of the EGEE technology

- Condensed Matter Physics &  Material Sciences Area (inc. Industrial dimension);

- Atmospheric Physics and Climatology.

(NB: As the project evolves, the consortium may find that other related disciplines may be appropriately placed within an event so titles may be subject to some form of variation.)

The Conference will take place in India, and will be devoted to a wider audience, focusing more on industrial and infrastructural aspects and topics currently not considered such as: Grid & the Media, Finance, Automotive, Environment, Grid & SMEs, Trust & Security issues, etc.

The general conference may leverage off the conference organised in New Delhi for the BELIEF project, considering it has been provisionally planned for month 16, a year after the BELIEF conference when EU-IndiaGrid is expected to have gained considerable visibility.

###### Potential Venues & Countries to host the workshop events

The project partners have adequate facilities or are aware of appropriate venues to host the workshops. Taking advantage of this means savings on venue hire and audio visual equipment. Coupled with this, the European partners will take advantage of the Indian partners’ networks to increase dissemination, promotion and national governmental support, if available.

The consortium sees the event organised as the following:

###### Potential Workshop Agenda (2 days)

Day 1 am

Welcome address from host organisation

Opening Visionary statement from Indian representative in the selected discipline (Research, Industrial or Governmental)

Opening Visionary statement from Indian representative in the selected discipline (Research, Industrial or Governmental)

EC representative

Day 1 pm

State of the art description (Indian representative)

State of the art description (European representative)

Real Case Study description (2 European & 2 Indian)

Platform to showcase results & Open discussion

Q&A

***********

Day 2 am

Round Table discussions following on from previous day

Recommendations & Conclusions

Next Steps

Day 2 pm

Site Visits

***********

##### Training Objectives

As outlined in the “Events Planner” in Appendix A.5, the consortium has identified as series of strategic events placed also around related initiatives, which would increase the number of events planned, at presumably minimal cost for the consortium members, except for travel, subsistence, and minimal consumables costs (NB: this provisional event planner is by no means definitive as it will be discussed, at length during the kick-off meetings and subsequent meetings held between consortium partners).

Each workshop organized in India will be supplemented by an extended training session covering applications in the same subject field of the Workshop. At least a fourth training event will be organized independently, hopefully linked to local Indian grid activities.

Each training activity aims at a selected number of between 20-40 individuals of Indian academic or industrial entities, already interested in exploiting grids, with the objective of making them fully aware of the potential and characteristics of the European grid technology, by actually porting real applications or subsets of them onto the grid test bed. The applications will be selected among those actually used and proposed by the participants. Priority will be given to institutions planning to use the grid in the framework of cooperation with European entities.

These institutions will be recruited through an initial emailing request sent out to potential organisations in understanding the users’ benefits and needs to then target the right audience.

Apart from the porting laboratory, introduction to the use of Grid will be provided; depending on the needs of the participants, training about grid site operation can be added.

###### Potential Venues & Countries to host the training events

Being addressed predominantly to Indian academic or industrial RTD staff, most of the activities will be run in India, at partners’ sites. As an example, at least the first event will be held at the Pune University Campus, where one of the partners, C-DAC, has its headquarters. C-DAC is already considering organizing an in-depth training activity for the support of the Indian national grid initiative GARUDA, and has adequate facilities to host the training. The EU-IndiaGrid project may boost this opportunity significantly. The possibility of organizing some of the activities at other partners’ sites is currently being explored and will be defined in the Events Planner, mentioned above.

###### Potential Training Agenda

Each training event will cover the following basic topics:

- introduction to grid computing;

- authentication and authorization mechanisms;

- job submission and control;

- data management;

- grid monitoring.

All the five topics will be presented by means of 1.5 hour lessons followed by hands-on sessions. This basic introduction to grid computing lasts one and a half days and aims at providing the basic notions about how to interact with the grid. The rest of the training event will focus on porting specific applications on the grid. There will be a general discussion where a few applications out of those proposed by the participants will be selected: each application will be then analysed and ported on the grid by a working group formed by participants assisted by a tutor. Upon request, some working groups could be devoted to infrastructure operation training, by installing and running a complete grid site integrated into GILDA, instead of application porting.

The consortium plans to have from 5 to 8 working groups for each training events. The duration of the porting activity (excluding the initial introductory day) can vary from at least 1 day to 4 days at most, depending on the various circumstances and the specific audience. All the hands-on sessions and the application porting activities will be performed on the GILDA t-Infrastructure. Each group is supposed to summarize and report on their activity at the end of the event.

.

##### Expected Outcomes

The workshops are expected to create a network of interested Europeans and Indians wishing to explore further common interests and look to leverage off each others’ know-how and expertise. The consortium, through its developments in WP2 of building an industrial and research community, will ensure a certain amount of industrial participants, where applicable, through its networking and dissemination efforts, to consider sustainable actions.

From the training perspective, participants are expected to gain a working knowledge of the grid infrastructure and of the benefits they can obtain from it. The participation is expected to be mainly from Indian groups, with Europeans participating when and if they are involved in a collaboration with Indian scientific institutes.

Apart from significantly increasing the number of institutions that can adopt grid technologies for their cooperative RTD activities, these training activities will form a number of persons skilled enough to help spreading the grid technology within the region, running their own small training events, to which the consortium is prepared to provide ongoing assistance

We expect that a significant fraction of the participants to the national Indian grid projects coordinated by the project partners ERNET and CDAC  will organize such a basic grid training, taking advantage from all the tools adopted by the project, like the GILDA t-Infrastructure and the Egrid LIVECD. The consortium will assist the organization of these training events if needed.

Specific support will be provided to the participants in the training events, to complete or expand the porting of their applications to the Indian grid infrastructure. This support will be provided through simple discussion fora available on the EU-IndiaGrid Web site, supplemented by videoconference or other means depending on the needs. These activities will, when suitable, be carried out in collaboration with WP5.

##### General Dissemination of the Workshops & Training

Both the workshop and the training events will be promoted using the partners’ mailing lists and National contacts. The consortium will distribute Announcements around the dates of the specific events. In addition, the consortium will develop specific activity poster/brochures promoting the workshops and training events

Follow-Up and  Evaluation

The evaluation reports resulting from the workshops will clearly contain conclusions as well as recommendations to assess for the future follow-up actions or next steps.

Likewise for the training, participants will evaluate the event as well as formulate recommendations about further training initiatives and evolution of services on the grid infrastructure. These documents will be part of the activity evaluation report.

All the materials used and produced in the training sessions, including handouts, reports on the application porting labs, possibly recorded versions of the lectures, will be made available on the  EU-IndiaGrid Web Site to registered members.

##### Financial Contributions to the events & training

Budget has been earmarked under the external costs and subcontracting categories for some of the partners who will negotiate favourable deals with suppliers. Having the events at the partners’ premises, where possible, will save considerably on financing. A detailed cost analysis has been carried out by the consortium to cater for the various expenses necessary.

##### Relation with the project’s objectives and success indicators

This work package implements O3, O4, and O5. The number of participants in the activities of the project (expected, as indicated from the events planner, see Measurable Impact row), in the region of around 550 interested European and Indian participants, is a critical success parameter in evaluating the achievement of O4 and O5.

Another crucial success parameter with respect to O4 will be the number of certificates delivered by GILDA Certification Authority to Indian users, and the number of jobs running on GILDA with  those certificates.

The number of induced local events and the number and quality of the follow-up indicated in sect. 7.2.2.6.3  is a critical parameter to evaluate the success in O3, that will be assessed at M5.2 and in the final report.

It is vital that the follow-up reporting closely monitors and tracks progress of follow-up between the European and Indian organisations post event to understand the two-fold effect of a) the training as described above and b) the workshop outcomes in terms of future collaborations and effective work between European and Indian organisations.

## Graphical presentation of work packages

In the following figure, the project plan in terms of time constraints is presented. Several basic assumptions have been made as described in the detailed Workplan. The Gantt chart additionally splits the Workpackages into activities.

Figure 5 – Gantt chart

### Interdependencies diagram

In the figure below, the project components interdependencies are shown.

Network                          Middleware       UsersPromotion

WP5: Applications

5.1: EGEE applications (ALICE, CMS)

WP6: Dissemination

WP4: Pilot infrastructure operational support

WP3: Network Planning and Support

6.1: Promotion & Dissemination Activities

6.2: International workshops

4.2: Define and implement the security and authentication framework

4.1: Define the deployment strategy for Indian Grids and deploy Key services

5.2: Biology applications

5.3: Condensed matter Physics applications

4.3: Study and deployment of Advanced Services

WP2: Building an eScience Network Community

2.2: Identifying industries, SMEs & international performers interested in Grid Infrastructures

2.1: Identifying researchers & RTD performers interested in Grid infrastructures

2.3: Relationships with other Projects

2.4: Sustainable Actions

6.5: EU-India GRID Portal Development & Mantainance

3.2: Network Support

4.4: Promote the development of existing and new grid Infrastructures in India

6.4: Follow-up activities

6.3: Training Events

3.1: Network connectivity plan

5.4: Earth and Atmospheric Sciences

Figure 6 - Interdependencies diagram

## Workpackage list (full duration of project)

| Work-package No | Work-package title | Lead contractor No | Person-months | Start month | End month | Deliverable No |
| --- | --- | --- | --- | --- | --- | --- |
| WP1 | Project administrative and technical management | 1 (INFN) | 26.2 (9.1) | M1 | M24 | D1.1 D1.2 D1.3 |
| WP2 | Building an eScience Network Community | 2 (MTW) | 23.4 (15.9) | M1 | M24 | D2.1 D2.2 |
| WP3 | Network Planning Support | 3 (GARR) | 28.0 (19.0) | M1 | M24 | D3.1 D3.2 D3.3 |
| WP4 | Pilot grid infrastructure operational support | 1 (INFN) | 84.9 (55.5) | M1 | M24 | D4.1 D4.2 D4.3 |
| WP5 | Applications | 1(INFN) | 155.9 (95.5) | M1 | M24 | D5.1 D5.2 D5.3 D5.4 D5.5 |
| WP6 | Dissemination & Networking Events | 2 (MTW) | 34.9 (31.4) | M1 | M24 | D6.1 D6.2 D6.3 D6.4 D6.5 |

## Deliverables list (full duration of the SSA)

| Del. No | Deliverable name | WP No | Lead Participant | Estimated person-months | Nature | Dissemination level | Delivery date (Proj. month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| D1.1 | Project presentation | WP1 | INFN | 2 | O | PU | M1 |
| D6.1 | The EU-IndiaGrid portal development | WP6 | MTW | 3,5 | O | PU | M2 |
| D6.2 | D6.2.1 Promotional brochures, D6.2.2 Workshop documentation (ppts, eventual proceedings) | WP6 | MTW | 2,2 | O | PU | M2 Ongoing |
| D6.3 | Training events materials | WP6 | ICTP | 13 | R | PU | M3, M12, M17, M23 |
| D5.1 | Specification and Requirements of applications | WP5 | INFN | 18 | R | PU | M3 |
| D3.1 | Status and perspectives of Network connectivity to India | WP3 | GARR | 8 | R | PU | M4 |
| D6.4 | Event Evaluation Reports | WP6 | MTW | 12,2 | R | PU | M4, M12, M17, M23 |
| D6.5 | Plan for using and Disseminating knowledge | WP6 | MTW | 3 | R | PU | M4, M12, M24 |
| D2.1 | EU-IndiaGrid Pan-European database (industry & research) | WP2 | MTW | 13,2 | O | PU* password access | M4 M24 |
| D4.1 | State-of-the-art in Security and Certification Authority preliminary report | WP4 | INFN | 11,9 | R | PU | M5 |
| D3.2 | Proposed Network connectivity roadmap | WP3 | GARR | 10 | R | PU | M8 |
| D5.2 | Integration of applications on the pilot grid infrastructure | WP5 | INFN | 33,1 | P | PU | M8 |
| D4.2 | CA and RA procedures and guidelines | WP4 | INFN | 20 | R | PU | M10 |
| D1.2 | First year progress report | WP1 | INFN | 10,2 | R | PU | M12 |
| D5.3 | First validation report for EGEE applications | WP5 | INFN | 48 | R | PU | M16 |
| D5.4 | Non-EGEE applications report | WP5 | INFN | 48,3 | R | PU | M18 |
| D4.3 | GARUDA Grid and EGEE interoperability report | WP4 | INFN | 53 | R | PU | M24 |
| D3.3 | Final report on Network provisioning and operation support | WP3 | GARR | 10 | R | PU | M24 |
| D2.2 | Sustainable Actions Reports | WP2 | MTW | 10,15 | R | PU | M24 |
| D1.3 | Final report | WP1 | INFN | 14 | R | PU | M24 |
| D5.5 | Final report on applications | WP5 | INFN | 8,5 | R | PU | M24 |
| D6.6 | Report on raising public participation and awareness | WP6 | MTW | 1 | R | PU | M24 |

### Milestones and expected results summary table (full duration of project)

| Milestone No | Work-package No | Milestone description | Date |
| --- | --- | --- | --- |
| M1.1 | WP1 | Kick-off meeting & nomination of Project Board Members | 1 |
| M6.1 | WP6 | EU-IndiaGrid portal fully operational | 2 |
| M3.1 | WP3 | Initial study of the network connectivity between Europe and India | 3 |
| M2.1 | WP2 | Database populated | 4 |
| M4.1 | WP4 | Policies and Certification Authority check | 6 |
| M4.2 | WP4 | First studies of Pilot Grid services interoperability | 8 |
| M2.2 | WP2 | Review of database population | 11 |
| M4.3 | WP4 | Operational support of advanced services achieved | 12 |
| M6.2 | WP6 | General EU-IndiaGrid Conference (India) | 16 |
| M5.1 | WP5 | Demonstration of Applications running on the intercontinental infrastructure | 18 |
| M2.3 | WP2 | Sustainable action definition | 23 |
| M1.2 | WP1 | Final Report | 24 |

## WORKPACKAGE DESCRIPTION (FULL DURATION OF PROJECT)

### Workpackage 1 description

| Workpackage number : |  | 1 | Start date or starting event: |  |  |  |  | M1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET |  | PUNE |  | SAHA |  | CDAC |  |  | BARC | TIFR |
| Overall effort in person/month per Participant: | 15,0 | 0,4 | 2,2 | 6,0 | 1,2 | 0,2 | 0,2 |  | 0,2 |  | 0,2 |  | 0,2 |  |  | 0,2 | 0,2 |
| EC-funded effort | 6,0 | 0,4 | 0,2 | 2,3 | 0,2 | 0,0 | 0,0 |  | 0,0 |  | 0,0 |  | 0,0 |  |  | 0,0 | 0,0 |
| Unfunded effort | 9 | 0 | 2 | 0 | 1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 |

Objectives The objective of this work package is the correct and effective coordination and management of the project, both in the technical and administrative areas. It will also follow the Community development management coordinating the participants contributions towards the common goal. It will follow also the interaction with related project and initiatives

Description of work - Administrative management (M1-M24): This activity will deal with the day-by-day administrative work necessary to maintain the project in good shape, to timely deliver and to match the milestones. - Technical management (M1-M24): This activity will be dedicated to coordinate the technical tasks of all the other work packages. By means of a Technical Manager and a Technical Board this activity will ensure the correct advancement of the work and the coordination of the activities carried out in the other 5 work packages. - Liaisons with related projects (M1-M24) This activity will follow the interaction with other projects relevant for EU-IndiaGrid, such as the major European and Indian Grid initiatives.

Deliverables D1.1 Project presentation M3 This deliverable will include all the necessary and relevant data to identify and present the project. D1.2 First year progress report M11 This report will summarize the overall proceeding of the project during the first year. D1.3 Final report M24 This report will summarize the overall proceeding of the project.

Milestones and expected result M1.1 Kick-off meeting & nomination of Project’s Boards Members (M1): this milestone marks the official start of the project activity and implementation of the Project Management Board. M1.2 Final Report (M24): this milestone marks the final report which will define the project in terms of its results, project coordination and project administration and summarise the results achieved.

### Workpackage 2 description

| Workpackage number : |  | 2 | Start date or starting event: |  |  |  |  | M1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET |  | PUNE |  | SAHA |  | CDAC |  |  | BARC | TIFR |
| Overall effort in person/month per Participant: | 0,0 | 7,2 | 2,2 | 4,0 | 0,0 | 2,0 | 2,0 |  | 1,0 |  | 1,0 |  | 2,0 |  |  | 1,0 | 1,0 |
| EC-funded effort | 0,0 | 7,2 | 2,2 | 4,0 | 0,0 | 1,0 | 1,0 |  | 0,0 |  | 0,0 |  | 0,5 |  |  | 0,0 | 0,0 |
| Unfunded effort | 0 | 0 | 0 | 0 | 0 | 1 | 1 |  | 1 |  | 1 |  | 1,5 |  |  | 1 | 1 |

Objectives The objective of this work package is to build an eScience Network Community, involving research Institutes and Industrial partners, which can profit from the EU-IndiaGrid infrastructure. This work package also includes liasing and synergising with related projects and initiatives.

Description of work T2.1 Community building identifying researchers & RTD performers interested in Grid Infrastructures or in eScience based on grid infrastructures This task includes the human networking activities necessary to complete and support the effective functioning of Research community. It will provide information for the development of the Pan-European database. RTD performers will be targeted and asked to register on the EU-IndiaGrid community portal (WP6.5). The task will establish the necessary contacts for the organization of the EU-IndiaGrid events (workshops and training). T2.2 Community building identifying industries, SMEs & international performers interested in Grid Infrastructures This task will deal with the identification and aggregation of existing Grid Infrastructure Industry Communities and forums and the gathering of other industrial players not already included in Research Infrastructure initiatives. It will provide information for the development of the Pan-European database. This grid infrastructure community will be targeted and asked to register on the EU-IndiaGrid community portal. The task will establish the necessary contacts for the organization of the EU-IndiaGrid events (workshops and training). T2.3 Synergies with related Projects & Initiatives Relationships with other projects (M0-M23): this activity will be dedicated to coordination with other related projects in the three connected areas: Network (GEANT, TEIN2), Grid (EGEE, India Grid), Dissemination & Support (BELIEF). T2.4 Sustainable Actions The goal of this task is to analyse appropriate means for seeking sustainability after the termination of the present EU-IndiaGrid initiative through the research and industry community building beginning from month 12 onwards. The general idea would be to continue the activities for a further 24 months.

Deliverables D2.1 EU-IndiaGrid Pan-European database (industry & research)) A community showcase of industrial & research players, including profiles & interests.; M4, M24. D2.2 Sustainable Actions report A report will indicate some potential ideas on how to sustain the EU-IndiaGrid initiative once the project has terminated. This activity will take place from month 12 to the end of the project.; M24.

Milestones and expected result M2.1; Database populated Contact strategies reviewed; M4. M2.2; Review of database population Contact strategies reviewed; M11. M2.3; Sustainable action definition; M23.

### Workpackage 3 description

| Workpackage number : |  | 3 | Start date or starting event: |  |  |  |  | M1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR |
| Overall effort in person/month per Participant: |  | - | 10 | - |  | - | 18 |  |  |  |  |  |
| EC-funded effort |  | - | 10 | - |  | - | 9 |  |  |  |  |  |
| Unfunded effort |  |  |  |  |  | - | 9 |  |  |  |  |  |

Objectives - Analyze the present and foreseen network connectivity plan between Europe and India and promote improvements in terms of bandwidth and network services. - Address the requirements of actual and potential grid users in India and provide them with adequate bandwidth and services. - Provide the EU-IndiaGrid community with adequate user support.

Description of work #### T3.1 – Network connectivity plan (Task Leader GARR) The task is intended to provide a plan in which, starting from the present status, the foreseen evolution of network connectivity and services will be described taking into account the EU-IndiaGrid applications and users special requirements. This activity will also liase with pertinent Organizations and Projects and perform appropriate lobbying activities (in synergy with task 1.3), in order to obtain the fulfilment of such requirements. #### T3.2 – Network support (Task Leader GARR) This activity will focus on ensuring that network performances and services are in line with the specific needs of the pilot applications and users receive adequate support in case of network malfunctioning, accidents, etc.

Deliverables D3.1 Status and perspectives of Network connectivity to India M04 This deliverable will describe the status and perspective of network connectivity between Europe and India. D3.2 Proposed Network connectivity roadmap M08 This deliverable will propose a roadmap to improve network connectivity D3.3 Final report on Network provisioning and operations support M24 This deliverable will summarize network provisioning and support activities for the whole project.

Milestones and expected result Initial study of the network connectivity between Europe and India M3

### Workpackage 4 description

| Workpackage number : |  | 4 | Start date or starting event: |  |  |  |  | M1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET |  | PUNE |  | SAHA |  | CDAC |  |  | BARC | TIFR |
| Overall effort in person/month per Participant: | 20 | - | - | - | 14.5 | - | 7.8 |  |  |  |  |  | 15 |  |  | 17.8 | 9.8 |
| EC-funded effort | 20 | - | - | - | 13.5 | - | 4 |  |  |  |  |  | 3 |  |  | 9.5 | 5.5 |
| Unfunded effort |  |  |  |  | 1 | - | 3.8 |  |  |  |  |  | 12 |  |  | 8.3 | 3.3 |

Objectives The objectives of this work package are: - Define the strategy for European and Indian Grids interoperability and provide an assessment about the key services - Define and agree the common security and authentication framework - Study and test of advanced services (grid monitoring, policy and resource brokering) in order to achieve a production quality infrastructure to be used by the applications

Description of work T4.1 - Establish GARUDA - EGEE interoperability Compare of GARUDA functional architecture and services with EGEE services and tools and ropose suitable solutions for the interoperability of the two (M1-M7) T4.2 - Define a common security and authentication framework Agree on the security policies with an Indian certification authority trusted from EU countries and trusting EU certification authorities. Carry out studies on the use of Virtual Organizations and related Grid tools in an Intercontinental environment. (M1 - M 24) T4.3- Operational support of advanced Services: monitoring, policy and accounting management Extend and support the usage of Advanced Grid tools in GARUDA making profit of the past experience of European partners and the acquired know-how of some Indian partners. Study grid monitoring tools and ensure a production quality service available to pilot and new applications (M1 - M24).

| Deliverables | Due on |
| --- | --- |
| D4.1 Common Security and Certification Authority This deliverable will present an overview of the state of the art for a common Security and CA tools. | M5 |
| D4.2 Guidelines for CA and RA procedures This deliverable gives detailed guidelines regarding CA and RA procedures and operation. | M10 |
| D4.3 GARUDA and EGEE interoperability report This report will present the state of the GARUDA and EGEE interoperability and summarise the final assessment of infrastructure operations. | M24 |

| Milestones and expected result | Due on |
| --- | --- |
| M4.1 Policies and Certification Authority check. This milestone marks the final check about policies and CA operation. | M6 |
| M4.2 First studies of Pilot Grid services interoperability. This marks the point where the initial studies of services interoperability is completed over a Pilot Grid infrastructure. | M8 |
| M4.3 Operational support of advanced services achieved. This marks the point where the Operational support of Advanced Services is achieved and a production service is available for applications. | M12 |

### Workpackage 5 description

| Workpackage number : |  | 5 | Start date or starting event: |  |  |  |  | M1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET |  | PUNE |  | SAHA |  | CDAC |  |  | BARC | TIFR |
| Overall effort in person/month per Participant: | 7 | 0,0 | 0,0 | 19 | 8,5 | 36,8 | 0,0 |  | 34,8 |  | 36,8 |  | 5,0 |  |  | 0,0 | 8,0 |
| EC-funded effort | 7 | 0,0 | 0,0 | 19 | 7,5 | 18,5 | 0,0 |  | 18 |  | 19 |  | 2,5 |  |  | 0,0 | 4,0 |
| Unfunded effort | 0,0 | 0,0 | 0,0 | 0,0 | 1 | 18,3 | 0,0 |  | 16.8 |  | 17.8 |  | 2,5 |  |  | 0,0 | 4,0 |

Objectives The objective of this work package is to validate the Intercontinental EU-India Infrastructure using EGEE applications and to support the porting of new applications relevant for the eScience and Industrial collaboration between Europe and India.

| Description of work T5.1 – High Energy Physics Applications (Task leader: INFN) Support the operation of EGEE applications on the Intercontinental infrastructure to validate it. T5.2 – Biology applications (Task Leader: CAM). Use GILDA to test and integrate applications. Give support to use high level user interfaces using GENIUS. Support the operation of the applications on the final intercontinental infrastructure. T5.3 – Condensed matter physics applications (Task leader: ICTP). Port and integrate scientific packages for condensed matter community on the computational grid environments. Support the operation of the applications on the intercontinental infrastructure and validate it. T5.4 – Application for Earth and Atmospheric Science (Task leader: CDAC). Attempt to port and integrate in unique workflow earth science application and atmospheric application in both GARUDA and the intercontinental infrastructure and validate it. Deliverables |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | D5.1 | Specification and Requirements of applications This deliverable has the goal to define, on the basis of a former analysis, a set of requirements and specifications needed for the applications deployment on the grid infrastructure. | M03 |  |
|  | D5.2 | Integration of applications on the pilot grid infrastructure This deliverable has the goal to support the integration of the applications within the pilot grid infrastructure. | M08 |  |
|  | D5.3 | First validation report for EGEE HEP applications This deliverable will represent the first report on the validation activity performed by the EGEE applications (mainly HEP) on the pilot grid infrastructure. | M16 |  |
|  | D5.4 | Non-EGEE applications deployment report This deliverable will represent the first report on the validation activity performed by the non EGEE selected applications on the pilot grid infrastructure, namely Biology applications and condensed matter applications and earth science and atmospheric science. | M18 |  |
|  | D5.5 . | Final report on applications This deliverable will represent the final report on the validation activity performed by all the applications on the global grid infrastructure | M24 |  |

Milestones and expected result Month 18 - Demonstration of Applications running on the intercontinental infrastructure: marking the organization of public demos on the intercontinental Grid infrastructure. It will be performed in conjunction with an event organized in the framework of WP6.

The following table will contain some useful  metrics to assess the progress made within WP5

throughout the course of the project. The metrics are sketched in this moment and it is difficult to

evaluate such in advance the validity of them: it is likely that some of these indicators may be

completely change and be subequently revised during the 24 months of the project.

| metrics | 12 months | 24 months |
| --- | --- | --- |
| Average number of research groups using grid applications belonging the four group of activities | 2 | 4 |
| average number of different applications running on the GRID for each application sector | 1 | 3 |
| average number of CPU hours for each group of application on the intercontinental infrastructure | O(103) | O(104) |

### Workpackage 6 description

| Workpackage number : |  | 6 |  | Start date or starting event: |  |  |  | M1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participant: | INFN |  | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR |
| Overall effort in person/month per Participant | 6,4 |  | 10,5 | 0,0 | 11,0 | 0,0 | 0,0 | 0,0 | 2,0 | 0,0 | 5,0 | 0,0 | 0,0 |
| EC-funded effort | 6,4 |  | 10,5 | 0,0 | 11,0 | 0,0 | 0,0 | 0,0 | 1,0 | 0,0 | 2,5 | 0,0 | 0,0 |
| Unfunded effort | 0 |  | 0 | - | 0 | - | - | - | 1.0 | 0 | 2.5 |  |  |

Objectives The objective of this work package is to provide the organizational, promotional dissemination and outreach activities associated with communicating the grid infrastructure. The work package will concentrate on organizing a series of focused networking activities to enhance the developments of an Euro-Indian e-Science grid community including: - developing 3 international focused workshops: (1 on High Energy Physics, Biology and Medical area, 1 on Condensed Matter Physics and Material Sciences area, 1 on Earth Sciences area) and 1 Project Conference focusing on general grid infrastructure and industrial applications. Due to the disciplinary structure, the workshops are predominantly academic but may attract significant industrial interest. The events may be organized in academic environments of the partners, which would minimize logistic expenses. - 4 major training events intended to provide to interested institutions an opportunity for an in-depth evaluation of the grid technologies with respect to the applications run by the interested academic and industrial entities; these events will include case studies of existing European or Indian porting of applications to grid, and extensive hands-on practice, intended to experiment the porting of the applications of the participants to the European grid testbed GILDA. They will be held in India, and, whenever possible, be associated to the workshops or with other related events going on at the same time. - A number of shorter Training Exposure events, associated to events organized in India by other European or Indian projects in related subjects. These short events will mainly consist in demo sessions of the European grid infrastructure and of applications running on it (See Appendix A.5) The workshop events are envisaged as informal and highly-interactive and collaborative functions in which qualified European and Indian participants from diverse backgrounds will be invited. The workshops will be one-to-two-day events that will attract ICT professionals on Grid Infrastructures from a wide pool of researchers, users, enterprises, government. The issues that these events will tackle are not only technical but will include managerial, economic, and policy-related issues, highlighting as well the developments in the two countries. The training events will be addressed to research or industrial groups willing to explore in detail the possibility of adopting the European grid technologies to run their existing applications. They will last from 2 up to 5 days (depending on the circumstances and audience) and involve the presentation of some case studies from the relevant field, and an extensive porting laboratory where the staff from the participating institutions will be assisted in porting their applications or parts thereof and validating them onto the European grid, using the GILDA or the EU-IndiaGrid testbeds. To support the dissemination of information on the activities of the project and of the grid e-Science and industrial communities, and to provide a consistent and traceable environment for the follow-up of the project activities, this workpackage will also develop and operate a Portal that will be used by all the activities of the project.

Description of work T6.1 Promotion & Dissemination Activities - Task Leader Metaware This task will concentrate on both participants and speaker & trainer recruitment as well as widespread marketing of the project activities. Promotion of the EU-IndiaGrid initiative is fundamental for project success, the events will be targeted according to different communities, keeping in mind cultural differences and geographic locations. Consortium links and relationships with European and worldwide multiplier associations will be leveraged for dissemination purposes as well as to attract, support, and recruit speakers, trainers & participants. Media relations will be established in Europe and India and announcements, articles, kits, and materials produced and delivered in conjunction with major project milestones. T6.2 International Workshops - Task Leader Metaware Four international workshops (M3, M11, M16, and M22) will be planned and organized in conjunction with international grid pertinent events, leveraging on existing participants. These workshop will focus each on a homogeneous disciplinary area, (High Energy Physics, Condensed Matter Physics and Material Science, Biomedical applications, Earth Sciences and disaster prevention, and will allow sharing of information and results of grid Infrastructure projects such as: EGEE-II, GEANT2, SEE-GRID2, as well as EU-IndiaGrid pilot application developments and results. More importantly they will help cross-fertilization of individual approaches and stronger interaction of the players involved. The event secretariat will be responsible for the on-site management and coordination of participant material T6.3 Training Events - Task Leader ICTP This task is devoted to the implementation of a set of training events (M2, M11, M16, and M22) intended to assist the research institutions and industrial entities contacted in WP2 to evaluate fully the benefits of the grid infrastructures, by assisting them in the porting of their applications (or of parts or evaluation versions of their applications) to the EU-IndiaGrid testbeds. These events, expected to last from 2 to 5 days, and with a large hands-on component, will be associated when possible to the workshops of T6.2 and will address the same disciplinary areas. In addition, shorter Training Exposure events will be associated to initiatives in related fields organized in India by other European projects (see Appendix ) or by Indian partners. T6.4 Follow-up activities and evaluation of events - Task Leader ICTP Following each workshop/training event, feedback collected from the participants will be analysed in order to verify the benefits gained to learn lessons for the subsequent workshops. In addition these evaluations will help obtain preliminary information on knowledge sharing experiences, improve cooperation opportunities, proposal preparation and future planned activities. A concise follow-up and evaluation document of results will be compiled for each of the events. The lectures and a full technical report of application porting activity performed within the T6.3 training activities will be posted on the EU-IndiaGrid portal and circulated among the communities identified in WP2. Follow-up support will be offered to trainees, both in porting their applications to the grid and in disseminating grid knowledge at their institutions; in order to consolidate their interest in the grid. T6.5 EU-IndiaGrid Portal Development & Maintenance – Task Leader Metaware The EU-IndiaGrid portal, with a Content Management System (CMS), web communication tool of the project will be set-up, developed, and maintained. The portal will define the EU-IndiaGrid Initiative identity and it will be organised to effectively function as the reference point and communication hub for the ICT EU-IndiaGrid community developed in WP2. This Open Source Software based interactive portal will include a forum, event management tools and will provide access to the grid submission and control environments developed in GILDA. The EU-IndiaGrid Community showcase will be an important facility for the workshop and training promotion as well as community creation and building.

Deliverables D6.1 The EU-IndiaGrid portal development. A Communication platform consisting of front/back office a CMS system, on-line registration facilities & EU-IndiaGrid community showcase (WP2), eScience & e-Infrastructure information, pilot applications progress & results, exploitation and dissemination material, etc.; M2. D6.2 Promotional Material. D6.2.1, Project brochures, flyers and press material. D6.2.2 Workshop documentation (ppts, eventual proceedings). A set of electronic and hardcopy promotional materials to raise awareness as well as maintain and increase the user community.; M2 (evolving throughout duration of project). D6.3 Training events materials and reports(*). Electronic and hardcopy materials, where appropriate, constituting the instructional part of the training events plus reports of the application porting laboratory, as well as recommendations towards further activities and follow-ups; M3, M12, M17, M23 (After completion of each event). D6.4 Workshops and ConferenceEvaluation Reports(*). Events on M3 and M11 will be associated to BELIEF activities in New Delhi and Dublin. Reports summarising the International workshops as well as including recommendations, conclusions and follow-up steps as a result of the events.; After completion of each event (M4, M12, M17, M23). D6.5 Plan for using and Disseminating knowledge (Preliminary and Final). These reports will outline the participants’ actual achievements in dissemination and plans for exploitation of the results.; M4, M12, M24. D6.6 Report on raising public participation and awareness This report is mandatory and gives an overview of how the consortium has tackled raising awareness.; M24. (*) The consortium will explore the possibility of associating its activities with initiatives from other institutions. In addition, the consortium is aware of other projects which may organise events and where it could be appropriate to include EU-IndiaGrid workshop as a piggy-back event. (E.g.: the EGEE-II Industry days which are organised every two months, which are domain-specific and organised in different European countries could be a good participating event for the project). As a consequence, the dates of some of the deliverables could be changed

Milestones and expected result M6.1; EU-IndiaGrid portal fully operational.; M2. M6.2; General EU-IndiaGrid Conference (India). Evaluation of status of dissemination activities; M16.

Measurable Impact for WP6

The following table provides a set of indicators that may be used as a provisional outline to track the progress of WP6.

the figures will be monitored continuously and revised according to the results achieved.

| Description | 12 months | 24 months |
| --- | --- | --- |
| Number of participants to extended training events | 60 | 140 |
| Number of participants to shorter training events | 40 | 120 |
| Number of participants to planned ‘training exposure events’ | 160 | 160 |
| Training events organized by non-partners, as a consequence of taking part in the planned training activities, and supported by Consortium | 2 | 8 |
| average number of different scientific macroarea participants come from | ~5 | ~8 |
| average number of different research groups attending the tutorial | ~10 | ~25 |
| GILDA certificates issued | 100 | 250 |
| Number of participants to workshops | 165 | 400 |

Geographical Representation on the website from participation to the focused and general events

| Description |  | 12 months | 24 months |
| --- | --- | --- | --- |
|  | European Researchers | 37 | 70 |
|  | Indian Researchers | 90 | 163 |
|  | European Industry | 32 | 66 |
|  | Indian Industry | 41 | 86 |
|  | New European User Profiles | 45 | 60 |
|  | New Indian User Profiles * | 80 | 115 |
|  | Total | 325 | 560 |

*The consortium will aim to attract new user profiles to the project by taking advantage of materials produced in other projects (such as the Research & Industry Handbook produced in BELIEF) to attract new users, especially Indian industry.

# Project resources and budget overview

## Efforts for the project

All the partners funded efforts are summarized in the following table (SSA Effort Form).The unfunded efforts are explicitly shown in the WP forms in chapter 7.6 and in the table below.

All partners are fully committed to the project and give contributions outside the EC contributions. In particular INFN, GARR, ICTP, Cambridge,  and Metaware contribute, with additional resources and time from their staff to the project management and coordination. All the Indian partners provide unfunded contribution in Person-Months (PM) at the same level of the corresponding EC funded PM contribution for the activities where they are involved.

Specific Support Action Effort Form – Full duration of project (Person Months)

| EU-IndiaGrid Effort |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR | TOTAL ACTIVITIES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | (IT) | (IT) | (IT) | (INT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) |  |
| Activities specific for the Support Action |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 | Total | 0,0 | 7,2 | 2,2 | 4,0 | 0,0 | 2,0 | 2,0 | 1,0 | 1,0 | 2,0 | 1,0 | 1,0 | 23,4 |
|  | Funded | 0,0 | 7,2 | 2,2 | 4,0 | 0,0 | 1,0 | 1,0 | 0,0 | 0,0 | 0,5 | 0,0 | 0,0 | 15,9 |
| WP3 | Total | 0,0 | 0,0 | 10,0 | 0,0 | 0,0 | 0,0 | 18,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 28,0 |
|  | Funded | 0,0 | 0,0 | 10,0 | 0,0 | 0,0 | 0,0 | 9,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 19,0 |
| WP4 | Total | 20,0 | 0,0 | 0,0 | 0,0 | 14,5 | 0,0 | 7,8 | 0,0 | 0,0 | 15,0 | 17,8 | 9,8 | 84,9 |
|  | Funded | 20,0 | 0,0 | 0,0 | 0,0 | 13,5 | 0,0 | 4,0 | 0,0 | 0,0 | 3,0 | 9,5 | 5,5 | 55,5 |
| WP5 | Total | 7,0 | 0,0 | 0,0 | 19,0 | 8,5 | 36,8 | 0,0 | 34,8 | 36,8 | 5,0 | 0,0 | 8,0 | 155,9 |
|  | Funded | 7,0 | 0,0 | 0,0 | 19,0 | 7,5 | 18,5 | 0,0 | 18,0 | 19,0 | 2,5 | 0,0 | 4,0 | 95,5 |
| WP6 | Total | 6,4 | 10,5 | 0,0 | 11,0 | 0,0 | 0,0 | 0,0 | 2,0 | 0,0 | 5,0 | 0,0 | 0,0 | 34,9 |
|  | Funded | 6,4 | 10,5 | 0,0 | 11,0 | 0,0 | 0,0 | 0,0 | 1,0 | 0,0 | 2,5 | 0,0 | 0,0 | 31,4 |
| Total 'specific activities' | Total | 33,4 | 17,7 | 12,2 | 34,0 | 23,0 | 38,8 | 27,8 | 37,8 | 37,8 | 27,0 | 18,8 | 18,8 | 327,1 |
|  | Funded | 33,4 | 17,7 | 12,2 | 34,0 | 21,0 | 19,5 | 14,0 | 19,0 | 19,0 | 8,5 | 9,5 | 9,5 | 217,3 |
| Consortium management activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP1 | Total | 15,0 | 0,4 | 2,2 | 6,0 | 1,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 26,2 |
|  | Funded | 6,0 | 0,4 | 0,2 | 2,3 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 9,1 |
| TOTAL consortium management | Total | 15,0 | 0,4 | 2,2 | 6,0 | 1,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 0,2 | 26,2 |
|  | Funded | 6,0 | 0,4 | 0,2 | 2,3 | 0,2 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 0,0 | 9,1 |
| TOTAL per PARTECIPANT | Total | 48,4 | 18,1 | 14,4 | 40,0 | 24,2 | 39,0 | 28,0 | 38,0 | 38,0 | 27,2 | 19,0 | 19,0 |  |
|  | Funded | 39,4 | 18,1 | 12,4 | 36,3 | 21,2 | 19,5 | 14,0 | 19,0 | 19,0 | 8,5 | 9,5 | 9,5 |  |
| Overall TOTAL EFFORTS | Total |  |  |  |  |  |  |  |  |  |  |  |  | 353,3 |
|  | Funded |  |  |  |  |  |  |  |  |  |  |  |  | 226,4 |

031834 (EU-IndiaGrid) SSA Project Effort Form - Full duration of project

In order to clarify the budget evaluation the PM cost for all participants is reported below together with the overall budget evaluation for personnel and other costs (funded and unfunded).

| Personnel Cost per month |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | (IT) | (IT) | (IT) | (INT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) |  |
|  |  | 5000 | 5250 | 5000 | 2300 | 4300 | 1000 | 1960 | 1000 | 1000 | 2556 | 1000 | 1000 |  |
| Overall Personnel Cost |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR |  |
|  |  | (IT) | (IT) | (IT) | (IT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) |  |
|  | Total | 242000 | 95025 | 72000 | 92000 | 104060 | 39000 | 54868 | 38000 | 38000 | 69518 | 19000 | 19000 |  |
|  | Funded | 197000 | 95025 | 62000 | 83490 | 91160 | 19500 | 27434 | 19000 | 19000 | 21724 | 9500 | 9500 |  |
| of which WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total | 75000 | 2100 | 11000 | 13800 | 5160 | 200 | 392 | 200 | 200 | 511 | 200 | 200 |  |
|  | Funded | 30000 | 2100 | 1000 | 5290 | 860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Other Costs |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR |  |
|  |  | (IT) | (IT) | (IT) | (INT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | TOTAL |
| Travel |  | 20000 | 16000 | 3000 | 22300 | 7000 | 3500 | 3900 | 4000 | 4000 | 4000 | 4000 | 4000 | 95700 |
| Audits |  | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 24000 |
| Subcontracting |  |  |  |  | 18310 |  |  |  |  |  |  |  |  | 18310 |
| Externals |  | 10000 | 9000 |  | 18800 |  |  |  |  |  | 19500 |  |  | 57300 |
| Overhead |  | 45800 | 61013 | 13400 | 25318 | 20032 | 5000 | 6667 | 5000 | 5000 | 9445 | 3100 | 3100 | 202874 |
| Total EC Contribution |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR | TOTAL |
|  |  | (IT) | (IT) | (IT) | (INT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) |  |
|  | Funded | 274800 | 146430 | 80400 | 170218 | 120192 | 30000 | 40001 | 30000 | 30000 | 56669 | 18600 | 18600 | 1015910 |
| of which WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Funded | 42000 | 4520 | 3200 | 8348 | 3032 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 75100 |
| excluded WP1 | Funded | 232800 | 141910 | 77200 | 161870 | 117160 | 28000 | 38001 | 28000 | 28000 | 54669 | 16600 | 16600 | 940809 |
| Total Project Effort |  | INFN | MTW | GARR | ICTP | CAM | NCBS | ERNET | PUNE | SAHA | CDAC | BARC | TIFR | TOTAL |
|  |  | (IT) | (IT) | (IT) | (INT) | (UK) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) | (IN) |  |
| Funded + Unfunded |  | 319800 | 183038 | 90400 | 178728 | 133092 | 49500 | 67434 | 49000 | 49000 | 104463 | 28100 | 28100 | 1280654 |
| Unfunded |  | 45000 | 36608 | 10000 | 8510 | 12900 | 19500 | 27434 | 19000 | 19000 | 47793 | 9500 | 9500 | 264745 |

## Overall budget for the project

(FORMS A3.1 & A3.2 from CPFs)

## Management level description of resources and budget

Following the recommendations of the ESR, the consortium has strengthened the Grid Expertise from Indian partners with the introduction of C-DAC, BARC and TIFR Mumbai.  The total budget has been kept unchanged moving resources from INFN and Metaware to the new partners. In this way the consortium has granted the cooperation of the Indian National Grid Computing Initiative, initiated and supported by C-DAC, with the involvement of most of the Indian partners of the Consortium. In addition C-DAC will be involved in the Dissemination workpackage activity and will contribute to the involvement of new applications.

Here below we detail the effort for all WPs.

### WP1 - Project administrative and technical management

7% of the overall requested EC funding is assigned for the overall project management. INFN leads this management work package, with support from ICTP and those two organisations have the largest percentage of resources. Moreover, these institutes, together with GARR and Cambridge, will provide an additional unfunded effort for the project coordination. For all other partners, the management activities are proportional to the amount of work allocated to the partner and complexity of management related to this work.

The overall management effort will be complemented by the support of administrative and legal services of the coordinating partner and the consortium partners.

### WP2 –Building an eScience Network Community

This work package foresees 23 Person Months (PM) effort (7.5 unfunded) over the lifetime of the project to perform the community building, synergising, and sustainability tasks. The request contribution will be used to help identify, collect, and develop a community building of RTD & Industrial performers. Effort will be required by the majority of European partners to access and contact their RTD networks and industrial networks to maximise visibility and gain support from interested actors in the development of the e-Infrastructure initiative. Synergies with other European initiatives are given a significant weight as they are essential for the visibility of the project.

### WP3 –Network Planning and Support

This work package will be lead by GARR with the contribution of ERNET. An evaluation of the effort necessary for this activity amounts to 28 Person Months. Salary expenses of technical staff involved in the network planning and user support mainly justify the expected budget. Moreover, a small amount of the financing requested is intended to cover travel expenses to attend technical meetings related to the activities of the work package.

### WP4 – Pilot grid infrastructure

The financing request is justified to define the EU-IndiaGrid interoperability, test, and support of operational services  to have a managed Grid infrastructure, including  authorization Grid services and advanced services. Those services implementations (overall the authentication Certification Authority) are fundamental to support the operation of a  reliable and robust Grid infrastructure, defining  the basis for the employment of advanced services to facilitate the integration of application defined in WP5. INFN will lead this work package with a person almost full time (20 PM). Cambridge collaborates with a funded effort of  7.5 PM while the Indian partners (C-DAC, ERNET, BARC,TIFR) contribute with a substantial effort: 51 PM (29 unfunded). The total PM effort on this work package is 85 PM and will ensure the EU-IndiaGrid interoperability, monitoring,   and operation of the infrastructure.

### WP5 –Applications

This WP is important to show the power of grid computing to the new communities in the project. The resources are allocated mainly to the partners strongly involved in the applications support and development and to the partners with experience in supporting communities in application porting on the grid. INFN will coordinate the HEP applications porting on GARUDA and the intercontinental infrastructure. The global effort for this first task is estimated in 7 PM for INFN and 37 PM (half of that unfunded) for the Indian partner (SAHA). Cambridge University  will focus on support for Biological application (for a total of 7.5 month/person) in close collaboration with NCBS Indian partner that will participate in this activity with 37 PM (half of that unfunded). Finally, ICTP will be involved in porting the Condensed Matter applications in close collaboration with Pune University and the Atmospheric physics applications in cooperation with CDAC.  ICTP allocates for this task 12 PM while the effort at Pune University will be more consistent: 35 PM (18 unfunded). C-DAC, in close collaboration with the Physics of Weather and Climate Group at ICTP will follow the porting of applications in the field of environmental sciences. This activity requires a little effort for C-DAC (5 PM, 2,5 unfunded ) while the activity at ICTP requires 7 PM.

### WP6 – Dissemination and Networking events

The 35 PM, the internal and external resources and travel costs are finalised to hold the international networking and training events both in India and Europe. Subsidised amounts have been set aside to invite guest speakers to conferences. All catering, conference documentation, and exhibition costs have been included.

## Materials and facilities

One important facility, which will be available in the project, is GILDA. GILDA consists of the following elements:

The GILDA Test-bed (https://gilda.ct.infn.it/testbed.html); it consists of several academic and “commercial” sites and contains all the most relevant Grid services such as Resource Broker, Information Index, Replica Location Service, etc.;

The Grid Demonstrator (https://grid-demo.ct.infn.it); a reduced version of the GENIUS grid portal that everyone can use to submit to the GILDA Test-bed a pre-defined set of demonstration applications;

The GILDA Certification Authority (https://gilda.ct.infn.it/CA); a real Certification Authority which issues in quasi-real-time way both personal (two-weeks life time) and server (one year) digital certificates;

The GILDA Virtual Organisation; a Virtual Organisation which includes all people wanting to use GILDA;

The Grid Tutor (https://grid-tutor.ct.infn.it); a full fledged version of the GENIUS grid portal to be used during tutorials, induction courses, and outreach events in general;

The GILDA Monitoring System (https://alifarm7.ct.infn.it/gridice/site/site.php); based on the GridICE tool from INFN, it can give different “views” of GILDA as function of both sites and VO’s;

The GILDA Mailing List; gilda@infn.it archived on the web at http://server11.infn.it/archive-gilda/.

On the GILDA home page links to detailed instructions on how to join GILDA both as single users and entire sites are also available. Instructions are given both as written web documents and video-tutorials (https://gilda.ct.infn.it/video.html) for self-teaching.

GILDA’s key advantages are the following:

GILDA uses INFN Grid middleware (http://grid-it.cnaf.infn.it), which is fully compatible with the middleware deployed on EGEE infrastructure. Middleware used by the INFN Grid and EGEE infrastructure differs only in a few services;

Users only need a certificate to access GILDA. This certificate, delivered by INFN, is valid for 2 weeks;

The GENIUS grid portal allows quick deployment of new applications.

By its nature, then, GILDA is one of the key enablers of the “virtuous cycle” set-up in the EGEE Project to attract and support new communities. In fact:

A novice user can get the feeling of what is grid computing and which applications can run on a grid infrastructure simply using the Grid Demonstrator which is available around the clock;

An interested user participating in a tutorial event or an induction course, can go through all the mandatory procedure of the request of a personal digital certificate and subscription to a VO and then use the Grid Tutor;

A community that is interested in testing the grid can join GILDA and try to port its applications on its test-bed, thus solving, on a smaller scale, all problems related to interfacing with grid services before entering the huge EGEE infrastructure;

The various applications from different communities ported on GILDA can be incorporated into the Grid Demonstrator, thus enriching the portfolio of examples that can be demonstrated to newcomers;

A site, which needs to set-up a computing, or a storage resource for a grid infrastructure can join GILDA in the short term and solve, on a smaller scale, all the problems of installation and proper configuration of the machines.

Up to now, GILDA has been used in more than 120 demonstrative events and induction courses. A continuously updated list of the tutorials given using GILDA is available at https://gilda.ct.infn.it/tutorials.html.

The GILDA web site has received more than 1,500,000 hits from tens of different countries in the world. Detailed statistics, continuously updated, can be found at https://gilda.ct.infn.it/usage.

Another  tool of great interest for the project is the EGRID Live CD.

The EGRID <http://www.egrid.it/> Live CD is a Knoppix <http://www.knopper.net/knoppix> Live CD derivative that comes preloaded with all the LCG-2 middleware (gLite in next edition). One can therefore run all of LCG-2 Grid elements off the live CD, without even installing on the hard-drive. A menu-driven configuration interface makes it easy to configure and run Grid elements, without having to delve into the intricacies of LCG-2 configuration. Eventually, if so requested, the Knoppix <http://www.knopper.net/knoppix> installer will install Debian GNU/Linux and the LCG-2 middleware on the hard-drive, preserving configuration.

The LIVECD is very interesting tool for dissemination and outreach. New and perspective users are often overwhelmed by the amount of technical details they have to master /before/ they can install a Grid site. Also, hardware resources are sometimes a concern --especially at smaller sites and in developing countries-- where only limited resources are available, even for production use.

The EGRID <http://www.egrid.it/> Live CD tries to solve this problems by giving people a means of trying the LCG-2 software in a snap: no OS reinstallation, no need to configure parameters. This tool can be therefore fundamental to help attendees of the four training events to easily set up small training events once back home. We plan to have a close interaction with GILDA Testbed: the Egrid LiveCD will be therefore equipped with specific parameter to easily join the GILDA testbed: in this way any attendee can easily set up a local site (or at least an UI) on the fly to run small the same demo he/she assisted during the official training events.

## Travels

With a major objective to build a human network and transfer knowledge via outreach events, the SSA will require a considerable amount in travel and subsistence costs.

The participation in the different workshops, as well as carrying out promotional activities, will be required from all European partners. Travel costs may increase for partners if any of the destinations do not have direct flights, which would involve an extra night of accommodation. Travel costs will be incurred for promoting the project at relevant events in Europe and internationally. The travel to the beneficiary country is seen as a facilitator for project work and crucial for dissemination and creation of the human network. The project during its execution will try to minimize those costs by implementing means of collaboration using electronic networks. Nevertheless, with a number of events organized by the project the amount will not be negligible.

# Other issues

## Ethical issues

EU-IndiaGrid will collect information on scientific organisations and industries as well as individuals in relation to the three workshops and four training events organised, and the membership of the EU-IndiaGrid Community Portal. All partners will abide to national data protection laws. Online forms will comply with EU law with respect to the proposed uses of any personal information provided. Information will be primarily used to help identify industries and scientific communities with an interest in research cooperation or exploitation of ICT related research results based on their profile, skills and experience.

In accordance with the Data Protection Directive, 95/46/EC of the European Parliament and of the Council of 24 October 1995 on the protection of individuals with regard to the processing of personal data and on the free movement of such data, the consortium will not disclose personal details to third parties without prior consent from the individuals concerned. Such personal information will be stored in a secure, encrypted database. In general, registered members of the EU-IndiaGrid Community Portal will be responsible for keeping their organisational and personal data up to date, and as part of the self-service publishing functionality of the portal, can choose what information to publish and what is to remain private.

Other than Data Protection, there are no ethical issues associated with EU-IndiaGrid.

## Gender issues

As established in Articles 2 and 3 of the Treaty of Rome the equality between women and men is a specific task of the European Community, as well as a horizontal objective affecting all Community tasks. The Treaty seeks not only to eliminate inequalities, but also to promote equality.

EU-IndiaGrid will raise awareness, in Research, Industry & Education fields that the different perspectives of males and females can be of particular benefit and importance to Research Infrastructure activities, as well as gender dimensions to be considered in the development of the knowledge based society.

All organisations involved in the EU-IndiaGrid project are equal opportunity employers or actively safeguard gender equality. That means that all employees should have equal opportunity for employment and advancement on the basis of their ability, qualifications and suitability for the work. No job applicant or employee receives less favourable treatment in any aspect of employment on gender, or furthermore, on the grounds of racial, religion, disability, marital status, age or sexual orientation and caring responsibilities or be disadvantaged by conditions or requirements which cannot be shown to be justifiable.

In particular, within the EU-IndiaGrid consortium there is good gender balance, with women in a number of partners (INFN, GARR, MTW, ERNET ) taking responsibility as either Task or Workpackage Leaders.

As part of the EU-IndiaGrid workshop and training events which will take place in the different countries, the partners will ensure that there is adequate discussion on challenges women in Industries face in participation in RTD or access to and use of the Grid e-Infrastructure in their daily working lives, and to suggest ways in which these challenges can be overcome to help women fully gain more opportunities for social and economic empowerment which Grid e-Infrastructure enables.

## Policy issues

In the foreword to Science and Society Action Plan (2002) the Commissioner for Research Mr. Philippe Busquin denounced that “only half of the Europeans consulted said that they were interested in science and many of them consider themselves to be poorly informed.” The communication issue resulted to be fundamental in research projects since many of them results to give poor feedback in social impact other than in commercial exploitation. A strong communication skill and a clear strategy are required when deep impact is required for a research initiative.

During the last years this need has been addressed in some way. See, for instance, the new feature of the 2004 Descartes Prize where, for the first time, awards were given not only for scientific research but also for projects aimed at promoting the understanding of scientific progress and its implications.

The EU-IndiaGrid dissemination and promotion activities will contribute in the direction foreseen by the action plan, opening the discussion at wider public in the conferences and creating bi-directional relations between industries, scientific communities, governments and research institutions.

Appendix A - consortium description

## a.1 Participants and the consortium

P01 – (Coordinator) – Istituto Nazionale di Fisica Nucleare (Italy) - INFN

P02 –Metaware

P03 – Consortium GARR (Italy) – GARR

P04 –International Centre for Theoretical Physics

P05 –Cambridge University

P06 – Tata Institute for Fundamental Research Mumbai, India

P07 –ERNET India

P08 –Pune University, India

P09 –SAHA Institute Calcutta, India

P10 – Centre for Development of Advanced Computing, Bangalore, India

P11 – Bhabha Atomic Research Centre

## A1.1 Preliminary table of Leaders

| WP1 | Project administrative & technical management – WP Manager: Alberto Masoni (INFN) |
| --- | --- |
| Administrative management PM: Alberto Masoni (INFN) Technical management TM: Stefano Cozzini (ICTP) |  |
| WP2 | Building an eScience Network Community - WP Manager: Douglas McKinley (Metaware) |
| WP3 | Network planning support - WP Manager: Marco Marletta (GARR) |
| WP4 | Pilot infrastructure support - WP Manager: Sergio Fantinel (INFN) |
| WP5 | Application support - WP Manager: Marco Verlato (INFN) |
| WP6 | Dissemination and networking events - WP Manager: Stephan Benians (Metaware) |

## P01 - Coordinator -  Istituto Nazionale di Fisica Nucleare (Italy) - INFN

### Profile

INFN is the Italian National Institute of Nuclear and Particle Physics (see http://www.infn.it). Founded in 1952, INFN is a governmental research organization, which promotes, co-ordinates and funds nuclear, particle and high-energy physics research. It is organised in 4 National Laboratories, 19 Departments (called Sections) and 11 Local Groups which operate in strong synergy with the Physics Departments at all the major Italian Universities (see http://www.infn.it/mappa.php). INFN staff research personnel amounts to more than 1500 peoples with an equivalent number of associates from University and other Scientific National Institutes.

INFN has a long tradition of dissemination and training, dedicated both to the scientific community and to the general public. Since several years INFN has a Technology Transfer Committee (http://www.infn.it/ctt) which is responsible for demonstrating and communicating to society, especially including school and industry, the scientific results achieved by the INFN activities and the possible spin-off activities. Along with the Technology Transfer Committee, INFN also manages a Committee for the Transition to the New Computing Technologies (see http://www.infn.it/cntc) which periodically organizes training courses and demonstration events.

INFN is one of the founding members of GARR, the Italian academic and research network.

INFN carries on high performance distributed computing activities since the beginning of 1998 when a nation-wide Condor Pool has been set up (see http://www.infn.it/condor) and started the oldest National Grid Project in Europe (see http://www.infn.it/grid), back in the fourth quarter of 1999, with the aim of building a national grid infrastructure which could exploit as much as possible its geographically “distributed” nature. In the year 2000 INFN performed a deep evaluation of the Globus Toolkit (see http://www.infn.it/globus) and, from 2001 to 2003, was involved in the EU DataGrid and DataTAG Projects as main contractor. Since the last quarter of 2002 INFN also has a leading role in the National Grid Project called GRID.IT (see http://server11.infn.it/firb-grid) aiming at building an Italian inter/multi-disciplinary e-Science grid.

INFN dissemination activities at both national and international level have mostly concerned the organization of several tutorials and training sessions and in the creation of the GENIUS web portal (see https://genius.ct.infn.it), a high level interface to various grid middle-wares (such as DataGrid’s and GLUE’s) developed in conjunction with NICE srl. GENIUS has been demonstrated, in fruitful collaboration with the CNR (the Italian National Research Council), in many official events in Italy and abroad and has also been adopted by the GriDis Project (see http://web.datagrid.cnr.it/GriDis/) as the default user interface.

A further step done from INFN was the development, in 2004, of the Grid INFN virtual Laboratory for Dissemination Activities (GILDA) project (see https://gilda.ct.infn.it). GILDA is a full grid test-bed completely devoted to dissemination and demonstration purposes. GILDA allows testing the strong capabilities of grid computing. On request, anyone can receive very quickly a grid certificate and a Virtual Organisation (VO) membership allowing them to use the infrastructure.

### Role in the project

INFN will be the coordinator of the project and will contribute significantly in all the workpackages with it’s large experience in Grid Technologies and Infrastructures. INFN contribution will be particularly significant in WP4 (Infrastructure), WP5 (Applications) and WP6 (Dissemination and Training). In WP4 will be transferred all the present knowledge of deploying and operating a large grid infrastructure based on the experience accumulated in national and European projects. In WP5 INFN will contribute to the extension of EGEE applications in Physics and Biology groups/Virtual Organizations to port their applications on the grid.

In WP6 the already significant experience accumulated in other projects will be used to extend the GILDA system to intercontinental usage and significant training activities will be managed to enlarge the knowledge of Grid technologies among the participant and the general public.

### Key Personnel

Dr. Alberto Masoni, born in Cagliari in 1961, graduated in Physics at University of Cagliari (110/110 cum laude) in 1984, is senior researcher at INFN where it works since 1988.  He worked at several experiments at CERN (the European Laboratory for Particle Physics) leading data analysis and online computing groups. He published 125 papers on international Journals including the Review of Particle Properties (20000 citations). He is member of the INFN Nuclear Physics Scientific Committee and of the Particle Data Group. He has been involved in management of large computing projects, as the Project Committee for the INFN Computing Regional Centre, the phase-2 costing Committee for the CERN Computing centre, the LHC Computing Grid Project where he was first member of the management board and now is member of the Grid Deployment Board.

Within the framework of the LHC Computing Grid Project he was at CERN from 2002 to 2004 as Scientific Associate.  Since its constitution is member of the Executive Board of INFN-Grid Special Project which manages and coordinate the INFN participation to national and international grid projects. He is member of the Scientific Board of the Cosmolab Consortium for Supercomputing of the Cybersar project  an approved National Objective Project of the Italian Ministry of University and Research.

Prof. Roberto Barbera

Prof. Roberto Barbera was born in Catania (Italy) in October 1963. He graduated in Physics "cum laude" at the University of Catania in 1986 and since 1990 he holds a Ph.D. in Physics from the same University. Since beginning of 2005 he is Associated Professor at the Department of Physics and Astronomy of the Catania University. Since his graduation his main research activitiy has been done in the realm of Experimental Nuclear and Particle Physics. He has been involved in many experiments in France, Russia, United States and Sweden to study nuclear matter properties in heavy ion collisions at intermediate energies. He has also been a member of the CLAMSUD Collaboration aimed at building a magnetic spectrometer to

detect pion, protons and kaon in proton-induced collisions. He is author of more than 60 papers published on international journals and about 100 proceedings of international conferences. Since 1997 he is involved in the NA57 Experiment at CERN SPS and in the ALICE Experiment at CERN LHC. Within ALICE, he is the co-ordinator of the Off-line software of the Inner Tracking System and member of the Off-line Board. Since late 1999 he is interested in Grid Computing. He is a member of the Technical Board of the Italian INFN Grid Project and inside this project, he is the coordinator of both the GENIUS portal project and the GILDA virtual laboratory for grid dissemination activities. At European level, he is the coordinator of NA4 Generic Applications activities inside the EGEE Project. Since 2001 Prof. Barbera he is also the member of the TERENA Technical Committee for grid Technology Area.

Dr Sergio Fantinel

Sergio Fantinel is member of the European EGEE-II project, Service Activity 1, as part of the Istituto Nazionale di Fisica Nucleare (INFN). He has been working in the area of Grid monitoring since 2002, when he participated in the WorldGrid, an event in connection with the SuperComputing Conference (SC2002). He is manager of the Grid resource pool contributed to the LHC Computing Grid by the Legnaro National Labs (Italy). He has a MSc degree in Computer Science Engineering from the University of Padova. He has contributed to the GridICE project since the beginning.

Dr Marco Verlato

Marco Verlato, has obtained the degree in Physics in 1990 and the PhD in 1998 at Padova University. Marco Verlato has a longstanding  experience in HEP data analysis and farm computing. He joined the DELPHI collaboration at the LEP startup in 1989, and completed his Diploma thesis in 1990. He continued his research activity in DELPHI collaboration with a INFN post-graduate grant, working on the measurement of the line-shape and asymmetry of Bhabha scattering around Z boson resonance energy, and then at LEP 2 energies, taking the Ph.D. Diploma in 1998 with a work about the search of new physics beyond the Standard Model.

At the same time he worked on the set up and operation of the Padova computing farm, and joined EU-Datagrid project since the beginning in 2001, and EU-DataTAG project in 2002. His contribution within these projects focused on several tasks: pure middleware development,  middleware deployment on the local computing farm,  development of interfaces between the LHC experiments application software and the grid middleware, interoperability between European grid and Globus-based US grid. Since 2004 he is member of EGEE project,  within the Service Activity 1 (SA1) group. He is involved in User Support, representing the Italian ROC in the EGEE Support Committee (ESC), in the deployment and management of the EGEE Pre-production and Certification test-beds, and in the tests of the gLite middleware and his interfaces to the LHC application software.

## P02 - Partner -  Metaware SpA (Italy) - MTW

Metaware SpA (www.metaware.it) was established in the year 2000 to ground a definite industrial project on the expertise that a group of senior ICT researchers had long ripened at the non-profit organisation Consorzio Pisa Ricerche by designing, implementing and managing RTD projects through close collaboration with public and private research centres across Europe. A key factor in the strengthening its own commitment in the field of technologies for e-government growth of Metaware was the decision to, extended its partnership to Infocamere SCpA, the ICT company of Italian Chambers of Commerce, focusing on digital signature and information security. Thanks to its forward thinking approach it now boasts over 40 information technologists and software engineers as part of its team. Based in the heart of Tuscany, Italy and hoarding a compound heritage of experiences and sound skills across leading-edge ICT, Metaware deploys its own resources in carrying out joint activities with national and international public bodies (Italian municipalities, provincial and regional authorities, government offices, monuments and fine arts services, the European Commission, the European Business Register) and private ICT and multimedia companies. Current interest areas include network intelligence management, digital IPR, workflow and interoperability management, financial modelling for rating, radio frequency authentication technologies.

Apart from its enviable position as one of the main providers of infrastructures for information security, software integration, e-government services and cultural heritage administration. Metaware also makes valuable contributions to ICT development and trend setting on an international scale. Metaware has an extensive and successful reputation as one of the forerunners in EU funded co-operation programs, which will guide and shape future ICT developments and initiatives. As a consortium member and involved in the event management and co-ordination of numerous European projects, Metaware has gained a considerable reputation for its professional approach and dedication in ICT event organisation and community development. Such event successes have not come without reward and Metaware can now claim to be involved in an array of on going international events and community development initiatives not least of which is the MONSOON series of Workshops & training events to be held in India, the BASIC-EuSEA2006 event and eChallenges e2005 edition to be held in Slovenia in October 2005. Previous international level events include EuroIndia2004 Co-operation Forum on the Information Society and eChallenges e-2003 and e-2004. Metaware is one of the few organisations to offer such innovative market products and solutions within the fields

### Role IN the Project

Building on Metaware’s pluriennial experience in designing and delivering networking platforms for the ICT industry and simultaneously taking advantage of a well-balanced mix of communication, business developments and IT expertise, the division's multinational team is expert in the exploitation of opportunities among user/provider communities from industry, research and academia.

By means of a variety of advanced tools and methodologies, the division will develop communication and branding packages, organise & manage EU-IndiaGrid events, design and execute training programmes in collaboration with ICTP and INFN and will raise awareness on promoting EU-IndiaGrid achievements internationally. The division strategically focuses on supporting the creation of new IT alliances between Europe and the developing countries, with particular reference to India, Russia, Latin America and South-East Asia, offering considerable added value to the EU-IndiaGrid consortium.

### Key Personnel

Hilary Hanahoe is currently collaborating with Metaware for the deployment of promotion, dissemination and training services on both an International and national level. She deals with the complete management of the organisation of events from planning, dealing with authors & delegates, to execution & logistics. Over 9 years of hands-on experience in administratively and scientifically co-ordinating National, Regional & European Union projects, provide her with high level Project Management skills.

Stephen Benians manages the FP6 IST project BELIEF the EU funded support project, which through its dynamic portal, establishes strategic synergies and common visions for research infrastructures. He has experience in project management in international environments that include EU funded as well as national funded research and innovation projects. He has managed international projects with the British Council in Brussels, which was a national contact point for an FP6 project promoting mobility of scientists and researchers in Europe; and worked with a political consultancy in Brussels managing a project on EU-China relations and also established an international network of think tanks. He has a Masters in European Union Studies from Edinburgh, and a Masters in Management of Innovation from the Scuola Superiore Sant’Anna, in Pisa Italy.

Douglas McKinley an Information Technologist from the Waterford Technological Institute in Ireland is currently collaborating on a number EU funded initiatives for Metaware and its consortium members. Coming from the Information Technology sector notably IT security and Middleware development. He is primarily involved in the design & execution of EC RTD projects specialising in finding mutual IT co-operation opportunities between Europe, India, Asia and Latin America, with experience in Marketing & Planning, International Co-operation, Press & Media and Relationship building with key project stakeholders. Douglas is currently collaborating on the EGEE-II Project and is Head of the Project's Industry Forum. In this role he also has a seat on the EGEE-II Project Execution Boards (PEB) and is a member of the EGEE-II Industry Task Force.

Laurette Gonzalès born in France. Her experience lies in developing ICT alliances in EU member states as well as International economies and researching clients in the field of editorial publishing houses in opening new markets in Italy and in France. Skills include: quality control checks, public relations with international clients, marketing management, managing complex administrative services, developing the organisation of work, and selecting pertinent suppliers. She is now collaborating with Metaware since 2002 and is involved in the organisation and management of both private & public, national and international projects & events and, over the years, has acquired expertise in financial budget planning, reporting, promotion and dissemination activities, execution and logistics in the field of IST. She is also involved in Metaware business deployment.

## P03 – Consortium GARR (Italy) - GARR

### Profile

Consortium GARR (http://www.garr.it/) is an Association under Italian law. It was established by the national Academic and Research Community. Its member institutions are the Italian Universities and the main governmental Research organizations as CNR (the Italian National Research Council), ENEA (Italian National Agency for New technologies, Energy and Environment) and INFN (Italian National Institute of Nuclear Physics). The aim of Consortium GARR is to plan, manage, and operate the Italian National Research and Education Network, implementing the most advanced technical solutions and services. It supplies the Italian Academic and Research Community with connectivity to the GARR backbone, interconnecting over 250 universities, laboratories, libraries, observatories and other research facilities. Also, Consortium GARR provides its member institutions with the main Operational and Application Networking Services. The GARR-G network, which started operations in 2004, is a widespread infrastructure covering the whole Italian territory; its backbone, based on the most advanced optical technologies and organized around 40 PoP, allows the backbone to reach a speed of 10 GB/sec and guarantees high reliability, security and error resilience. The broadband access allows to introduce advanced technologies such as IPv6, QoS, multicast and VPN on GARR-G , to supply new advanced services and to fully support innovative applications such as Grids, tele-medicine, eLearnig, Multimedia, High Energy Physics, Radio Astronomy, Heart Observation of Supercomputing.

GARR is connected at 10Gbps to GEANT and to the North American and Japanese networks and is currently taking part to the EUMEDCONNECT and ALICE initiatives, which aim to widen such connectivity to the Mediterranean and Latin American Countries.

Besides supporting the Italian Academic and Research Community thanks to the provision of advanced network services, Consortium GARR itself is actively involved in a number of Research and Development activities both at a national and international level. Currently, Consortium GARR participates to several European projects from the 5th and 6th FP, such as GN2, EGEE-II, 6NET, EUMEDCONNECT, ALICE, MUPBED and is involved in international task forces like TF-NGN and IETF.

### Role in the project

Thanks to the active participation to projects such as EUMEDCONNECT and ALICE, which aim to bridge the digital divide in developing Countries, Consortium GARR has achieved a wide experience, not only in terms of the technical issues of such initiatives, but also regarding their typical problems and difficulties.

As regards to Grids, Consortium GARR takes part to the EGEE-II project, working at the development of the Grids’ "network element" and at the implementation and management of services related to this level, such as Bandwidth Allocation Reservation and Network Performance Monitoring. Furthermore, Consortium GARR supports advanced users (such as INFN and ENEA), which implement their own grid applications. Recently, GARR has been actively involved in drafting two new regional Grid projects, aiming to extend the EGEE infrastructure to non-EU areas (i.e. EUMEDgrid, addressing the Mediterranean Region, and EUChinagrid, addressing China), which were favourably evaluated and are currently in the negotiation phase. The contribution from Consortium GARR to the EU-IndiaGrid project will be especially focused on Network provisioning and operations, and in maintaining tight liaisons with related projects

### Key Personnel

Enzo Valente: is the general manager of Consortium GARR and will have overall responsibility for the GARR participation in the GN2 project, in particular for management issues. He was the Director of INFN-GARR.

Marco Marletta: is Senior Network Engineer at GARR. He has a degree in  Electronic Engineering and he joined GARR in 2000, where his main  responsibilities are in the field of planning evolutions of  the GARR network and taking care of the routing infrastructure, with a particular attention on the multicast transmission; he is involved as well in several european-wide projects such as EUMEDCONNECT, EVLBI and DEISA as main GARR technical contact. He will lead the network planning and operations workpackage, and will be in charge for maintaining contacts with ERNET and DANTE from a technical point o view.

Federica Tanlongo: is PR  manager of  GARR . She has an ICT master degree in New  Media and Communication from the University of Rome “La Sapienza”. She is responsible for dissemination activities, planning and organizing events and creating ad-hoc contents (newsletters, websites etc). She is currently involved in several European Projects, both on dissemination and support to the management activities. She will collaborate to task 2.3 (Synergies with related projects).

## P04 – The Abdus Salam International Centre for Theoretical  Physics (ICTP)

### Profile

The Abdus Salam International Centre for Theoretical  Physics (ICTP) (http://www.ictp.it/ ) founded in 1964 by the late Nobel Laureate Professor Abdus Salam, is an international institute of research and high level training in pure and applied physics and mathematics offered mainly to developing countries scientists. In recent years, about 5,000 scientists per year from almost all nations have visited ICTP to participate in the Centre's research and training activities- more than fifty per year - and to conduct their own research in various fields. In particular, Indian scientists are spending almost 400 man-months per year in ICTP.

ICTP has an excellent network of contacts in Developing Countries and former Soviet Union Countries,  and a long-standing tradition of formation and dissemination in IT themes, like networks, wireless networks, cluster computing and HPC and quite recently Grid computing ( in Venezuela(2004), Ghana,(2005) and in Trieste (2004) with participation from 15 countries. In 2006 the ICTP organized a workshop in Trieste for 2006 on Porting Scientific Applications on Computational grids, during which porting of various  scientific applications have been addressed.

In addition to these grid oriented training activities, ICTP is currently implementing a national grid infrastructure for financial and economic research in the framework of the "Egrid project", funded by the Italian Ministry for research (See for further details www.egrid.it). The Egrid project and applications within it are now also participating at the EGEE-II project as "generic application".

ICTP is moreover a leading partner in the grid@Trieste project, that aims to build a metropolitan grid infrastructure within the Scientific Institutions in Trieste.

ICTP has well established scientific collaborations with several Indian institutions in the field of computational condensed matter science, and shares with them a number of condensed matter applications and Atmospheric Sciences models.

### Role in the project

In this project ICTP’role will be mainly in WP5 and WP6. In WP5 ICTP  is committed to port Condensed Matter Physics  and Atmospheric Physics applications on computational grids. Three ICTP sections will be involved in this part of  the  project: the Condensed Matter Group and the Physics of Weather and Climate will provide the scientific applications and specify the computational requirements; the Scientific Computer Section, which already participates in the EGRID project, will provide its expertise to port the applications on the grid. The work will be carried out in collaboration with two indian partners: Dr. Shobhana Narasimhan, of the Jawaharlal Nehru Centre for Advanced Scientific Research (JNCASR), Bangalore, India, and Prof. Dilip Kanhere, of the Department of Physics, University of Pune. Both teams are interested in porting on the grid the scientific applications for ab-initio quantum simulations contained in the Quantum Expresso package (www.quantum-espresso.org). The package contains state-of-the-art parallel programs for quantum simulations in condended matter physics.

ICTP will give a significant contribution within the Dissemination activity in WP6 as well. As mentioned above, the ICTP has a strong commitment in advanced knowledge transfer to scientists from developing countries in IT, and recently in particular in grid technologies and applications. This is as witnessed, beyond the activities listed in the Institute profile, by the International workshop (in collaboration with INFM-Democritos) on Porting Scientific Applications on Computational grids, held in February 2006; and by the South Asian Regional Workshop on Electronic Structure Methods and their Applications, to be held in July 2006, in Bangalore, India, and the training activity on grid to be held in September 2006 in Colombo, Sri Lanka, in association with the SEARCC 2006 Conference

### Key Personnel

Stefano Cozzini: Education: PhD in Physics, University of Padova, Italy (1995); “Laurea” in Physics, University of Trento, Italy (1991)

Professional Experience: INFM Development scientist in the Condensed Matter Group at Sissa and at Democritos (1999-current. Member of the HPC group at CINECA (1997-1998). Post-doc researcher at Physics department of the University of Seville (Spain) (1995-1996).

Selected Professional and Synergistic Activities: Leader of the Information Technology Research Activity of Democritos National Simulation Center. Consultant for Grid Computing at ICTP (International Center for Theoretical Physicis). Co- Project  leader  of ICTP E-GRID project. Co-Project leader for the Grid@Ts  project. Co-Organiser and co-director of three editions of the ICTP SCHOOL IN "HIGH PERFORMANCE COMPUTING  ON LINUX CLUSTERS", ( Trieste 2002/ Merida (Venezuela) 2003/ Kumasi (Ghana 2005)

Organizer of  the Democritos/ICTP workshop on “Porting scientific applications on computational grids”to  be held at ICTP, february 2006 Co-chair on the international workshop  “Grid  in finance 2006” Organiser of the DataGrid Tutorial, Trieste, january 2004 and of the“First latin american school in grid computing”.(november 2004 Merida Venezuela Member of the Program Committee of the “Linux Cluster Revolution” meeting ( 2002/2003/2004/2005/2006 editions).

Alvise Nobile was born in Trieste in 1950. He graduated in physics in 1973 at the University of Trieste. He has been responsible of the scientific computing services of the International School for Advanced Studies (SISSA) of Trieste from 1975 to 1989, and of the International Centre for Theoretical Physics (ICTP) from 1989 to 2005. During his service at ICTP, he organized most of the ICTP training activities in the areas of Computing and Internet technologies, both in Italy and in developing countries (Latin America, Africa).

Sandro Scandolo: PhD in Physics ( Scuola Normale Superiore, Pisa, 1993) Degree cum laude in Physics ( Universita' di Pisa , 1989)  Degree cum laude in Physics ( Scuola Normale Superiore , Pisa, 1989)

He currently holds a Research scientist position at ICTP. Previous experience includes 2000-2002 - Visiting Research Staff, Dept. of Chemistry and Princeton Materials Institute, Princeton University, 2002 Associate Professor, International School for Advanced Studies, 1998-2002 Assistant Professor, International School for Advanced Studies. His professional activity has fruited more than 60 scientific publications, more than 20 invited talks at international conferences, Supervisor of about ten between PhD (SISSA) and Diploma (ICTP) theses as well as being Organizer of the 1998 ICTP Spring College on Computational Physics, and of the 2000 ICTP Spring College on Electronic Structure Approaches to the Physics of Materials, Trieste, Italy

Organizer of the CECAM/Psi-k workshop on Applications of First-Principle Methods to Geophysics, July 2001, Lyon, France. In 1998 at the Gordon Research Conference on ``Research at High-Pressure'' he was awarded the J.C. Jamieson award for high pressure physics. His Research interests include high-pressure physics: first-principles simulations of phase transitions in covalent, molecular, and metallic systems, with applications to materials science, geophysics and planetary science; Surface science: first-principles calculations of surface reconstructions, adatoms on semiconductors, surface magnetism, metal-insulator transitions. Polymers: structural, dynamical, electronic and transport properties of ideal and defected polyethylene. Non-linear optics: sum rules and Kramers-Kronig relations, linear and non-linear optical properties of semiconductor microstructures.

## P05 - Cambridge University

## The Cambridge eScience Centre

The Cambridge eScience Centre (http://www.escience.cam.ac.uk/) has a remit to promote e-Science research in Cambridge region. It is part of a national network connected through SuperJanet. It offers access to major supercomputer facilities, using a package of Grid software based on the Globus standard. The main objectives of the Centre are:

- To support e-Science projects involving scientists and industry in the Cambridge region.

- To enable new scientific advances by using Grid-enabled applications to tackle Terascale problems.

- To develop new generic Grid-based tools for massive data handling, high-performance computing and visualisation applications on wide area networks.

The Centre supports a wide range of projects including:

- LHC computing - running a 54 CPU node on the LCG for as part of EGEE/GridPP.

- CamGrid - a University wide grid of shared research computing resources.

- Telemedicine on the Grid - Demonstrating the capability of Grid technology to support multi-disciplinary meetings for the review of cancer diagnoses and treatment.

- Molecular Informatics - Exploiting modern methods of information management to discover new molecular information.

- Electromagnetic Scattering from Aircraft - visualising complex 3D electromagnetic field data.

- CosmoGrid - enabling UK cosmologists to make world class contributions from observation of the cosmic microwave sky, using remote visualization and computational steering tools on high performance computing systems.

- Distance CFD Supercomputing for Industry - understanding turbulent flow patterns in complex systems like gas turbines and aero engines, using a grid based system.

- FutureGrid - A program for long-term research into Grid systems architecture.

- CancerGrid - Open standards for clincal cancer informatics.

- GROWL - A light-weight Grid services toolkit and applications.

- SciBorg - a project to use natural language processing to extract scientific information from literature sources and make it available for computational processing and archiving.

- MaterialsGrid - an industrial collaboration to create a database of material properties using computational grids.

In addition the Centre has a strong collaboration with Microsoft Research Cambridge and the Cambridge Computational Biology Institute to develop tools for scientific computing, especially in the life sciences. MSR have sponsored a Research Fellow at CeSC and a PhD student at CeSC, and two students at CCBI as part of this project.

The Centre is also one of the sites providing support and infrastructure for the UK e-Science GridMon project. GridMon is a UK e-Science project whose intention is to establish and maintain a "best of breed" infrastructure for e-Science and Grid oriented network performance monitoring.

### Role in the Project

The Department of Physiology, Development and Neuroscience at Cambridge University are the local scientific partners in this project, under Dr Dennis Bray. CeSC is already supporting this group in its use of the CamGrid system to run their scientific applications. CeSC staff will be able to expand this role to enable the group to make use of the EGEE/IndiaGrid system. CeSC has expertise in all the relevant technologies, including Globus, SRB and the EGEE software framework, as well as the Condor deployment used on CamGrid. Most of this work will be in WP4 (Pilot Grid Infrastructure operational support), in particular providing system manager support for the necessary grid nodes in Cambridge, and transferring expertise in the use of Grid software from Globus and EGEE. It will also be necessary to consider the storage needs of the project. Here CeSC is expert in the use of SRB and the University digital archive, Dspace. Finally CeSC can offer advice on security aspects such as virtual organisation management, certificate handling and issues with local firewalls. In WP5 (Applications) we will support the Department of Anatomy and NCBS in the deployment of their applications. In WP6 (Dissemination) we will be able to include this project in a variety of dissemination channels, such as the UK All Hands Conference, where we make public demonstrations of our project outputs, and in our series of technical meetings for local scientists and system managers.

### Key Personnel

Andy Parker

Andy Parker is a Professor of High Energy Physics, with over 100 publications on aspects of particle physics.  His current research interests involve experiments to reveal new physics such as extra space dimensions and quantum-sized black holes.

As Director of the Cambridge eScience Centre, he is responsible for grid computing initiatives across the University, covering a wide variety of projects in life sciences, earth sciences, medicine, chemistry and engineering, all requiring the sharing of large computational and data resources. He is PI or co-I on many eScience grants, including the CancerGrid project, funded by the MRC, and MaterialGrid funded by the DTI. He leads the CamGrid project which links up computing resources across six University departments.

He is a member of the UK national eScience Steering Committee. He sits on the Management Committees of the National Institute of Environmental eScience, the Cambridge Computational Biology Institute, the Cambridge-Cranfield High Performance Computing Facility, and the CamGrid project. Within the GridPP project he is a member of the User Board, and the SouthGrid Management Committee. He is a member of the Microsoft Research 2020 Expert Group, which is producing a road map for the future of computational sciences.

He has been a leader of the ATLAS experiment for the Large Hadron Collider, due to begin operations at CERN in Geneva in 2007. This machine will be the most powerful particle accelerator ever constructed, and will generate a Petabyte of data each year, to be analysed by the 150 collaborating institutes. As a member of the ATLAS Executive Board, Prof Parker was for 6 years the Project Leader for the ATLAS Inner Detector, the most complex tracking detector constructed at CERN to date, with overall responsibility for all aspects of its design and construction, including its software systems. The construction team contained over 50 partners worldwide, with extensive use of collaborative tools, especially video conferencing technologies.

Prior to this, Prof Parker was a CERN Fellow and Staff member, and was Software Coordinator for several CERN experiments. He has long experience of distributed computing. He was responsible for all aspects of the software of the UA2 experiment at the CERN proton-antiproton collider in the 1980s, which was at the time the highest rate and data volume accelerator.

He holds a PhD from the University of London, and an MA from Oxford. He is a Professorial Fellow at Peterhouse, Cambridge. He was awarded the Pilkington Prize for excellence in teaching in 1997.

Mark Hayes

Mark Alexander Hayes was born in 1974, BA (Honours) in Mathematics, King's College, Cambridge in 1995 and has 10 years experience in IT systems management and Internet technologies. 7 of those years have been in the area of scientific computing with the last 4 years in a senior management role. From November 2001 is the Deputy Director, Cambridge eScience Centre, University of Cambridge (Technical Director until July 2005). The Cambridge eScience Centre is one of ten regional centres for research and development in wide area distributed computing, also known as Grid computing. It focuses on applications of eScience and has a wide-ranging portfolio of scientific computing projects from cancer clinical trials to tranport data modelling. The centre employs a system manager, several developers and a project manager, all of whom report to the deputy director.

Mark Hayes is  principal investigator and project director for GROWL: a light-weight Grid toolkit with applications in bioinformatics, materials science & social science. He is member of the management committees for the eScience centre and for the CamGrid project, which is building a University-wide campus Grid based on Condor. He has an advisory role with the National Institute for Environmental eScience, the Cambridge Computational Biology Institute & the National Transport Data Framework.

Affiliations & other professional activities

• Member of the Programme & Steering Committees for the UK e-Science All

Hands Meeting 2004-2006.

• Member of the Programme Committee for the International Conference on e-

Social Science 2006.

• Member of the Global Grid Forum

• Member of the ACM

Mark Calleja

Mark Calleja, BSc(Hons) in Theoretical Physics (1st class) at the University of Kent, Ph.D. at the University of Kent, is Grid Computing Specialist at the Cambridge eScience Centre, University of Cambridge. Apart from other things, this involves setting up a university-wide Condor facility (CamGrid) based on a flocked architecture, rolling out a Storage Resource Broker (SRB) service for general use and installing and maintaining a number of Globus (GT 4.0.2) gatekeepers to provide external access to the facility. From 1996 to 2000 Senior Engineer at Roke Manor Research. From 2000 to 2002 Postdoctoral Research Associate at the Department of Earth Sciences at the University of Cambridge.  From 2002 to 2004 he has been NERC eMinerals Postdoctoral Research Associate based at the University of Cambridge. The work was primarily concerned with setting up the eMinerals minigrid.

Cambridge University Department of Physiology Development and Neuroscience

### Profile

The Cambridge University Department of Physiology, Development, and Neuroscience (PDN) (http://www.pdn.cam.ac.uk) has a high level of achievement in both Research and Teaching. It was awarded a rating of 5A in the last two Research Assessment exercises and a score of 23/24 in the latest Teaching Quality Assessment. It has an internationally distinguished reputation for its research in the areas of Cellular and Systems Physiology, Development Biology, Neuroscience and Biological Imaging.

### Role in the project

Recent developments within the Cambridge School of Biological Sciences led to the formation (in Summer, 2005) of a new Department of Physiology, Development, and Neuroscience  (PDN), from the existing Departments of Anatomy and Physiology. Its creation recognizes the breakdown of traditional subject barriers and the inherently integrative nature of modern biology. The new institute includes, in addition to the aforementioned topics, a constellation of distinguished researchers with expertise in the sensory physiology of cells and organisms. The strength of the new grouping will be further enhanced new appointments currently being made in the general area of Systems Biology.

A major theme of the new Department is the inclusion of mathematical and computational approaches, building on a distinguished record of achievements. These include the quantitative analysis of signalling events in the visual pathway, the analysis of cell movements underlying morphogenesis in the developing vertebrate embryo, and in the computer-based analysis of the molecular event of bacterial chemotaxis,

### Key Personnel

Prof. Bray (BSc in Chemistry at London 1962, PhD in Biochemistry at the Massachusetts Institute of Technology 1967) is Emeritus Professor (active) at PDN. Dr Bray was previously a research cell biologist widely recognized for his many contributions to nerve cell development and actin-based motility. In 1990 he made an abrupt transition to computational work since when he has been developing accurate simulations of especially the bacterial chemotaxis pathway. He has formed a number of productive collaborations with physicists and computational scientists leading to important discoveries concerning the logic of intracellular signaling. This includes inter alia the prediction of conformational spread between membrane receptors – subsequently supported by experimental evidence and now widely accepted in the cell biology community. Bray is an active and influential proponent of the use of computation in cell biology, widely sought as a lecturer and instructor at meetings and courses on the interface between cell biology and physics at locations such as MBL Woods Hole, Caltech, Aspen Center for Physics, MPI Dresden, and AMOLF Amsterdam. He is organizer of research seminars on Computational Biology, running since 1997, co-developer of publicly available programs BCT, StochSim, Smoldyn and founder member of the systems biology markup language (SBML) software consortium. Bray is author of over 100 refereed articles, 6 textbooks, 30 scholarly reviews, and multiple editorial commentaries. He currently serves on three editorial boards, including Science.

## P06 – Tata Institute of Fundamental Research (TIFR)

## Tata Institute of Fundamental Research (TIFR) Mumbai, India

### Profile

The Tata Institute of Fundamental Research (TIFR) was established in 1945 at the initiative of Dr. Homi Jehangir Bhabha. The Institute is proud to have produced many of the finest scientists of India who have been involved in seminal research in fields ranging from Mathematics, Biology, Chemistry, Computer Science, Physics and Science Education as well as some aspects of Public Health. 
There are at present about 400 scientists in the Institute working in various disciplines grouped into three major schools: the School of Mathematics, the School of Natural Sciences and the School of Technology and Computer Science. The Homi Bhabha Centre for Science Education at Deonar, Bombay; The National Centre for Radio Astrophysics at Pune and The National Centre for Biological Sciences at Bangalore also form a part of TIFR activities. 
The School of Mathematics has research interests in areas like Algebra, Algebraic Geometry, Lie Groups, Lie Algebras, Algebraic Groups, Representation Theory and Quantum Groups, Theory of Numbers, Combinatorics, Differential Geometry and Topology, Real and Complex Analysis, Ergodic Theory, Probability Theory on Groups and Mathematical Physics. 
Scientists in the School of Natural Sciences work mainly in the fields of Astronomy and Astrophysics, Chemical Sciences, Condensed Matter Physics, High Energy Physics, Molecular Biology, Nuclear & Atomic Physics, Radio Astronomy and Theoretical Physics. The Institute is also actively involved in the field of educational research with a special emphasis on school level education as well as some aspects of public health.

The Institute has several field stations and research facilities in different parts of the country. A Giant Meterwave Radio Telescope, the largest of its kind in the world, is operational at Khodad near Narayangaon, north of Pune and a large equatorially mounted cylindrical radio telescope and a high energy cosmic ray laboratory are operational at Udhagamandalam in Tamil Nadu. High Energy Cosmic ray and Gamma Ray laboratories are operated from Pachamarhi in Madhya Pradesh. TIFR runs a National Balloon Facility in Hyderabad which is among the best in the world and has the geographical advantage of being close to the geomagnetic equator. At Gauribidanur, TIFR scientists have built an extremely sensitive balance to study the difference between gravitational and inertial mass. A Heavy Ion Low Energy Accelerator capable of accelerating particles to moderate energies for studying heavy ion atomic interactions and a Nuclear Magnetic Resonance Facility to study complex molecules are also housed in TIFR. The Institute's Dental Section has been actively involved in investigations pertaining to carcinogenic effects of tobacco.

The Institute has acquired the status of a Deemed University as of June, 2003.

### Role in the project

As seen in the TIFR Institutional profile, there are many diverse areas of research in the institute. For many of these areas, the availability of grid connectivity would be a boon and could both improve the quality and speed of collaborative research as well as lead to new methodologies of carrying out such research. Examples are in the areas of (i) astronomy and astrophysics, where data from many satellite observatories is freely available, (ii) biological sciences, where already the TIFR National Centre for Biological Sciences (NCBS) at Bangalore is entering this project and that could easily be extended to the main TIFR campus, (iii) high energy physics, which, as one is aware, is the main driver of grid applications and technology world-wide.

Thus, as a first step it is envisaged that the thrust of grid related activity would be driven by the experimental high energy physics community which is a member of the CERN based CMS collaboration.

As HEP is expected to be the initial driver for grid applications at TIFR, some more details of this project from the national perspective are given here. Two Experimental High Energy groups at TIFR (TIFR-EHEP and TIFR-HECR) are members of the CMS collaboration at CERN and, together with four other Indian groups (BARC, Delhi University, Panjab University, Chandigarh and Visva-Bharati University, Santiniketan) form the India-CMS collaboration. TIFR plays the nodal role in the India-CMS collaboration and the CMS Tier-2 Regional Computing Center is being set up here. Thus, on the one side TIFR needs international connectivity to CERN (and Europe) and on the other side domestic connectivity to the other Indian groups which will be Tier-3 centers. Setting up, maintaining and contributing effectively to the CMS collaboration via the overall India-CMS effort which would utilize the facility provided by the EU-grid project would be an excellent example of India-EU collaboration under this project.

It is expected that with the successful example set up by the HEP community, other diverse research projects would also make effective use of this project.

### Key Personnel

- Prof Atul Gurtu, India-CMS Spokesperson

Date of birth, 16 January 1946, joined TIFR in November 1969. Worked on bubble chamber and hybrid bubble chamber experiments followed eventually by all-electronic experiments L3 and now CMS. Currently India-CMS Spokesperson and member of Particle Data Group collaboration, co-responsible for W and Z sections.

- Prof Sunanda Banerjee

Date of birth, 20 July 1952, joined TIFR in January 1978. Worked in a variety of experiments starting from Bubble Chamber experiments at low energies to hybrid spectrometer experiments and finally with counter experiments, WA83 (pi-p interactions looking for direct photon production), e+e- (CELLO, L3 and Belle) and CMS. Worked on software developments for L3 and CMS - also took part in software projects, RD44, RD45 and also in GEANT3, GEANT4 program developments.

- Prof N.K. Mondal

Date of birth, 11 March 1951, joined TIFR in September, 1977. 29 years experience in the field of experimental high energy physics. Leader of the TIFR group involved in the DZERO experiment at Fermilab and TIFR-HECR group involved in the CMS experiment at CERN. Played a key role in setting up the DZERO computing farm at TIFR. Co-leader of the CMS-Tire-2 Grid computing station at TIFR.

Technical persons:

- Mr P. Nagaraj

Date of birth, 30 May 1963, joined TIFR in July 1986. Computer system administrator for the TIFR-HECR group involved in DZERO experiment at Fermilab and CMS experiment at CERN. Main system person responsible in setting up and running the DZERO Computing FARM at TIFR. One of the main system person responsible for setting up the CMS Tier-2 Grid station at TIFR.

- Mr P.V. Deshpande

Date of birth, 10 Jan 1955, joined TIFR in Feb 1979. Computer system administrator for the EHEP group. Has handled, maintained and managed EHEP systems connected to mainframes, workstations ranging from Apollo to HP, PC's of all generations, has set up cluster for BELLE experiment simulations, and recently was one of the main persons responsible for setting up the CMS Tier-2 48 node prototype at TIFR.

## National Centre for Biological Sciences, Bangalore, India (NCBS)

### Profile

The National Centre for Biological Sciences (http://www.ncbs.res.in) is a basic research institution in modern Biology. The Centre was founded in 1988, as a daughter institution of the Tata Institute of Fundamental Research (TIFR), in Mumbai (http://www.tifr.res.in). TIFR has been one of the premier research institutions in India since its founding in 1945. Following some years on the campus of the Indian Institute of Science in Bangalore NCBS moved to its own premises in 1999. The Centre currently has 21 groups in 4 main research areas of Biology and is continuing to expand. NCBS has post-graduate programmes at the Masters and PhD levels, an active visiting student programme.

NCBS has a very active meetings and workshops programme, typically hosting 5 or more international and national meetings each year (see http://www.ncbs.res.in/%7Eevents/presentindex.html).  Several of these workshops are structured as short courses and training programmes for international and Indian students.

NCBS has long been committed to interdisciplinary research at the interface between Biology and the physical sciences, in keeping with its mandate to pursue research at the leading edge of Biology. In recent years this has become formalized in the iBio (Interdisciplinary Biology) programme, which is represented by more than half of the NCBS faculty. Three of the groups at NCBS (Thattai, Sowdhamini, Bhalla) have a substantial computational component to their research. The Centre established a supercomputer facility in 2003 with high-quality cooling and power infrastructure. This currently houses 3 clusters with considerable room for expansion.

### Role in the project.

NCBS will collaborate with several European laboratories, including the group of Dennis Bray at the new Department of Physiology, Development and Neuroscience, at the University of Cambridge. The focus of these efforts will be the development and application of high-performance simulation software for systems biology. We propose to port our software to the grid platform (WP5, applications) and to make this software publicly available. We propose to develop Systems Biology Markup Language (SBML) compatibility for our software which will facilitate its dissemination and use by other researchers, and we will conduct training in such simulation deployment including the use of Grid technologies (WP6).

### Key Personnel

Dr. Bhalla (BA in Physics at Cambridge 1986, PhD in Biology at the California Institute of Technology) is associate Professor at NCBS where he has been since 1996. Dr. Bhalla has been involved in high-performance computation in biological simulations since the 1980s. He was involved in the development of the widely used neuronal simulator GENESIS, which was one of the first simulators to be ported to parallel architectures (the Intel Touchstone Delta at Caltech, a prototype for the Intel Paragon). In the 1990s Dr. Bhalla extended GENESIS for use in systems biology simulations and is actively developing the next generation version of the numerical code. Dr. Bhalla has published over 30 papers in international journals, including Science, and serves on four international journal editorial boards.

Dr R.Sowdhamini's pre-doctoral studies were at Indian Institute of Technology,chennai, doctoral work at Indian Institue of Science,Bangalore and post-doctoral work at Birkbeck College and University of Cambridge,U.K.

Her interests are in the bioinformatics of protein folding and structure/function prediction. She has developed several algorithms and databases as tools to carry out such predictions. Many of these resources are online on her home page at http://www.ncbs.res.in/~faculty/mini.html.

## P07 – ERNET India

### Profile

ERNET (Education & Research Network) India (http://www.eis.ernet.in/), an autonomous scientific society under Ministry of Communications & Information Technology, Government of India was established in the year 1998.

Its activities are organized around five technology focused areas: Nationwide Academic and Research Network; Research and Development in the area of Data Communication and its Application; Human Resource Development in the area of High-end Networking; Educational Content; and Campus-wide High Speed Local Area Network.

C-DAC and ERNET India both Autonomous Scientific Organizations under the Ministry of Communications and Information Technology have initiated to setup India Grid in the country.  In the initial stage, grid will connect 45 higher learning educational and research institutions in the country on a 100 Mbps backbone.  The project has been taken up as proof-of-concept.  After the concept gets matured, bandwidth of the backbone will be increased to 2.5Gbps.  Initially, the institutions will access computer resources of each of the institutions and computer facilities installed at C-DAC.

ERNET’s responsibility is to lay down high-speed communication fabric.  C-DAC is engaged in developing applications and provide high computing platform to the institutions.  The applications identified in the proof-of-concept phase are in the area of Weather Forecasting, Bio-informatics and Bio-technology-Molecular, Disaster Management and solid modular applications. It is expected that the grid will be laid by mid of December, 2005.  The other institutions which are actively involved are – seven Indian Institutes of Technology (IITs), about 25 Universities and 13 other higher learning educational and research institutions.

Network and Points of Presence (PoPs)

ERNET India has set up and operating a state-of-the art nodal Intra and Internet network for Educational and Research Institutions.  It has 13 Points of Presence at the premier educational and research institutions in the country.  All the 13 PoPs are equipped with state-of-the-art IT infrastructure which can provide connectivity in the range of Kbps to 155 Mbps.  These PoPs are connected on a countrywide IPv6 fibre optic terrestrial backbone which is further connected with satellite backbone at STP Bangalore.  The entire infrastructure supports by IP multicasting, web casting and video broadcasting. The entire network is managed and operated through the premiere educational institutions.  The countrywide backbone is connected to dedicated international links at Delhi, Mumbai, Pune, Chennai and Bangalore.  An international bandwidth of about 90 Mbps is currently installed at ERNET.

ERNET also operates VSAT based network in the C-band of frequency spectrum for providing connectivity to academic and research institutions located in remote parts of the country.  Three satellite transponders (each of 36 MHz) in the C-band of frequency spectrum leased from Department of Space are presently deployed in the network.

Today more than 1200 educational and research institutions are connected on ERNET.

All the universities and other higher learning institutions including Agricultural Institutions, Schools and Engineering Colleges are connected on Intra and Internet through ERNET.

Pertinent project Experience:

- ASEAN India Digital Archive

  - Culture specific digital Archive under Indo ASEAN cooperation.  All the ASEAN 9 countries participated in the project.

  - Contains voice, picture and video clippings of common words, phrases and events from India.

- Instruction on Demand – Development of Distance Learning Tool

- A distance learning tool

- Prepares and delivers on-line and stored lectures over a TCP/IP network.

- Can work on dial up connectivity as it requires low bandwidth

- Digital Library

About 500 reputed international journals like IEEE etc in all areas of disciples are hosted on the network. A digital library with more than 42000 books is available on the network.

- Network Monitoring Tool (NMT)

The tool monitors illegal and unauthorized communication leading to cyber crime over Internet.

Projects with the European Union

Connecting ERNET with European Grid – GEANT, a programme being pursued in consultation with European Union.  The latter was providing funds to the extent of 50% of the international connectivity cost.

National QoS Test Bed framework for 4G Mobile Networks – the project proposal is submitted for funding to European Union.

### Key Personnel

Gulshan Rai: Gulshan Rai is the Executive Director of ERNET. He gained a M. TECH, PhD. He has an overall 24-year-experience in handling IT related activities. Among his major activities and contributions in the IT Infrastructure we can state the conceptualized, designed and implemented e-governance applications and solutions in the areas of: Taxation including VAT; Police, Internal Security; Banking; Medical Informatics; Passport and Immigration; Transportation. With regards to Intra and Internet he supervised the design and setting up of ERNET, a nodal Intra and Internet for Educational Institutions, which include Universities, Engineering Colleges and Agricultural Institutions. In Research & Development he is associated with projects for the development of indigenous Technology in the areas of: Computer Technology particularly large and mainframe computers; Low cost Personal Computers; Firewall and Intrusion Detection System; Network Monitoring Tools; Bandwidth Manager; Nationwide QoS Testbed for Network related applications; 4G Mobile Network. He was in charge of the Design and implementation of a large Gigabit campus LAN Network with 3000-4000 nodes deploying multi technologies like Fibre, UTP and wireless based on 802.11 protocols.

Bharat Bhushan Tiwari: Bharat Bhushan Tiwari gained a Scientist ‘D’ and a Master of Engineering. He has an overall 21-year-experience. He has attended courses and received awards in the field of Network Security & Ethical Hacking. Major Activities and Contribution thereto in the last five years refer to the ‘Nationwide establishment of QoS Network Testbed’ which would be open for academia and industry to test their real time applications like telemedicine, distance learning, VPN, VoIP, interactive video, robotic control, ‘Network Control Center under setup at ERNET POP’ whose objective is to make use of sophisticated network diagnostics to monitor the entire POP’s network for problems, ‘Design and Development of Network Monitoring Tool (NMT)’ to develop Internet monitoring tool for intelligence gathering and evidence collection and to develop capabilities in the area of cyber security, ‘Setting up Cyber Forensic and Digital Analysis Laboratory at CBI H.Q.’.

Geeta Kathpalia: Geeta Kathpalia gained a Scientist ‘E’ and a M. TECH in Integrated Electronics. She currently heads the VSAT Hub operations. The VSAT Hub providing internet connectivity is a major set up of ERNET, which caters to a total of 300 Educational institutions with varied network architecture.

Within this framework she takes over the following responsibilities: Proposal and VSAT solution to users; setting up VSAT link at the site under various schemes like UGC Infonet, AICTE, Navodaya Vidyalaya and others; LAN/WAN Management; ensure customer satisfaction; ensure proper routing and Internet connectivity; proper functioning of Mail Servers and administration of Mail-Server and DNS services; technology evaluation and procurement of equipment; upgradation and expansion of the network; planning of Hub Installation and Management; coordinate link upgrades; coordination with Department of Telecommunication and Department of Space for licence, transponder allocation and payment related with leasing of resources; frequency approval.

## P08 - Department of Physics, University of Pune

### Profile

The Department of Physics of University of Pune (physics.unipune.ernet.in) started its activity in 1952, and has presently research programs in Materials Science, Solid State Physics, Condensed Matter Physics, Nonlinear Dynamics, Scanning Tunneling Microscopy, Cloud Physics, Thin/Thick Films, Diamond Coatings, Nuclear and Accelerator Physics, Lasers, Plasma Physics, Field Electron/Ion Microscopy, Biophysics etc. The department has about 30 faculty members, and a number of post-graduate and doctoral programs. It has been recognized that teaching in this department is among the best in the country.

### Role in the project

- ERNET and CDAC has jointly initiated a pilot grid computing project in India called GARUDA the University of Pune has been identified as one of the nodes on this grid the University authorities have already agreed to participate in this project and the site preparation to establish a MUX is already on. It may be mentioned that the University of Pune has extensive experience in parallel and cluster computing because of the presence of CDAC the central agency established by Government of India on the campus.

- University of Pune and ICTP have a long-standing collaborative relationship. There are five associates (all in the field of computational physics) presently there is an ongoing collaborative research project between Department of Physics/ Professor D. G. Kanhere and Condense Matter group (Dr. Scandolo), ICTP. This is in the area of electronic structure applications requiring extensive computational facility (Large scale electronic structure calculation, thermodynamics, density functional theory etc.)

- Total number of faculty and research students involved in serious computing on campus is about 35 in the areas: Computational Material Science, density functional theory applications, Nonlinear dynamics, atmospheric science, Quantum chemistry, molecular modeling, The departments involves are Physics, chemistry, computer science, Bioinformatics and Biotechnology.

- Four schools/ centers namely Centre for Simulation and Modeling, School for scientific computing, Centre for Network Computing and Centre for Bioinformatics would immensely benefit from Grid computing activity in terms of

- Development of trained manpower

- New paradigms and code development

- Development of New Tools

- We expect substantial benefit from enhance computing power at research front.

- The grid computing collaborative project would offer exciting and unparallel opportunities for carrying out projects at graduate and postgraduate level. B.E, M. Sc. in computer science, Computer engineering. Pune University Of Pune is known to have an excellent pool of such talent

### Key personnel

Prof. Dilip Kanhere (physics.unipune.ernet.in/~kanhere/) (PhD, 1976, IIT Kanpur): his reaserch interests are in the area of theoretical condensed matter physics, with particular enphasis on its computational aspects. Specific ares of research include: Monte Carlo methods / Ising model, electronic structure, atomistic simulation of nanoclusters. He is presently also Director of the Center for Network Computing, University of Pune.

Professor S R Gadre, Professor of Chemistry, Director, School for scientific computing.

Prof Gadre's main research interests are in applications of quantum  chemistry to a variety of problems. He has a very active research group and uses large scale computing facilities at Pune and other places including PARAM parallel machine of CDAC.

He has over 150 publications in this area.

## P09- SAHA Institute Calcutta

### Profile

Saha Institute of Nuclear Physics (SINP) (see http://www.saha.ac.in) is a autonomous National Research Institute which is under the administrative control of Department of Atomic Energy, Government of India. SINP was founded in 1951 and is recognized internationally for its research activities in Physical and Biological Sciences. A substantial number of faculties are also involved in teaching at various universities. At present, the institute has about 135 faculties, 25 poct-doctoral fellows and 80 graduate students. The total staff strength is about 650.

### Role in the project

The SAHA High Energy Physics group is taking part in the ALICE experiment  planned at the CERN Large Hadron Collider (LHC). In particular Dr Chattopadhyay is the Project Leader of the Indian Dimuon Collaboration in ALICE. He is also the member of the Steering Committee of “India-ALICE Collaboration” and is a member of the Steering Committee of “grid Computing for CMS and ALICE – Setting up of a TIER 2/3 Centres in India”.  These Computing Centres will provide services for the LHC experiments activities in India in cooperation with the LHC Computing Grid project.

Therefore the Saha group can give an excellent contribution, within the EU-IndiaGrid project in setting up an early use of the pilot grid for High Energy Physics Applications.

### Key Personnel

Dr. Sukalyan Chattopadhyay, born in Kolkata in 1963, graduated in Physics at University of Kolkata in 1985, is a professor at SINP where he is working since 1995.  He has done his Ph. D in 1994 on High Spin Nuclear Structure Studies. Since 1997, he has been working in the ALICE collaboration at CERN. He has published 25 research papers in reputed International journals. Presently, he is the Project Leader of the Indian Dimuon Collaboration in ALICE. He is the member of the Steering Committee of “India-ALICE Collaboration” and is a member of the Steering Committee of “grid Computing for CMS and ALICE – Setting up of a TIER 2/3 Centres in India”.

Prof. Pradip Roy

He is an associate Professor in the High Energy Physics division of Saha Institute. His research interest is 'Phenomenology of Quark-Gluon-Plasma'.

## P10-  Centre for Development of Advanced Computing Bangalore

### Profile

The Centre for Development of Advanced  Computing (http://www.cdac.in) is an autonomous scientific  society of the Department of Information Technology, Ministry of Communication and Information Technolgy (MCIT), Government of India. It is primarily an R&D institution involved in the design, development and deployment  of electronics and advanced information technology (IT) products and solutions. It  is a multi-locational and multi activity organization spread out at 10 locations with 14 laboratories.

The technologies that C-DAC has addressed in recent years include High Performance Computing (HPC) and Grid Computing, Multilingual Computing and related areas, Power Electronics, Agri-electronics, Real time systems, Embedded systems and VLSI design, Information Security and internet technologies, Software (including OSS/Linux), Multimedia, Graphics and database technologies, Geomatics, Health Informatics, e-Governance and ICT for addressing digital divide.

Recently, C-DAC has initiated the “National  Grid Computing Initiative : GARUDA” project which will connect 17 cities across the country in its Proof of Concept (PoC) phase with an aim to bring grid networked computing  to research labs and industry. GARUDA aims at strengthening and advancing scientific and technological excellence in the area of Grid and Peer to Peer technologies. To achieve its objective, GARUDA brings together a critical mass of well established researchers from 45 research laboratories and academic institutions that have planned an ambitious program of activities.

### Role in the project

C-DAC will collaborate with several partners in India an Europe for research and technology development of various areas of grid computing  including high speed communication network. C-DAC will be also able to disseminate new technologies among the research community by conducting periodic training and workshop in various parts of India.

### Key Personnel

Mohan Ram is the Chief Investigator for the GARUDA National Grid Computing Initiative. He also heads the C-DAC Centre at Bangalore, which houses the terascale supercomputer – the PARAM Padma. The Centre has more than 140 members, with a large group working in system software for the PARAM series of Supercomputers and also groups working in real time systems, heritage computing, digital libraries, business projects and training activities.

Mohan Ram has made significant contributions to the design, development and deployment of PARAM Padma at C-DAC’s Terascale facility (CTSF) in Bangalore. He also led the initiative, which was responsible for placing the PARAM Padma in the June 2003 list of Top500 supercomputers in the world. He has also made significant contributions to the system architecture and software technologies for the complete PARAM series of high performance systems. He is the Chief Architect of C-DAC’s HPCC Software, which provides a flexible parallel and distributed software environment for Unix clusters.

Mohan Ram is involved in several professional activities and has held various positions in technical groups and societies. He has authored several technical reports and has publications in national/international Conferences. He has received the C-DAC PARAM award for excellence on several occasions. He did his M.Tech in Computer Science from the Indian Institute of Technology, Madras and was also an IIT merit scholar. His research interests include computer architectures, system software, cluster and grid computing.

Dr. Subrata Chattopadhyay (BE from REC, Durgapur, M.Tech from IIT, Kanpur and Ph.D in Metallurgical Engineering from University of British Columbia, Canada, 1986) is currently head of System Engineering and Networking Group at C-DAC, Bangalore.  He was involved in setting up the PARAM Padma, Supercomputing facility and the formation of HPC user group and address their requirements.  He has also contributed to the setting up of high speed communication fabric of GARUDA and looking at the challenges of deploying grid middleware across various platforms of supercomputers.

Previously he worked at Mirronex Technologies Pvt. Ltd., as systems and data center manager, Chemical Industries Consulting Bureau as Head of IT Division, Jindal Vijaynagar Steel Ltd. for setting up IT systems in a green field project and National Metallurgical Laboratory, Jamshedpur as a Scientist at Computer Applications Division.  He has authored about 20 technical papers to his credit.

His major areas of interest include high performance computing, grid computing and process modeling and simulation of material processes.

Dr. Prahlada Rao, currently working as Head of  System Software Development Group,  C-DAC,  Bangalore.   Passed B.Tech (1979) in Electrical and Electronics Engineering  from  College of Engineering, JNTU with Distinction,  M.Tech  (1981) in Control Systems Engineering from  Indian Institute of Technology (IIT)-Kharagpur, and  Ph.D (1995) in Computer Science & Automation Department , Indian Institute of Science(IISc), Bangalore.

Earlier worked as  Advisory R&D Engineer and Deputy General Manager for Software Development (2000-04)  in IBM Global Services India Pvt Ltd, Bangalore, worked  as Group Leader at ST Microelectronics (1998-2000), worked as Technical Manager (2004-05) at Agere Systems India Pvt Limited,  Bangalore, Mentor Graphics (1997-98),  and Worked at Hindustan Aeronautics Ltd  (HAL), Hyderabad, Bangalore  during 1982-90 on Avionics and  Real time Computing R&D. Worked on S/W Tools Development,  Parallel Computing ,  Evolutionary Computing,  Real Time Computing ,  Aeronautics,   Optimization Algorithms in VLSI, and Genetic  Algorithms.

He was a Nominated member for the Technical Experts Council IBM Academy of Technology 2003-04, and  worked as Task force Member for P-CMM Core Team, at IBM.  FPGA, ISO, and SW-CMM Task force Member  at STMicro.  He was an Invited Speaker to WorkShop on Soft Computing-Applications, Sri Satya Sai Institute of Higher Learning, and Invited Faculty for MS Program  BITS, Pilani  during 2002-04. Served as Program Committee Member of CSI Annual Conf-1995 and reviewer  for International  Conf VLSI Design, Evolutionary Computation, SPDP and  ICPP. He authored 10 Journal and Conference papers, and holds 1-US Patent.

His major areas of  interest are   Grid Computing, Cluster Computing, Networking, Algorithms development,  Intellectual Property  &  Innovations  and  Academic Interactions.

Dr. Vijayraghavan Sundararajan received degrees of B.Sc and M.Sc in Physics from Madras University and Ph.D in Physics from Anna University, Chennai in 1989.  After a brief post-doctoral position at University of Pune, he worked as a lecturer there till March 1994.  During this tenure, he visited International Centre for Theoretical Physics, Trieste, Italy for about 14 months during 1992-93.  Since April 1994 he has been working at Centre for Development of Advanced Computing (C-DAC), Pune.  Currently he is the coordinator of the Scientific and Engineering Computing Group which spearheads the applications on the high performance computing platforms.

He was a visiting associate professor at Institute of Materials Research and Centre for Inter-disciplinary studies at Sendai, Japan for about five months during 2000-01 and later a guest scientist at the German Cancer Research Centre, Heidelberg for about 15 months.  His major areas of research interest are protein structure prediction multi scale modeling and simulations, applied evolutionary computing, high performance computing and Grid computing.  He has published about 45 research articles to his credit.

Ms. Akshara Kaginalkar (M.Sc in Solid State Physics at University of Pune, India) is team coordinator of Computational Atmospheric Science Group at C-DAC, Pune.

Ms. Akshara has worked extensively in scientific computing.  She was involved in the development of parallel processing applications for ab-initio electronic structure calculations, cellular automata.  Currently working in computational atmospheric science.  Major areas in research are parallelisation of medium range weather forecast application, benchmark of HPC with atmospheric models, design air pollution modeling system, automated workflow for real time weather forecast system.  Has contributed in software engineering processes for CMM implementation in C-DAC.

She has presented papers in international conference and workshop at National Centre for Atmospheric Research (NCAR), USA and European Centre for Medium Range Weather Forecast (ECMWF), UK and Institute of Numerical Mathematics (INM), Russia.  She has worked on collaborative projects with Indian research institutes and with NCAR, USA, University of Lilie, France, University of California, Riverside, USA, United States Asia Environment Partnership (USAEP), INM, Russia.

## P11 Bhabha Atomic Research Centre (BARC), Mumbai, India

### Profile

The Bhabha Atomic Research Centre (http://www.barc.gov.in ) is an R&D Organisation under Department of Atomic Energy (DAE), Government of India. It is a Multi-disciplinary R&D institution involved in the design, development and deployment of detector & sensor electronics and advanced information technology (IT) products and solutions. It is a multi-location and multi activity organization spread across 33 different locations with 4 R&D laboratories. BARC has been actively engaged in R&D in high performance computing (HPC) in the areas of Parallel Processing Supercomputers and Grid Computing.

BARC has taken a lead in DAE-CERN collaboration, contributing in many areas. DAE is also actively involved in the design, development and supply of LHC magnets, Power supplies, LHC control software, Data Acquisition System, detectors at CERN for the past few years. Indian scientists are taking active part in CMS and ALICE experiment. To support researchers with required infrastructure, India has setup regional Tier-2 of CERN. This center would provide access for various Universities and Indian collaborators, LCG Data Grid services from India.  Two Tier-2 centers one at TIFR, Mumbai with 34 Mpbs international leased link to CERN mainly for CMS experimentalist, which in turn will have gateway for ALICE center at Saha Institute/VECC Kolkatta and there will be number of TIER-3 centres located at user’s premises. DAE also developed number of Grid based Tools in the area of Fabric management, AFS file system and Data Management, which are being deployed by CERN in their phase-I of LHC Grid operations since July 2003. BARC also has test-bed setup of 32 nodes, each node consisting of PIV@1.7MHz with 640 MB RAM, Linux with OpenAFS, Globus Grid software, OpenPBS, EDT-II tools (LCG environment) and 2 Mbps Internet link to CERN to carryout software development and testing work of LCG project at CERN. So far during last two and half years number of software tools & packages such as correlation engine, grid operations monitoring, problem tracking system, Pool Database Backend Prototype, Scientific Library Evaluation and Development of Routines, AliEn Storage System and Andrews File System etc were developed by DAE team members under Computing Software agreement. Currently BARC engineers are working on the development of Extremely Large Fabric Monitoring and Grid Deployment & Operations software tools.

Recently, BARC has initiated the “DAE Grid” project which will eventually connect more than 33 locations across the country with an aim to bring grid networked computing to research labs and industry. DAE Grid aims at strengthening and advancing scientific and technological excellence in the area of Grid technologies. To achieve its objective, DAE-Grid brings together a critical mass of well established researchers from 33 laboratories and academic institutions that have planned an ambitious program of activities.

BARC has also signed an MOU with INFN in Feb 2006 to establish a Grid Research Hub in Mumbai and carryout advanced research in Grid Computing middleware software and deployment of scientific applications using Grid Computing in collaboration with INFN.

### Role in the project

BARC will collaborate with several partners from various Universities in India and Europe for research and technology development in Tier-I and Tier III set ups in CMS and ALICE including high speed communication network. BARC will be also able to disseminate new technologies among the research community by conducting periodic training and workshop in various parts of India. BARC has already held one such workshop during March 2006 in Mumbai and will be associated with the first CMS Tier-II workshop in November 2006 at TIFR, Mumbai.

### Key Personnel

Mr. P.S.Dhekne born in Ogalewadi, Karad, India in 1945 graduated in Physics at University of Pune in 1967 and B.E. with Distinction from University of Pune in 1970, is Associate Director Electronics & Instrumentation Group at BARC and there since 1977.  Shri Dhekne after graduation joined ECIL training school in computer discipline and served in many DAE institutions including ECIL, TIFR, VECC and BARC. Since 1988 he has ably shouldered the responsibility as an Officer-In-Charge, Computer Centre, BARC. Currently he is heading Computer Division, BARC. His major contributions include those of design and development of various models of ANUPAM parallel processing systems. He was also actively involved in the design and development of high-resolution (5120x4096) wall-size tiled display panel using commercially available multiple LCD’s (4x4) interfaced with a parallel cluster for large volume data visualization purpose, which is first of its kind in the country. He made innovative use of clustering approach as a low cost alternative to many solutions in computing such as Web Farms, Computing Farms, Load Balancing Cluster, High Availability Cluster, HPC Cluster, High-end Graphics and Grid Computing.

He worked at CERN (the European Laboratory for Particle Physics) as leading software development Group in LCG as DAE-CERN agreement to provide worth 7.5 MCHF. He published more than 40 papers on international Journals He is member C-RRB as India representative and also is member of the Grid Deployment Board.

Shri Dhekne is a winner of the Indian Nuclear Society Award INS-2001, presented by Honorable Prime Minister of India on Thursday 30th Oct 2002 for his pioneering work in development of parallel processing computer series ANUPAM. He was also elected as fellowship of National Academy of Engineers (FNAE) in 2002. Currently he has been awarded distinguish professor from National Academy of Engineering.

Mr. A.G.Apte,  Head Computer Division BARC, Mumbai and Project coordinator DAE-Grid in India

Mr. R.S.Mundada, Head of Supercomputing Research Facility, Computer Division, BARC and Team leader in development of middleware tools in LCG project.

## A.2  Sub-contracting

There are no specific sub-contracts already foreseen except those required for the organisation of the events and conferences. These possible subcontracts will essentially deal with logistics, catering, professional translations, printing of brochures, etc. It is planned to make use of conference fees and sponsorships to cover part of the expenses related to the events and conferences, the expected budget dedicated to these sub-contracts is evaluated to be 15 K€ for the whole duration of the project.

## A.3 Third parties

There are no third parties in the project.

## A.4 Funding of third country participants

The EU-IndiaGrid consortium is composed of 12 participants, 7 of which are Indian Institutions selected on the basis of their high level scientific and technical profile. For international co-operation partners the project complies to e-IRG’s focus on e-Infrastructure developments, specifically in the Asia-Pacific, Latin America and the US regions to reach the higher goal of further opening up the digital global market, the global advancement of science, the proliferation of knowledge and its global accessibility, and the world-wide enabling and support of education.6

The principal reason behind selecting ERNET (IN) as full consortium partner is due to the significant and positive links established back in 2003 with the European Commission when ERNET contributed to the first international co-operation forum on Information Communication Technology, the EuroIndia2004 event (www.euroindia2004.org), organised in New Delhi, and supported by the EC and Confederation of Indian Industry. As a result of this initial liaison, ERNET went on to collaborate on a series of EU initiatives, including close collaborations with the GEANT network and ERNET is now very familiar with the mechanisms of ICT European funded programs, as well as providing the most important state-of-the art nodal Intra and Internet network for Educational and Research Institutions in India.

C-DAC brings to the project his leading role on National Grid Initiative (GARUDA), which is extremely relevant for the main project goal, namely joining grids between Europe and India. In addition C-DAC allows the introduction of a new application in earth and atmospheric science. For their leading activity in Grid technology dissemination in India their role is important also within the Dissemination workpackage.

BARC and TIFR have been selected on the basis of their expertise in grid middleware, computing infrastructures and networking. They are top level profile Institutions in India in the fundamental research and in the information technology domains.

NCBS, SAHA, PUNE are all top level profile scientific institutes in the research domain of Biology, High Energy Physics and Condensed Matter Physics. TIFR has several diverse research areas which are within the interest of the project: astronomy and astrophysics, biological sciences, High Energy Physics.   All these Institutes have a consolidated collaboration with European Research Institutions and expertise in grid computing.

The requested EU-funded contribution for the Indian partners amount to 223 k€,  about 22% of the total. Their unfunded contribution is about 2/3 of the EU-funded contribution.

## A.5 Events Planner

|  |  |  |  | Related Project Events |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Calendar | EU-IndiaGrid project month | EU-IndiaGrid Workshops | Eu-IndiaGrid Training | BELIEF | EGEE-II | MONSOON | 6DISS | Measurable Impact (participants) |
| Oct-06 | 1 |  | Presence at Geneva event for BELIEF Brainstorming event | Geneva Medical Informatics event |  |  |  | 20 |
| Nov-06 | 2 |  | Intervention on hands-on training demo during IST at Monsoon stand | Helsinki IST |  | Raising awareness of FP7 India & presence at IST2006 | Global IpV6 Summit (Cannes, FR) | 60 |
| Dec-06 | 3 | High Energy Physics | 2-5 days of training in India | New Delhi Conference |  |  |  | 85 |
| Jan-07 | 4 |  | Training exposure during MONSOON networking |  |  | Hyderabad (thematic Workshop) |  | 20 |
| Feb-07 | 5 |  | Training exposure during MONSOON networking |  |  | Chennai (thematic Workshop) |  | 20 |
| Mar-07 | 6 |  |  |  |  |  |  |  |
| Apr-07 | 7 |  | Training exposure during BELIEF networking | Dublin Openstandards/ quality assurance? |  | Mumbai (presenting results of collaboration) |  | 20 |
| May-07 | 8 |  |  |  |  |  |  |  |
| Jun-07 | 9 |  |  |  |  |  |  |  |
| Jul-07 | 10 | Condensed Matter Physics & Material Sciences | 3-4 days of training in India | USA |  |  |  | 80 |
| Aug-07 | 11 |  |  |  |  |  |  |  |
| Sep-07 | 12 |  | Extra Training during EGEE-II conference | Sao Paolo Conference (BR) | EGEE-II conference |  |  | 20 |
| Oct-07 | 13 |  |  |  |  |  |  |  |
| Nov-07 | 14 |  |  |  |  |  |  |  |
| Dec-07 | 15 |  |  |  |  |  |  |  |
| Jan-08 | 16 | General Project Conference with first results of Call 1 IST FP6 | 3-4 days of training in India |  |  |  |  | 150 |
| Feb-08 | 17 |  |  |  |  |  |  |  |
| Mar-08 | 18 |  |  |  |  |  |  |  |
| Apr-08 | 19 |  |  |  |  |  |  |  |
| May-08 | 20 |  |  |  |  |  |  |  |
| Jun-08 | 21 |  |  |  |  |  |  |  |
| Jul-08 | 22 | Earth Sciences & Disaster prevention Workshop | 2-5 days of training in India |  |  |  |  | 85 |
| Aug-08 | 23 |  |  |  |  |  |  |  |
| Sep-08 | 24 |  |  |  |  |  |  | 560 |

LEGEND:

extra presence either through training events or workshop representation with piggy-backed on existing events

Training and education are meant as actions for the dissemination of knowledge.

For a detailed discussion of the GILDA facility features and key advantages, see chapter 8.2, “Materials and Facilities”.

TIFR includes two participating Institutes: TIFR, Mumbai and NCBS, Bangalore

TIFR participates with two Institutes: TIFR-Mumbai and NCBS-Bangalore. In order to better understand the role and the activity of each institute we separate them indicating in the text and in all tables TIFR-Mumbai as “TIFR” and NCBS-Bangalore as NCBS

1 This list is not exhaustive and may be subject to change

Workpackage number: WP 1 – WP n.

Number of the contractor leading the work in this workpackage.

Overall effort (funded effort in the brackets). Unfunded effort is explicitly shown in the WP forms in Chapter 7.6

Relative start date for the work in the specific workpackages, month 0 marking the start of the project, and all other start dates being relative to this start date.

Relative end date, month 0 marking the start of the project, and all ends dates being relative to this start date.

Deliverable number: Number for the deliverable(s)/result(s) mentioned in the workpackage: D1 - Dn.

Deliverable numbers in order of delivery dates: D1 – Dn

Please indicate the nature of the deliverable using one of the following codes:

R = Report

P = Prototype

D = Demonstrator

O = Other

Please indicate the dissemination level using one of the following codes:

PU = Public

PP = Restricted to other programme participants (including the Commission Services).

RE = Restricted to a group specified by the consortium (including the Commission Services).

CO = Confidential, only for members of the consortium (including the Commission Services).

Milestones numbers in order of delivery dates: M1 – Mn

Activity that will produce this Deliverable

Month in which the Milestone is expected; months’ number from 1 to 24, month 1 marking the start of the project, and all dates being relative to this start date.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

Milestones are control points at which decisions are needed; for example concerning which of several technologies will be adopted as the basis for the next phase of the project.

This figure includes activities decided and organized in the 2nd year of the project but actually performed after the 24th month see T2.4 IS THIS ACCEPTABLE

An opinion by Roberto?  (taking into account the possibilità of some ‘permanent Gilda corners’ ?) Otherwise drop

TIFR participates with two Institutes: TIFR-Mumbai and NCBS-Bangalore. In order to better understand the role and the activity of each institute we separate them indicating in the text and in all tables TIFR-Mumbai as “TIFR” and NCBS-Bangalore as NCBS

In CPF forms the participation of the two Institutes TIFR-Mumbai and NCBS-Bangalore is included within TIFR as project participant

6 European leadership in e-Science & Grids e-Infrastructures Reflection Group White Paper Version 2.0-pre 16 November 2004