# Life Sciences SSC Work Plan (Part B)

Please provide the following information for your SSC.  Much of this material is probably already available, but please reformat the material to conform to the structure below.  Do NOT change the structure of the sections or the tables.  They correspond exactly to certain sections of the Commission’s required project proposal format (specifically Part B).  Note that you should duplicate Section 1.4 for each of your SSC’s work packages.

The following are some general comments on filling in the work plan:

- The reason for having the SSCs at all is to create a hub of activity and expertise to coordinate and to manage the use of grid technology (and the grid infrastructure) by a particular scientific community. Common goals include: 1) providing a "repository" of experience for safeguarding grid knowledge/expertise in the community and 2) deepening grid knowledge for current users and expanding the number of people within the community using grid technology.  The attached overview of the proposal has some concrete topics that should be treated by each SSC.  (See the last section.)

- The objectives of a work package need to describe an outcome or goal, not an activity.  For example, a "liaison" between groups is not an objective; "encouraging/promoting/providing bi-lateral communication to ensure that service X conforms to our needs" is.  This has further implications for the rest of the work plan.  The deliverables and milestones should be clearly tied to the stated objectives and measure progress towards achieving them.  The risks must be those unfortunate incidents that would prevent those objectives from being achieved or achieved in a timely manner.  Issues that the work package addresses within the community are justifications for the work package, not risks!

Changes from V1 to V2:

- Add general advice for completing work plan.

- Add a short description of the SSC.

- Simplify partner information in this document.  Provide detailed information in a separate spreadsheet available on trac.

- Add title for each work package to the header of the description.

- Change in work package numbering.

- Group work packages by activity type and list groups in the order NA, SA, JRA.

- Change label for times from Project Month (PM) to just (M) to avoid confusion with Person-Month.

- Update the deliverable and milestone table.

- Add section for Additional Costs.

- Add impacts section.

- Life Sciences SSC

  - SSC Description

Provide a short (half page) description of the corresponding SSC.  This description must include 1) the scope of the SSC (i.e. the targeted community), 2) an estimate of the size of that community in Europe, 3) current state of grid use within that community, and 4) principal services to be offered by the SSC to the targeted community.

The LSSSC user community covers all scientific activities relevant to biology and medicine.  The LSSSC aims at enabling researches for understanding the laws of life and improving healthcare in developed countries but also at using the grid to address digital divide and support medical development.

LSSSC covers the scientific perimeter of the following ESFRI design studies:

- BBMRI, European Biobanking And Biomolecular Resources

- EATRIS, The European Advanced Translational Research Infrastructure

- ECRIN, Infrastructures For Clinical Trials And Biotherapy

- ELIXIR, Upgrade Of European Bioinformatics Infrastructure

- INFRAFRONTIER, Infrastructure for Phenomefrontier and Archivefrontier

- INSTRUCT, Integrated Structural Biology Infrastructure

Relevant to the LSSSC activity is also the field of biodiversity where the LifeWatch design study is also exploring the opportunities for using grid technology.

The Life Sciences community has been for several years the second largest user of grid resources after High Energy Physics. The Biomed Virtual Organization on EGEE accounts for about 5% of the consumed resources.

However, the use of e-infrastructures  is still restricted to a subset of the community and the major challenge for the LSSSC is to foster a broader adoption by the provision of services.

If we look for instance at the molecular biology community, it appears very clearly that most of its members are not interested to port applications to grids. They either prefer to use bioinformatics portals for the analysis of their data or define their own analysis pipeline using their favorite data analysis environment. For these users, grid portals are not relevant and the call to grid resources must be transparently integrated into the existing services.  Within the context of the EMBRACE Network of Excellence (http://www.embracegrid.info) funded by the European Commission within FP6, we have explored the relevance of Grid and Web services technologies to address specific requirements of molecular biology for data integration and analysis. The EMBRACE consortium has proposed the approach of Service Oriented Architectures (SOA) and Web services as defined by the W3C to increase the general interoperability of the resources.  More than 800 bioinformatics web services are already available on the EMBRACE registry at http://embraceregistry.net/ which provides a collection of available services, documentation and dynamic information on their status. The EMBRACE registry is the forerunner of the newly launched BioCatalogue (http://www.biocatalogue.org), developed by UoM and EMBL-EBI.  The BioCatalogue already registers over a 1000 services. Workflow tools like Taverna (http://www.taverna.org.uk) allow interactive definition of data analysis pipelines where these services are called and executed using the clients listed on the registry.  These services may well be Grid services; for example Taverna has plug-ins to execute over ARC (courtesy of the EU project KnowARC) and gLite (courtesy of CNRS as part of EGEE II).

The services to be provided to the community are the following

- scientific gateways under the form of grid portals for on demand access to grid resources

- bioinformatics and medical informatics web services running transparently on grid resources

  - Call Objectives

Please describe how your SSC will address the following objectives.  This should be a high-level description, so please limit the response to a couple of paragraphs for each objective.  Not all SSCs need to address all of the objectives.  If your SSC does not address one of them, please just write “Not applicable”.

- Deployment of e-Infrastructures in research communities in order to enable multi-disciplinary collaboration and address their specific needs.

Response: the SSC will leverage the work of several European projects (EGEE, EMBRACE, eLico, e-NMR, Health-e-Child VLe,…) to provide services for accessing the resources of the National Grid Initiatives federated in the European Grid Initiative to the research communities in molecular biology, medical imaging, drug discovery and next generation sequencing. Through the involvement of key European institutes or associations, it will foster the adoption of grids and the use of EGI resources by the Research Infrastructures that will map the field of life sciences in the coming years .

- Deployment of end-to-end e-infrastructure services and tools, including associated interfaces and software components, in support of virtual organisations in order to integrate and increase their research capacities.

Response: the Life Sciences SSC will operate and improve the services of the Biomed Virtual Organization which was the EGEE catch-all VO for life sciences, which accounted for more than 90% of the scientific production in life sciences on this infrastructure and already provided access to more than 20.000 CPUs in Europe and beyond in 2009. The goal of the SSC is to improve the services offered by the VO in the following ways:

- Extend resources accessible to the VO users beyond those operated by gLite to resources operated by ARC and UNICORE

- Develop tools allowing users of the scientific gateways to access resources operated by the different middlewares supported by UMD (gLite, ARC, UNICORE)

- Improve the monitoring of the resources using existing tools like the Dashboard

- Maintain, promote and enrich a catalogue of grid services for healthcare. The catalogue will be developed within the framework of the EGI_PROPER proposal and be complementary to the BioCatalogue for molecular biology.

- Building user-configured virtual research facilities/test-beds by coalition of existing resources (e.g. sensors, instruments, networks, and computers) from diverse facilities, in order to augment the capacities of research communities for real world observation and experimentation.

Response: the Life Sciences SSC will provide support to the Research Infrastructures in the field of life sciences wishing to develop testbed and virtual research facilities. Its role is not to develop its own facilities but rather to help ESFRIs to develop their own Distributed Computing Infrastructures and fully take advantage of the services offered by EGI.

- Addressing human, social and economic factors influencing the creation of sustainable virtual research communities as well as the take up/maintenance of e-Infrastructure services by communities.

Response: the Life Sciences SSC will address the fragmentation of the virtual research communities in Europe. It seems today that each middleware stack has its own user community in life sciences. The Life Science SSC will take the following initiatives to break the walls between these communities:

- it will promote the exchanges between the users of the different middleware stacks (gLite, KnowARC, UNICORE) through its support to joint events like the HealthGrid conference

- it will identify and adopt already existing tools for transparent access to resources operated by different middleware stacks Like workflows or distributed query processors or portals or enterprise platforms.

- Integrating regional e-Infrastructures and linking them to provide access to resources on a European or global scale.

Response: the Life Sciences SSC will build upon the success of the WISDOM initiative which received support from several regional e-infrastructures (AuverGrid, COMETA, EELA, EUMEDGrid, EUChinaGrid, SeeGrid, TWGrid) including e-infrastructures in the United States (Digital Ribbon, OSG).  Several partners of the SSC (CERM, CNRS, CSC, HealthGrid, IBRB, INFN, UPV) will play a coordination role with projects such as AuverGrid, COMETA, EUAsiaGrid, EUIndiaGrid, EUMEDGRID-Support, NDGF, SEEGrid. The SSC will be able to provide support to the biomedical activities of the regional e-infrastructures while they will be able to contribute resources to global initiatives.

  - Interactions With Other SSCs

Please list possible interactions/collaborations with the other SSCs involved in this project.

Please also list possible interactions/collaborations with SSCs that are NOT involved in this project

| SSC name | Technical collaboration | Scientific collaboration | Other |
| --- | --- | --- | --- |
| Complex sciences |  | Emerging diseases monitoring and modelling |  |
| High Energy Physics | AMGA, Dashboard, GANGA |  |  |
| Computational Chemistry | Deployment of Molecular Dynamics software codes |  |  |

Interaction/collaboration with other SSCs involved in this project

| SSC name | Technical collaboration | Scientific collaboration | Other |
| --- | --- | --- | --- |
| Dissemination |  |  | Coordination of dissemination efforts |
| Training | Support to training events | Support to training events | Coordination of training efforts |
| Application porting | Sharing of tools and expertise | Support to application porting |  |

Interaction/collaboration with SSCs outside this project

  - Partners

Please provide a list of partners that will be involved in your SSC.  If a partner will participate but will not receive funding from the Commission (i.e. is completely “unfunded”), please indicate that in the table.

Please fill in the information concerning the scientific and administrative contacts in the summary excel spreadsheet that can be found with the other documents on trac: https://trac.lal.in2p3.fr/EGISSC/wiki/Proposal.

| Acronym | Full Name | Unfunded | Country |
| --- | --- | --- | --- |
| AMC | Academic Medical Center of the University of Amsterdam | No | Netherlands |
| CERM | Magnetic Resonance Center | No | Italy |
| CNR | Consiglio Nazionale delle Ricerche | No | Italy |
| CNRS | Centre National de la Recherche Scientifique | No | France |
| CNU | Chonnam National University | Yes | Korea |
| CSC | CSC – IT Center for Science Ltd | No | Finland |
| EBI | European Bioinformatics Institute | No | UK |
| EMBnet | European Bioinformatics Institute, SLU | No | Sweden |
| HealthGrid |  | No | France |
| HES-SO | Haute Ecole Spécialisée de Suisse Occidentale | No | Switzerland |
| INFN | Istituto Nazionale di Fisica Nucleare | No | Italy |
| IBRB | Institute of Biological Research & Biotechnology | No | Greece |
| SIB | Swiss Institute of Bioinformatics | No | Switzerland |
| UoM | The University of Manchester | No | UK |
| UPV |  | No | Spain |

  - Work Package Coordination (NA.LS.2)

Please duplicate this section for each work package of your SSC.  Change the fields in angle brackets to the values appropriate for the work package.  Use the activity type for TYPE (NA, SA, or JRA), the SSC’s acronym for the SSC (without “SSC”), and a sequential number starting at 1 for NUMBER within each type of work package.

Please use the project Month (M) to indicate the starting and ending months of a task.  If a task will last throughout the project, then the corresponding numbers are M01 and M36.

For the activity type, use RTD (Research and Technological Development or Joint Research Activity), COORD (Co-ordination or Networking Activity), or SVC (Service Activities).  You should not use MGT (Management of the consortium) as this is limited to just the coordination of the project as a whole.

    - Overview and Effort

| Work Package Number | NA.LS.2 |
| --- | --- |
| Start Date | M01 |
| End Date | M36 |
| Activity Type | COORD |
| Partner Acronym | Effort in Person-Months |
| CNRS | 17 |
| AMC | 7 |
| CERM | 7 |
| CNR | 3 |
| CSC | 4 |
| EBI | 24 |
| EMBnet | 6 |
| HealthGrid | 8 |
| HES-SO | 4 |
| INFN | 4 |
| IBRB | 2 |
| SIB | 1 |
| UoM | 1 |
| UPV | 2 |

    - Objectives

Please provide a concise, bulleted list of the objectives of the work package.  Each objective should be a single sentence that immediately conveys a goal of the work package

Coordination goals

- integrate the LSSSC activities with NGI activities

- develop synergies between NGIs

- develop complementarities

- VO coordination, resource allocation and monitoring of use

    - Description of Work

Please provide a detail description of the work to be carried out within the work package to meet the objectives stated above.  If there are multiple distinct 9oil9eties, then please identify these through subtasks.

Coordination with EGI dissemination SSC, NGI and Regional grid infrastructure dissemination structures (IBRB, INFN)

Coordination and management of the services provided by the Biomed VO

- Update list of VO members

- resource monitoring

- activity monitoring

- integration of resources operated by ARC in the biomed VO

    - Partner Contributions

Please describe concisely each partner’s contribution to the above work plan.  Provide a separate paragraph/section for each partner.  If the work plan is broken down into subtasks, then identify exactly which partners contribute to each subtask.

| Partner name | Contribution | Effort |
| --- | --- | --- |
| AMC | Coordination with EGI | 4PM |
| AMC | Coordination with Dutch NGI (NBIC BioAssist programme) | 1PM |
| AMC | Contribution to VO coordination, resource allocation and monitoring | 2PM |
| CERM | Coordination with INSTRUCT | 7PM |
| CNR | Coordination with Italian NGI and the Italian Bioinformatics Network | 1PM |
| CNR | Coordination with ELIXIR & BBMRI | 2PM |
| CNRS | Coordination of the SSC | 6PM |
| CNRS | Coordination of the work package | 6PM |
| CNRS | Coordination with French NGI | 1PM |
| CNRS | Contribution to VO coordination, resource allocation and monitoring | 4PM |
| CSC | Coordination with Finnish NGI | 1PM |
| CSC | Coordination of access to resources on NDGF | 3PM |
| EBI | Coordination with ELIXIR | 22PM |
| EMBnet | Coordination with ELIXIR | 6PM |
| HealthGrid | Coordination with LifeWatch | 4PM |
| HealthGrid | Contribution to VO coordination, resource allocation and monitoring | 4PM |
| HES-SO | Coordination of access to resources operated by ARC | 3PM |
| HES-SO | Coordination with Swiss NGI | 1PM |
| INFN | Coordination with EUMEDGRID-Support, EUAsiaGrid, EUIndiaGrid, Mediterranean countries and COMETA | 3PM |
| INFN | Coordination with NGI | 1PM |
| IBRB | Coordination with SeeGrid | 1PM |
| IBRB | Coordination with Greek NGI | 1PM |
| SIB |  |  |
| UoM | Coordination with UK NGI. Promotion with NBIC, DutchGrid and BioAssist programme. | 1PM |
| UPV | Coordination with EELA and South America | 1PM |
| UPV | Coordination with Spanish NGI | 1PM |

    - Deliverables and Milestones

Please list the deliverables and milestones for the work package.  You should try to minimize the overall number of deliverables as they have a large overhead.  However, you must propose enough deliverables such that the project reviewers will be able to gauge the success of the work package.  Milestones should correspond to important decision points in the work plan and/or major events.

Please order the entries by due date and give those dates in Project Months.  (M01 being the start of the project; M36 being the end.

| Risk | Impact | Occurrence Probability | Mitigation |
| --- | --- | --- | --- |
| Lack of interest from user communities | Few users | Low | Dissemination based on successes from EGEE and national/regional grid initiatives |
| NGIs do not respond | Disconnection between LSSSC 11activities and NGI 11activities – duplication of work | Medium: some NGIs are strongly connected to this proposal, some are not | Dissemination to the NGIs not represented in the proposal |

Please number the deliverables as D.<WP No.>.<SEQ> where <SEQ> is a sequence number starting at 1, for example D.NA.HEP.1.1.  For milestones use the same format with a leading “M”, for example, M.NA.HEP.1.1.  Use separate sequence numbers for deliverables and milestones.

“Nature” should be R = Report, P = Prototype, D = Demonstrator, or O = Other.

| No. | WP No. | Title | Lead Partner | Nature | Due Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
| M.NA.LS.1.1 | NA.LS.1 | Web site | CNRS | O | PM1 | LSSSC web site operational |
| D.NA.LS.1.1 | NA.LS.1 | Coordination report | CNRS | R | PM9 | Status report on coordination activities |
| D.NA.LS.1.2 | NA.LS.1 | Updated coordination report | CNRS | R | PM21 | Updated status report on coordination activities |

    - Risks

We must demonstrate that we’ve analyzed what can go wrong with our work plan and have planned contingencies if things do go wrong.  Please list possible risks for the work plan (both internal and external), their effects, and mitigation strategies.

  - Work Package Dissemination and Training (NA.LS.3)

Please duplicate this section for each work package of your SSC.  Change the fields in angle brackets to the values appropriate for the work package.  Use the activity type for TYPE (NA, SA, or JRA), the SSC’s acronym for the SSC (without “SSC”), and a sequential number starting at 1 for NUMBER within each type of work package.

Please use the project Month (M) to indicate the starting and ending months of a task.  If a task will last throughout the project, then the corresponding numbers are M01 and M36.

For the activity type, use RTD (Research and Technological Development or Joint Research Activity), COORD (Co-ordination or Networking Activity), or SVC (Service Activities).  You should not use MGT (Management of the consortium) as this is limited to just the coordination of the project as a whole.

    - Overview and Effort

| Work Package Number | NA.LS.3 |
| --- | --- |
| Start Date | M01 |
| End Date | M36 |
| Activity Type | COORD |
| Partner Acronym | Effort in Person-Months |
| EMBnet | 30 |
| AMC | 4 |
| CERM | 2 |
| CNR | 9 |
| CNRS | 6 |
| CSC | 1 |
| EBI | 2 |
| HealthGrid | 6 |
| HES-SO | 5 |
| INFN | 6 |
| IBRB |  |
| SIB |  |
| UoM | 2 |
| UPV | 3 |

    - Objectives

Please provide a concise, bulleted list of the objectives of the work package.  Each objective should be a single sentence that immediately conveys a goal of the work package

Dissemination goals

- Integrate the LSSSC in the research communities targeted

  - participation to existing events

- Promote the services offered by the LSSSC to the potential users

  - brochures

  - participation to events

  - collaboration with other dissemination efforts

- Promote the activities of the NGIs and regional grid initiatives in the field of life sciences

- Contribute to EGI User Forums

Training goals

- Provide training to application developers, to the use of grid services and to the use of high level tools on top of grid services (TAVERNA, WISDOM, Vle, MOTEUR, …)

- Provide training to access and use Life Sciences SSC services

- Provide training to the use of Biomed VO specific services

- Integrate grid in existing international training programmes in life sciences

- Address the digital divide and foster the use of grids for medical development

- Pursue the existing yearly biomed grid school

    - Description of Work

Please provide a detail description of the work to be carried out within the work package to meet the objectives stated above.  If there are multiple distinct 14oil14eties, then please identify these through subtasks.

Dissemination

- Organization of yearly LSSSC events in conjunction with other events

- Dissemination to the research communities involved in ESFRIs (BBMRI, INSTRUCT, ELIXIR, LIFEWATCH)

- Graphical design of LSSSC web portal and scientific gateways

- Contribution to EGI User Forums

  - promotion to life sciences user community including ESFRIs

  - joint demos and booths with regional grid infrastructures

Training:

- Coordination with EGI training SSC

- Organization of yearly biomed Grid schools

- Coordination with regional grid infrastructures for organizing biomed grid schools, including in developing countries

- Integration of grid tutorials into EMBnet training events

    - Partner Contributions

Please describe concisely each partner’s contribution to the above work plan.  Provide a separate paragraph/section for each partner.  If the work plan is broken down into subtasks, then identify exactly which partners contribute to each subtask.

| Partner name | Contribution | Effort |
| --- | --- | --- |
| AMC | Contribution/Coordination with regional grid training schools | 3PM |
| AMC | Coordination with EGI training SSC | 1PM |
| CERM | Dissemination to protein structure community and coordination with e-NMR | 2PM |
| CNR | Organization of yearly biomed school | 9PM |
| CNRS | Contribution to regional grid training schools | 3PM |
| CNRS | Dissemination to Asia, sub-Saharan Africa and North America | 3PM |
| CSC | Dissemination to Nordic countries | 1PM |
| EBI | Dissemination to life sciences community | 2PM |
| EMBnet | Web site operation | 6PM |
| EMBnet | Coordination with EGI dissemination SSC | 3PM |
| EMBnet | Dissemination to EMBnet network of partners | 6PM |
| EMBnet | Work package coordination 16 | 6PM |
| EMBnet | Coordination with EGI training SSC | 3PM |
| EMBnet | Organization of training events within EMBnet network | 6PM |
| HealthGrid | Web site graphical design | 2PM |
| HealthGrid | LSSSC Scientific Gateways graphical design | 2PM |
| HealthGrid | Organization of LSSSC workshop at HealthGrid conferences | 2PM |
| HES-SO | Dissemination to the medical informatics community | 2PM |
| HES-SO | Training for the medical informatics community | 3PM |
| INFN | Contribution to regional grid training schools Provision of the GILDA t-infrastructure to training events | 6PM |
| UoM | Contribution to training events for the use of BioCatalogue, Taverna and MyExperiment on the grid | 2PM |
| UPV | Contribution to regional grid training schools | 2PM |
| UPV | Dissemination to South America | 1PM |

As support to the LSSSC training events, INFN will provide its GILDA t-Infrastructure used so far with success in many grid training events, some of them specific for the life science community in projects like BioinfoGRID and e-NMR, or  for the regional projects like EELA and EELA-2, EUAsiaGrid, EUChinaGRID, EU-IndiaGrid and EUMEDGRID,.

INFN can also provide as unfunded contribution its virtual training facility based on Adobe Connect Pro and Adobe Connect Training that has already been successfully used in the International Winter School of Grid Computing 2009 (IWSGC’09).

    - Deliverables and Milestones

Please list the deliverables and milestones for the work package.  You should try to minimize the overall number of deliverables as they have a large overhead.  However, you must propose enough deliverables such that the project reviewers will be able to gauge the success of the work package.  Milestones should correspond to important decision points in the work plan and/or major events.

Please order the entries by due date and give those dates in Project Months.  (M01 being the start of the project; M36 being the end.

Please number the deliverables as D.<WP No.>.<SEQ> where <SEQ> is a sequence number starting at 1, for example D.NA.HEP.1.1.  For milestones use the same format with a leading “M”, for example, M.NA.HEP.1.1.  Use separate sequence numbers for deliverables and milestones.

“Nature” should be R = Report, P = Prototype, D = Demonstrator, or O = Other.

| No. | WP No. | Title | Lead Partner | Nature | Due Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
| M.NA.LS.3.1 | NA.LS.3 | Web site | CNRS | O | PM1 | LSSSC web site operational |
| M.NA.LS.3.2 | NA.LS.3 | LSSSC workshop at EMBnet conference | EMBnet | O | PM6 | Satelllite workshop at EMBnet conference |
| D.NA.LS.3.3 | NA.LS.3 | Biomed Grid school | CNR |  | PM 9 | First biomed Grid school |
| M.NA.LS.3.4 | NA.LS.3 | LSSSC workshop at HealthGrid conference | HealthGrid | O | PM12 | Satelllite workshop at HealthGrid conference |
| D.NA.LS.3.5 | NA.LS.3 | EMBnet training event | EMBnet |  | PM 15 | First EMBnet grid training event |
| M.NA.LS.3.6 | NA.LS.3 | LSSSC workshop at EMBnet conference | EMBnet | O | PM18 | Satelllite workshop at EMBnet conference |
| D.NA.LS.3.7 | NA.LS.3 | Biomed Grid school | CNR |  | PM21 | Second biomed Grid school |
| M.NA.LS.3.8 | NA.LS.3 | LSSSC workshop at HealthGrid conference | HealthGrid | O | PM24 | Satelllite workshop at HealthGrid conference |
| D.NA.LS.3.9 | NA.LS.3 | EMBnet training event | EMBnet |  | PM 27 | Second EMBnet grid training event |

    - Risks

| Risk | Impact | Occurrence Probability | Mitigation |
| --- | --- | --- | --- |

We must demonstrate that we’ve analyzed what can go wrong with our work plan and have planned contingencies if things do go wrong.  Please list possible risks for the work plan (both internal and external), their effects, and mitigation strategies.

Work Package User Support (SA.LS.1)

Please duplicate this section for each work package of your SSC.  Change the fields in angle brackets to the values appropriate for the work package.  Use the activity type for TYPE (NA, SA, or JRA), the SSC’s acronym for the SSC (without “SSC”), and a sequential number starting at 1 for NUMBER within each type of work package.

Please use the project Month (M) to indicate the starting and ending months of a task.  If a task will last throughout the project, then the corresponding numbers are M01 and M36.

For the activity type, use RTD (Research and Technological Development or Joint Research Activity), COORD (Co-ordination or Networking Activity), or SVC (Service Activities).  You should not use MGT (Management of the consortium) as this is limited to just the coordination of the project as a whole.

    - Overview and Effort

| Work Package Number | SA.LS.1 |
| --- | --- |
| Start Date | M01 |
| End Date | M36 |
| Activity Type | SVC |
| Partner Acronym | Effort in Person-Months |
| UPV | 18PM |
| AMC | 3PM |
| CSC | 2PM |
| UoM | 3PM |

    - Objectives

Please provide a concise, bulleted list of the objectives of the work package.  Each objective should be a single sentence that immediately conveys a goal of the work package

Achieve a large adoption of scientific gateways both from users and service providers in the life sciences user community

Promote and encourage the use of grid-enabled bioinformatics and medical informatics web services in the research community

Provide first line user support for the access to VO core services in collaboration with EGI user support teams

    - Description of Work

Please provide a detail description of the work to be carried out within the work package to meet the objectives stated above.  If there are multiple distinct 20oil20eties, then please identify these through subtasks.

Users developing and deploying Grid applications for health will surely meet doubts, problems and unsolved needs that might be solved by other experts in the field. There are different ways of providing support:

- Knowledge base. This will contain references to other general purpose documentation sources about Grid programming and deploying, but it will also develop new use cases based on the specific scenario and requirements of LS. This subtask will also generate a list of requirements coordinated with other SSCs for driving developers on new generation components.

- Ticket-based support request. Tickets on unexpected behaviour, failures or usage doubts are a very powerful tool to help particular users and to contribute to the knowledge base. However, this approach has been unefficient in many past experiences, mainly due to the lack of organisation and reward. This task proposes reducing those barriers by means of creating an explicit list of expertises and people, the creation of the figure of the ticket dispatcher, according to this expertise, and the implementation of a rewarding mechanism for the most active ticket-solvers with, for example, covering the registration to conferences in the field (such as Healthgrid).

    - Partner Contributions

Please describe concisely each partner’s contribution to the above work plan.  Provide a separate paragraph/section for each partner.  If the work plan is broken down into subtasks, then identify exactly which partners contribute to each subtask.

| Partner name | Contribution | Effort |
| --- | --- | --- |
| UPV |  |  |
| AMC | Support to new users | 3PM |
| UoM | Support for new Taverna users | 3 PM |

    - Deliverables and Milestones

Please list the deliverables and milestones for the work package.  You should try to minimize the overall number of deliverables as they have a large overhead.  However, you must propose enough deliverables such that the project reviewers will be able to gauge the success of the work package.  Milestones should correspond to important decision points in the work plan and/or major events.

Please order the entries by due date and give those dates in Project Months.  (M01 being the start of the project; M36 being the end.

Please number the deliverables as D.<WP No.>.<SEQ> where <SEQ> is a sequence number starting at 1, for example D.NA.HEP.1.1.  For milestones use the same format with a leading “M”, for example, M.NA.HEP.1.1.  Use separate sequence numbers for deliverables and milestones.

“Nature” should be R = Report, P = Prototype, D = Demonstrator, or O = Other.

| No. | WP No. | Title | Lead Partner | Nature | Due Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Support report |  | R | P12 | Status report of support activities |
|  |  | Support report |  | R | P24 | Status report of support activities |
|  |  | Support report |  | R | P36 | Status report of support activities |

    - Risks

We must demonstrate that we’ve analyzed what can go wrong with our work plan and have planned contingencies if things do go wrong.  Please list possible risks for the work plan (both internal and external), their effects, and mitigation strategies.

| Risk | Impact | Occurrence Probability | Mitigation |
| --- | --- | --- | --- |
| Shortage of interest | No work | Low | Dissemination |
| Too much interest | Cannot fulfill users expectations | High | Coordinate with external parties (regional programmes) for training of additional manpower |

  - Work Package Scientific Gateways (SA.LS.2)

Please duplicate this section for each work package of your SSC.  Change the fields in angle brackets to the values appropriate for the work package.  Use the activity type for TYPE (NA, SA, or JRA), the SSC’s acronym for the SSC (without “SSC”), and a sequential number starting at 1 for NUMBER within each type of work package.

Please use the project Month (M) to indicate the starting and ending months of a task.  If a task will last throughout the project, then the corresponding numbers are M01 and M36.

For the activity type, use RTD (Research and Technological Development or Joint Research Activity), COORD (Co-ordination or Networking Activity), or SVC (Service Activities).  You should not use MGT (Management of the consortium) as this is limited to just the coordination of the project as a whole.

    - Overview and Effort

| Work Package Number | SA.LS.2 |
| --- | --- |
| Start Date | M01 |
| End Date | M36 |
| Activity Type | SVC |
| Partner Acronym | Effort in Person-Months |
| HealthGrid | 18PM |
| AMC | 5PM |
| CERM | 9PM |
| CNR | 4PM |
| CSC | 6PM |
| CNRS | 3PM |
| HES-SO | 3PM |
| IBRB | 10PM |
| INFN | 3PM |
| SIB ? |  |
| UoM | 12PM |

    - Objectives

Please provide a concise, bulleted list of the objectives of the work package.  Each objective should be a single sentence that immediately conveys a goal of the work package

One of the major goals of the LSSSC is to enlarge the community of users of e-infrastructures in life sciences. It is crucial that users are able to access grid resources through different mechanisms. Through dedicated grid portals, users are able to deploy their application in a user-friendly way.  But it must be understood that grid portals are only one entry point. Indeed, the user communities in the field of life sciences are being structured around ESFRIs: each of these ESFRIs is going to have its own distributed computing and data infrastructure to which the LSSSC must be able to propose the right services. The LSSSC partners are directly involved in ELIXIR (distributed infrastructure for molecular biology), LIFEWATCH (infrastructure for biodiversity), INSTRUCT (infrastructure) and BBMRI (Biobanking and Biomolecular Resources Research Infrastructure). The objectives of this activity are to provide to users of these three ESFRIs as well as to rest of the community services for scientific data analysis on EGI.

The services to be provided by this work package are the following

- scientific gateways under the form of grid portals for on demand access to grid resources

- tools and services to create grid-aware or grid enabled  bioinformatics and medical informatics web services for execution on e-infrastructures and integration into pipelined analysis

Provision of these services requires a number of tasks:

- for the scientific gateways

  - definition of the list of requirements for each of the communities and ESFRIs targeted

  - Harmonization of the SG implementation technology. This will be done in collaboration with SG dedicated projects

  - Harmonization in the integration of existing tools and services  into the scientific gateways: design and conception of plug-ins

  - Customization and maintenance of the scientific gateways when required

  - Access to the BioCatalogue of Web Services and extension to Grid Services

- for the provision of grid-enabled  bioinformatics and medical informatics web services

  - definition of the list of requirements

  - design and implementation of tools  for wrapping bioinformatics and medical informatics tools into web services for execution on the grid

    - Description of Work

Please provide a detail description of the work to be carried out within the work package to meet the objectives stated above.  If there are multiple distinct 24oil24eties, then please identify these through subtasks.

Definition of requirements and liaison with the project providing the portal implementation(s)

Integration of existing tools and services of the molecular biology community   into the Life Science gateway: design and conception of plug-ins.

Integration of existing tools and services of the structural biology community   into the Life Science gateway: design and conception of plug-ins. (CERM & INFN)

Integration of existing tools and services of the biodiverstity community   into the Life Science gateway: design and conception of plug-ins. (HealthGrid ?)

Integration of existing tools and services of the HealthGrid community   into the Life Science gateway: design and conception of plug-ins. (HealthGrid -HESSO)

Integration of existing tools and services of the medical imaging community   into the Life Science gateway: design and conception of plug-ins. (AMC )

Integration of existing tools and services of the genetic population community   into the Life Science gateway: design and conception of plug-ins. (CNR)

Integration of existing tools and services of the microarray analysis community   into the Life Science gateway: design and conception of plug-ins. (IBRB)

| Partner name | Tool name | Field | Subfield |
| --- | --- | --- | --- |
| AMC | Vbrowser | Generic tool | Graphical front-end |
| CERM | e-NMR platform | Structural biology | Protein structure determination |
| CNR | LINKAGE | Bioinformatics | Linkage analysis |
| CNRS | MOTEUR | Generic tool | Workflow management |
| CNRS | WISDOM | Drug discovery | Virtual screening |
| CSC | SOMA2 | Drug discovery | Docking |
| IBRB | GRISSOM | Bioinformatics | Microarray analysis |
| UoM | BioCatalogue | Bioinformatics and Medical Web services |  |
| UoM | Taverna | Generic Tool | Workflow management System |
| UoM | myExperiment | Generic Tool | Workflow catalogue |
| SIB |  |  |  |
| … |  |  |  |

Table of the services to be integrated in the Scientific Gateways (to be completed by partners)

Description of the services to be integrated in the scientific gateway

SOMA2

SOMA2 is a web browser based workflow environment for computational drug design and general molecular modeling (http://www.csc.fi/soma). Purpose of the SOMA2 environment is to provide users an easy access to computational tools. SOMA2 hides all technicalities related to execution of scientific applications in complex computing facilities. This allows users to focus in their actual scientific tasks. SOMA2 provides user friendly and intuitive WWW interface to applications that user can seamlessly connect into application workflows where several applications are automatically processed one after another. The SOMA2 environment also processes data provided by applications and offers direct result analysis view within the system. The SOMA2 environment is designed so that integration of new applications and tools into the system is easy. SOMA2 includes interfaces for, e.g., protein docking software (GOLD)

Vbrowser

The Virtual Resource Browser (Vbrowser, http://www.vl-e.nl/vbrowser) is an interactive graphical front-end and framework to access grid resources (both data and web services). It is developed by the Informatics Institute of the University of Amsterdam.

MOTEUR

MOTEUR is a workflow management system developed at the CNRS Sophia Antipolis (http://modalis.polytech.unice.fr/softwares/moteur/start). Workflows can be started from a Vbrowser plugin and enacted on grids using various middleware (gLite, ARC). The platform MOTEUR+Vbrowser is currently successfully adopted by various biomedical researchers in France and The Netherlands, and it could be extended to a larger community.

e-NMR platform

The e-NMR platform is a comprehensive ensemble of integrated web services that are aimed at structural biologists, particularly those making use of NMR spectroscopy as a tool to investigate protein structure. It also includes applications for the investigation of macromolecular adducts that potentially exploit a wide variety of different experimental data. This platform has been initially developed within the FP7 e-NMR project, and its evolution is planned to be carried out in the context of a future external e-Infrastructure project, where it will be also supplemented with services relevant also to other applications in structural biology such x-ray and crystallography.

The activity of in this work package, carried out mainly by CERM in collaboration with INFN, will consist in supporting the integration and harmonization of the e-NMR platform with respect to the other frames for scientific gateways for the Life Sciences domain.

Luciano: description of LINKAGE

BioCatalogue (http://www.biocatalogue.org) is a expert and community curated catalogue of web services that are relevant and useful to the Life Sciences, which takes over from the EMBRACE registry. It is developed jointly between the University of Manchester UK and  EMBL-EBI; the latter host the catalogue.  The catalogue is a REST-based service itself with read and write APIs. We propose to (a) register and promote Grid Services  and (b) incorporate the BioCatalogue into the gateways.

myExperiment (http://www.myExperiment.org) is a community-sourced repository and social networking environment for scientific workflows of any kind of workflow system. It is developed jointly by the University of Manchester and the University of Southampton.  It already holds workflows developed by the Healthgrid community. The catalogue is a REST-based service itself with read and write APIs. We propose to (a) register and promote workflows such as those developed for MOTEUR, Taverna and other workflow systems and (b) incorporate myExperiment into the gateways.

Taverna (http://www.taverna.org.uk) is an open source scientific workflow management system designed to link together service based resources and enact dataflows. It has been widely adopted throughout Europe the USA, South America and SE Asia. The development is primarily at the University of Manchester.  It has plugins for gLite (developed by CNRS), ARC (developed by KnowARC) and Globus Toolkit 4 (developed by Argonne Labs/Manchester). We propose to consolidate the ARC/gLite execution from Taverna.

WISDOM

The deployment of large scale data challenges for in silico drug discovery since 2005 within WISDOM initiative has led to the development of a dedicated framework with specific features:

- interoperability: the data challenges have involved many grid infrastructures around the world so the framework was designed to allow easy deployment on multiple infrastructures

- scalability:  up to several thousands CPU must be simultaneously loaded and monitored

- distributed and secured data management:: input and output data must be securely stored according to a complex data model

The WISDOM production environment has been developed as the result of a collaboration between EGEE-III and EMBRACE and is used for large scale docking and bioinformatics analysis.

GRISSOM

The GRISSOM portal(GRids for In Silico Systems BiOlogy and Medicine) (www.grissom.gr) enables exploitation of GRID resources for DNA microarray distributed processing. It provides experts with a complete web-based solution for generic management, search and dissemination of biological knowledge in the context of gene expression patterns on a genomic scale. The platform is developed and deployed using open source software components. GRISSOM supports versatile analysis for both cDNA and oligonucleotide (Affymetrix/ Illumina) microarray data, encompassing among others data import, filtering, normalization, statistical selection, annotation, clustering, gene ontology based pathway analysis. The underlying algorithms are parallelized through the use of either MPI computing or Direct Acyclic Graph (DAG) Scheduler for optimal performance and flexible grid deployment. Through the use of web service technologies (WSDL language) GRISSOM can be encapsulated in other biomedical processing workflows through Taverna workbench, providing transparent access to its algorithms. The GRISSOM portal integrates a local repository of microarray data, complying to both MIAME and miniML (MIAME Notation in Markup Language)  annotation systems. GRISSOM foresees advanced security mechanisms regarding access control and data encryption, in order to ensure proper usage of grid computational resources and entrust data security.

    - Partner Contributions

Please describe concisely each partner’s contribution to the above work plan.  Provide a separate paragraph/section for each partner.  If the work plan is broken down into subtasks, then identify exactly which partners contribute to each subtask.

| Partner name | Contribution | Effort |
| --- | --- | --- |
| AMC | Requirements and liaison with Vbrowser developers | 1PM |
| CERM | Integration of the eNMR platform into the Life Sciences gateways. | 9PM |
| CNR | Human genome Linkage analysis for finding the position of human disease genes relative to known genetic markers. | 4PM |
| CNRS | Deployment and maintenance of MOTEUR service | 3PM |
| CSC | Grid enabling, customization and maintenance of SOMA2 environment | 4PM |
| CSC | Maintenance of scientific gateways and web services | 2PM |
| HealthGrid | WP coordination | 6PM |
| HealthGrid | Integration of services in the scientific gateways | 12PM |
| HES-SO | Integration of medical informatics web services | 3PM |
| IBRB | Integration of the GRISSOM platform for the microarray analysis community in a scientific gateway | 10PM |
| INFN | Integration into the Life Science gateway of tools and services dovelped in LIBI, e-NMR and regional projects: plug-ins design and implementation | 8PM |
| UoM | Maintenance of BioCatalogue for web Services; extension for Grid Services | 4PM |
| UoM | Taverna | 6PM |
| UoM | myExperiment | 2PM |
| SIB |  |  |
| … |  |  |

    - Deliverables and Milestones

Please list the deliverables and milestones for the work package.  You should try to minimize the overall number of deliverables as they have a large overhead.  However, you must propose enough deliverables such that the project reviewers will be able to gauge the success of the work package.  Milestones should correspond to important decision points in the work plan and/or major events.

Please order the entries by due date and give those dates in Project Months.  (M01 being the start of the project; M36 being the end.

Please number the deliverables as D.<WP No.>.<SEQ> where <SEQ> is a sequence number starting at 1, for example D.NA.HEP.1.1.  For milestones use the same format with a leading “M”, for example, M.NA.HEP.1.1.  Use separate sequence numbers for deliverables and milestones.

“Nature” should be R = Report, P = Prototype, D = Demonstrator, or O = Other.

| No. | WP No. | Title | Lead Partner | Nature | Due Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | VBrowser + MOTEUR demonstrator | AMC | D | P6 | Implementation of a medical imaging use case using the LS SSC VBrowser and MOTEUR service |
|  |  | Demonstration of the implementation of the eNMR platform | CERM | D | P12 | Implementation of a protein structure calculation and refinement use case |
|  |  | BioCatalogue integration | UoM | D | P6 | Integration of BioCatalogue in an example Bio Portal gateway |
|  |  | myExperiment integration | UoM | D | P12 | Integration of myExperiment in a Bio Portal |
|  |  | Taverna – Glite/ARC execution | UoM | D | P18 | Execution of example bioinformatics workflows using gLite and ARC services. |

    - Risks

We must demonstrate that we’ve analyzed what can go wrong with our work plan and have planned contingencies if things do go wrong.  Please list possible risks for the work plan (both internal and external), their effects, and mitigation strategies.

| Risk | Impact | Occurrence Probability | Mitigation |
| --- | --- | --- | --- |

  - Work Package Targeted Application Porting (SA.LS.3)

Please duplicate this section for each work package of your SSC.  Change the fields in angle brackets to the values appropriate for the work package.  Use the activity type for TYPE (NA, SA, or JRA), the SSC’s acronym for the SSC (without “SSC”), and a sequential number starting at 1 for NUMBER within each type of work package.

Please use the project Month (M) to indicate the starting and ending months of a task.  If a task will last throughout the project, then the corresponding numbers are M01 and M36.

For the activity type, use RTD (Research and Technological Development or Joint Research Activity), COORD (Co-ordination or Networking Activity), or SVC (Service Activities).  You should not use MGT (Management of the consortium) as this is limited to just the coordination of the project as a whole.

    - Overview and Effort

| Work Package Number | SA.LS.3 |
| --- | --- |
| Start Date | M01 |
| End Date | M36 |
| Activity Type | SVC |
| Partner Acronym | Effort in Person-Months |
| Coordinating partner | To be defined |
| AMC | 5PM |
| CNR | 2PM |
| CNRS | 2PM |
| CSC | 1PM |
| UPV | 13PM |

    - Objectives

Please provide a concise, bulleted list of the objectives of the work package.  Each objective should be a single sentence that immediately conveys a goal of the work package

Provide first line user support to application porting in collaboration with application porting SSC

    - Description of Work

Please provide a detail description of the work to be carried out within the work package to meet the objectives stated above.  If there are multiple distinct activities, then please identify these through subtasks.

Actors in the LS SSC can be classified among different criteria. If we consider Grid-usage awareness, we can identify clearly from top level users with challenging scientific problems and low capabilities on Grid usage and exploitation, to research groups with large expertise on the migration and exploitation of such infrastructures. There is a inherent need for collaboration, which should be the target of this subtask.

In order to make this collaboration happen, several issues must be faced:

- Awareness. An inventory of expertises and problems will be performed to identify the potential synergies. This inventory will be available and organised at different levels of detail. This will also include inventories of components, tools and even data.

- Communication. The LS SSC will foster the collaboration among groups creating thematic groups and communication tools.

- Confidence. Collaboration is based on mutual confidence. Mutual confidence cannot be imposed, but can be constructed more easily on top of signed agreements. The task will propose templates for IPR management, scientific cooperation agreements and other basic regulations. This could avoid medium-term misunderstandings and improve the quality of collaboration.

Support to the addition of plug-ins  on the scientific gateways, targeted towards service providers in the life sciences user community

Support to the provision of grid-enabled  bioinformatics and medical informatics web services, targeted towards service providers in the life sciences user community

Support to application porting through the scientific gateways

Support to application porting using grid-enabled bioinformatics and medical informatics web services

Support to application porting through the population genetics analysis scientific gateways

    - Partner Contributions

Please describe concisely each partner’s contribution to the above work plan.  Provide a separate paragraph/section for each partner.  If the work plan is broken down into subtasks, then identify exactly which partners contribute to each subtask.

| Partner name | Contribution | Effort |
| --- | --- | --- |
| UPV |  | 13PM |
| AMC | Support for application porting using the VBrowser/MOTEUR platform | 3PM |
| AMC | Targeted user support for experiment planning and monitoring | 2PM |
| CNR | Support to application porting through the population genetics analysis scientific gateways | 2PM |
| CNRS | Support for application porting using the VBrowser/MOTEUR platform | 2PM |
| CSC | Support for application porting (e.g. Chipster for microarray analysis and high-throughput sequencing; Auto-Rickshaw protein crystal structure determination platform) | 1PM |

    - Deliverables and Milestones

Please list the deliverables and milestones for the work package.  You should try to minimize the overall number of deliverables as they have a large overhead.  However, you must propose enough deliverables such that the project reviewers will be able to gauge the success of the work package.  Milestones should correspond to important decision points in the work plan and/or major events.

Please order the entries by due date and give those dates in Project Months.  (M01 being the start of the project; M36 being the end.

Please number the deliverables as D.<WP No.>.<SEQ> where <SEQ> is a sequence number starting at 1, for example D.NA.HEP.1.1.  For milestones use the same format with a leading “M”, for example, M.NA.HEP.1.1.  Use separate sequence numbers for deliverables and milestones.

“Nature” should be R = Report, P = Prototype, D = Demonstrator, or O = Other.

| No. | WP No. | Title | Lead Partner | Nature | Due Date | Description |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Support report |  | R | P12 | Status report of support activities |
|  |  | Support report |  | R | P24 | Status report of support activities |
|  |  | Support report |  | R | P36 | Status report of support activities |

    - Risks

We must demonstrate that we’ve analyzed what can go wrong with our work plan and have planned contingencies if things do go wrong.  Please list possible risks for the work plan (both internal and external), their effects, and mitigation strategies.

| Risk | Impact | Occurrence Probability | Mitigation |
| --- | --- | --- | --- |
| Shortage of interest | No work | Low | Dissemination |
| Too much interest | Cannot fulfill users expectations | high | Coordinate with external parties (regional programmes) for training of additional manpower |

  - Additional Costs

If you foresee additional costs associated with the project, then indicate the nature of those costs and the expected amount.  The project as a whole will have to decide policies on whether any costs other than effort will be claimed.

  - Impacts

Please list the expected impacts that will stem from the given work plan.  This should include both scientific impacts as well as any socio-economic impact.  Please concisely describe (one paragraph) each impact.

  - Sustainability plan

  - Summary of partner contributions

https://gilda.ct.infn.it.

http://www.bioinfogrid.eu.

http://www.enmr.eu/.

http://www.eu-eela.org/first-phase.php.

http://www.eu-eela.eu.

http://www.euasiagrid.eu.

http://www.euchinagrid.eu.

http://www.euindiagrid.eu.

http://www.eumedgrid.eu.

http://www.adobe.com/products/acrobatconnectpro.

http://www.adobe.com/uk/products/connect/productinfo/features/training/.

http://www.iceage-eu.org/iwsgc09/index.cfm.